## Work List
Exported on: 2026-10-07 13:28:21
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Khoja kua
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / GANDHWANI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722006046/DP/22012034524327 — सार्वजनीक कुप जमरा बयडीपुरा खोजाकुआ | Physically Completed | 335557.32 | 0 | 2021-04-10 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722006046/DP/22012034613765 — सार्वजनिक कूप निर्माण नयापुरा खोजकूआ | New | 0 | 0 | 2024-04-12
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722006046/IC/22012034892760 — Sarvjanik Kup Nirman Kamatpura Khojakuwa | New | 0 | 0 | 2025-11-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722006046/IC/22012034892761 — Sarvanik Kup Nirman Kakadpura Khojakuwa | New | 0 | 0 | 2025-11-08
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006046/IF/22012035274691 — Kapil dhara kup nirman Suresh Sevla khojakua | Approved | 234311.6 | 0 | 2024-10-02
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1722006046/IF/22012035277706 — Construction of Kapildhara Kup Nirman Endersing Jamsinh Khojakua | Ongoing | 198485.28 | 0 | 2025-04-10
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1722006046/IF/22012035277744 — Construction of Kapildhara Kup Dinesh Bharat Khojakua | Ongoing | 199685.11 | 0 | 2025-05-25
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006046/IF/22012035399472 — JGSA 2025 recharge structure kapil dhara kup nirman suresh sevla khojakua | Completed | 25899.46 | 0 | 2025-04-28 | 2026-08-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/197854 — Construction of IAY House -IAY REG. NO. MP-22-006-046-001/57 | Completed | 23490 | 0 | 2024-10-17 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/197870 — Construction of IAY House -IAY REG. NO. MP-22-006-046-001/54 | Completed | 23490 | 0 | 2024-10-17 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/198004 — Construction of IAY House -IAY REG. NO. MP-22-006-046-001/28 | Ongoing | 27000 | 0 | 2025-02-08
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/198027 — Construction of IAY House -IAY REG. NO. MP-22-006-046-001/52 | Ongoing | 27000 | 0 | 2025-02-08
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/198048 — Construction of IAY House -IAY REG. NO. MP-22-006-046-001/58 | Ongoing | 27000 | 0 | 2024-10-17
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/2569488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4174614 | Completed | 23490 | 0 | 2022-10-06 | 2026-07-24
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/2570105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4213838 | Ongoing | 27000 | 0 | 2022-10-06
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4141364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116230876 | Completed | 23490 | 0 | 2024-09-05 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4144961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116734471 | Ongoing | 27000 | 0 | 2024-07-25
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4359795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116919048 | Ongoing | 27000 | 0 | 2024-10-17
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4569660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116981065 | Ongoing | 27000 | 8400 | 2025-02-08
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4570221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116589085 | Completed | 23490 | 0 | 2024-12-19 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4572474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117543971 | Completed | 23490 | 0 | 2024-12-02 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4673517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117546058 | Completed | 23490 | 0 | 2024-12-02 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4673519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117548137 | Completed | 23490 | 0 | 2025-01-23 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4674168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116229709 | Completed | 23490 | 0 | 2024-12-02 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4694475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116734503 | Completed | 23490 | 0 | 2025-04-16 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4694961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116588999 | Ongoing | 27000 | 0 | 2025-11-27
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4694966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116590691 | Completed | 23490 | 0 | 2025-01-23 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4697640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116954622 | Ongoing | 27000 | 0 | 2025-11-27
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4697782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117548007 | Completed | 23490 | 0 | 2025-08-14 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4697783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117548506 | Ongoing | 27000 | 0 | 2025-09-08
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4697784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117548542 | Ongoing | 27000 | 0 | 2024-12-02
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4700273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116588930 | Completed | 23490 | 0 | 2024-12-02 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4701020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118612583 | Ongoing | 27000 | 0 | 2025-09-06
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4701022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118613125 | Completed | 23490 | 0 | 2025-04-24 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4701299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116230735 | Completed | 23490 | 0 | 2024-12-02 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4750871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116229490 | Completed | 23490 | 0 | 2025-01-23 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4750872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116229883 | Ongoing | 27000 | 0 | 2025-11-27
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4751354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116588851 | Completed | 23490 | 0 | 2025-06-27 | 2026-08-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4751356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116590621 | Completed | 23490 | 0 | 2025-09-08 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4751722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116955094 | Completed | 23490 | 0 | 2024-12-19 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4752749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116737380 | Completed | 23490 | 0 | 2025-01-23 | 2026-07-31
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4860033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117547966 | Completed | 23490 | 0 | 2025-05-08 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/4871026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115358001 | Completed | 23490 | 0 | 2025-07-15 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5248291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116736466 | Completed | 23490 | 0 | 2025-07-28 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5250523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120271463 | Ongoing | 27000 | 0 | 2025-09-07
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5255550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116589236 | Ongoing | 27000 | 14700 | 2025-09-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5268797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116229859 | Ongoing | 27000 | 0 | 2025-10-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5269610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116220362 | Ongoing | 27000 | 0 | 2025-11-12
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5272746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116589181 | Ongoing | 27000 | 0 | 2025-08-01
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5273917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116588816 | Ongoing | 27000 | 6300 | 2025-08-14
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5277164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116590657 | Ongoing | 27000 | 12600 | 2025-08-14
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5282223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116590642 | Completed | 23490 | 0 | 2025-07-28 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5283868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116736981 | Completed | 23490 | 0 | 2025-05-08 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5284787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106047690 | Physically Completed | 27000 | 0 | 2025-11-27 | 2026-09-06
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5288474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116954942 | Approved | 27000 | 0 | 2025-03-15
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5305956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118577000 | Ongoing | 27000 | 0 | 2025-04-16
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5317224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116230056 | Ongoing | 27000 | 0 | 2025-04-16
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5321361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117548645 | Ongoing | 27000 | 12600 | 2025-04-16
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5329693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116735967 | Ongoing | 27000 | 7000 | 2025-09-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5333763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117548765 | Completed | 23490 | 0 | 2025-05-08 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5339659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116230706 | Ongoing | 27000 | 8400 | 2025-04-16
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5401670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116735446 | Ongoing | 27000 | 0 | 2025-04-16
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5443561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116896945 | Ongoing | 27000 | 0 | 2025-04-16
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5450995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116229775 | Completed | 23490 | 0 | 2025-04-16 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5508253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107018523 | Completed | 23490 | 0 | 2025-05-08 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5510246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117547620 | Completed | 23490 | 0 | 2025-07-28 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5510248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117548424 | Ongoing | 27000 | 0 | 2025-11-27
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5511070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116229904 | Completed | 23490 | 0 | 2025-09-10 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5512043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116229981 | Completed | 23490 | 0 | 2025-09-08 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5512351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117476688 | Completed | 23490 | 0 | 2025-05-08 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5512455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105860632 | Completed | 23490 | 0 | 2025-05-08 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5635749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116588793 | Completed | 23490 | 0 | 2025-07-28 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5693558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120270900 | Ongoing | 27000 | 0 | 2025-11-27
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5694074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116954812 | Ongoing | 27000 | 0 | 2025-11-27
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/5787369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116230643 | Ongoing | 27000 | 0 | 2026-02-07
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006046/IF/IAY/6399612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117544903 | Approved | 27000 | 0 | 2026-08-04
DHAR / GANDHWANI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722006046/RC/22012034831075 — CONSTRACTION OF C.C. ROAD AT KHUMSINGH KE GHAR SE HANUMAN MANDIR TAK KHOJAKUWA | Approved | 0 | 0 | 2024-08-15
DHAR / GANDHWANI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006046/RS/22012034582038 — SBM SSP SHOKPIT Malpura School ke pass Khojakuwa | Physically Completed | 11999.97 | 0 | 2021-11-01 | 2026-08-21
DHAR / GANDHWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722006046/WC/22012034820200 — CTRA roof watar harweasting panchayat bhawan khojakua | Completed | 22229.14 | 0 | 2022-05-19 | 2026-08-07
DHAR / GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722006046/WC/22012034822310 — CTR ROOF WATER HARWESTING ms school khojakua | Completed | 22229.14 | 0 | 2021-11-01 | 2026-08-07
DHAR / GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722006046/WC/22012034822313 — CTRA Con.Of Rooftop Harvesting Patel pura Khojiya kova | Completed | 22229.14 | 0 | 2021-11-01 | 2026-08-21
DHAR / GANDHWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006046/WC/22012034960084 — CTRA Constr of Nistar Tank Khakhra wala Nala Khojakua | Physically Completed | 1485001.23 | 0 | 2022-05-19 | 2026-08-21
DHAR / GANDHWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722006046/WC/22012034963308 — ctranala trechiichig nirman kaya khojakua emli wala nala | Ongoing | 800000.23 | 0 | 2022-05-25
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006046/WC/22012035234027 — Construction of Sarwajanik Kup Malpura Kekdiya baba Khojakua | Approved | 0 | 0 | 2024-10-15
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006046/WC/22012035239404 — Construction Of Boulder Check Dam Nim Wala Nala Khojakua | Physically Completed | 498633.43 | 0 | 2025-01-28 | 2026-08-21
DHAR / GANDHWANI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722006046/WC/22012035254851 — तलाई निर्माण कार्य मालपुरा नाला खोजाकुआ | Ongoing | 364807.4 | 181800 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722006046/WC/22012035281529 — JGSA 2025 recharge structure sarvjanik kup nirman junakheda nayapura khojakua | Approved | 25899.46 | 0 | 2025-04-17
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722006046/WC/22012035281539 — JGSA 2025 recharge structure sarvjanik kup nirman junakheda baydipura khojakua | Approved | 25899.46 | 0 | 2025-04-17
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722006046/WC/22012035281543 — JGSA 2025 recharge structure sarvjanik kup nirman nayapura khojakua | New | 0 | 0 | 2025-04-17
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722006046/WC/22012035281545 — JGSA 2025 recharge structure sarvjanik kup nirman nayapura khojakua | Approved | 25899.46 | 0 | 2025-04-17
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722006046/WC/22012035281547 — JGSA 2025 recharge structure sarvjanik kup nirman malpura khojakua | Approved | 25899.46 | 0 | 2025-04-17
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722006046/WC/22012035281551 — JGSA 2025 recharge structure sarvjanik kup nirman patelpura khojakua | Approved | 25899.46 | 0 | 2025-04-17
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722006046/WC/22012035281563 — JGSA 2025 recharge structure sarvjanik kup nirman kamatpura khojakua | Approved | 25899.46 | 0 | 2025-04-17
DHAR / GANDHWANI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722006046/WC/22012035324739 — Parcolation Tank Khakhra Wala Nala Khojakua | Ongoing | 1479993.56 | 108900 | 2026-08-21
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722006046/WC/22012035324741 — Nistar Tatab Nirman Behda Wala Nala Khojakua | Approved | 0 | 0 | 2025-11-15
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722006046/WC/22012035324759 — Parcolation Tank Juna Kheda Wala Nala Khojakua | New | 0 | 0 | 2025-08-15
DHAR / GANDHWANI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722006046/WC/22012035324760 — Percolation tank juna Kheda wala Nala khoja Kuan | Ongoing | 1481838.9 | 51300 | 2026-08-21