## Work List
Exported on: 2026-10-14 08:02:36
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Malhera
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / GANDHWANI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722006065/DP/22012034444496 — सार्वजनीक कुप रावतपुरा मल्‍हेरा | Ongoing | 445000 | 0 | 2021-05-24
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006065/IF/22012034928388 — Kapildhara kup nirman keshri bai shiwalal malhera | Physically Completed | 271203.25 | 0 | 2022-05-27 | 2026-09-30
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006065/IF/22012034970718 — कपिलधारा कुप कालुसिंह रणसिंह मल्‍हेरा | Ongoing | 245705.28 | 0 | 2022-11-26
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006065/IF/22012034970992 — कपिलधारा कुप बलराम रामसिंह मल्‍हेरा | Ongoing | 255091.37 | 0 | 2023-05-19
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006065/IF/22012034973329 — कपिलधारा कुप लक्ष्‍मण मोतिया मल्‍हेरा | Ongoing | 254625.55 | 0 | 2023-06-24
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006065/IF/22012035036308 — Kapil dhara kup nirman mohabbat bheru | Ongoing | 283703.12 | 0 | 2023-06-23
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006065/IF/22012035038544 — kapil dhara kup nirman narsingh ganpat | Ongoing | 275146.12 | 0 | 2023-02-16
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006065/IF/22012035060760 — कपिल धारा कूप निर्माण सीताराम अमरसिंह | Ongoing | 269219.03 | 0 | 2023-07-09
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Masonry/CC Anicut for Individuals / Construction of Masonry Check Dam for Individual | Construction of Check Dam/Stop Dam | 1722006065/IF/22012035204347 — खेत तालाब निर्माण कार्य बुदेसिंह पिता मोतिया | New | 0 | 0 | 2024-04-12
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006065/IF/22012035443010 — JGSA 2025 khet talab nirman karya sikadar malhera | Physically Completed | 128570.81 | 0 | 2025-05-20 | 2026-07-30
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006065/IF/22012035443026 — JGSA 2025 khet talab nirman karya sikdar malhera | New | 0 | 0 | 2025-04-15
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006065/IF/22012035443045 — JGSA 2025 khet talab nirman karya revsingh malhera | Physically Completed | 131961.23 | 0 | 2025-06-03 | 2026-07-30
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006065/IF/22012035443055 — JGSA 2025 khet talab nirman karya parvat bhuvan malhera | Ongoing | 120684.66 | 0 | 2025-05-30
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006065/IF/22012035443068 — JGSA 2025 khet talab nirman karya budhiya malhera | Approved | 123878 | 0 | 2025-04-15
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006065/IF/22012035443078 — JGSA 2025 khet talab nirman karya laxman malhera | Ongoing | 125859.46 | 0 | 2025-05-30
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006065/IF/22012035443087 — JGSA 2025 khet talab nirman karya balram bheru malhera | Approved | 122498.49 | 0 | 2025-04-15
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006065/IF/22012035443094 — JGSA 2025 khet talab nirman karya sitaram amarsingh malhera | Ongoing | 147621.16 | 0 | 2025-05-21
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006065/IF/22012035443103 — JGSA 2025 recharge structure kapil dhara kup narsingh ganpat malhera | Approved | 25899.46 | 0 | 2025-04-15
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006065/IF/22012035443112 — JGSA 2025 recharge structure kalu khuman malhera | Ongoing | 25899.46 | 0 | 2025-05-30
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006065/IF/22012035443122 — JGSA 2025 recharge structure kapil dhara kup balram ramsingh malhera | Ongoing | 25899.46 | 0 | 2025-05-13
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006065/IF/22012035443135 — JGSA 2025 recharge structure kail dhara kup amarsingh bholiya malhera | Approved | 25899.46 | 0 | 2025-04-15
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006065/IF/22012035443153 — JGSA 2025 recharge structure kapil dhara kup laxman motiya malhera | Ongoing | 25899.46 | 0 | 2025-05-13
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006065/IF/22012035443167 — JGSA 2025 recharge structure kapil dhara kup rameshwar madan malhera | Ongoing | 25899.46 | 0 | 2025-05-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006065/IF/22012035528687 — JGSA 2025 khet talab nirman karya kansing jogiya malhera | Approved | 0 | 0 | 2025-04-15
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4546282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106807890 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4551955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113588767 | Ongoing | 27000 | 0 | 2025-04-10
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4557236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113815312 | Physically Completed | 27000 | 4200 | 2025-12-03 | 2026-08-30
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4681666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148520654 | Completed | 23490 | 0 | 2025-12-03 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4690329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113599164 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4690859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113801417 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4691233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115195372 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4691875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106224668 | Completed | 23490 | 0 | 2025-04-26 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4693630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114834152 | Completed | 23490 | 0 | 2025-11-09 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4703653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120823255 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4723674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147560935 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4727907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148525546 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4738630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106179147 | Ongoing | 27000 | 0 | 2025-11-29
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4740085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106416442 | Physically Completed | 27000 | 0 | 2025-09-13 | 2026-10-11
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4743671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113941834 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4745193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113599171 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4747673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115195557 | Ongoing | 27000 | 4200 | 2025-12-03
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4748870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114176036 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4847068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113872944 | Ongoing | 27000 | 0 | 2025-09-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4861887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115195209 | Physically Completed | 27000 | 0 | 2025-12-03 | 2026-10-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/4882670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115195598 | Physically Completed | 27000 | 0 | 2025-09-12 | 2026-10-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5146471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114836447 | Ongoing | 27000 | 0 | 2025-08-03
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5150662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113815608 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5150724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113800900 | Completed | 23490 | 0 | 2025-08-03 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5153133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113589228 | Completed | 23490 | 0 | 2025-07-01 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5154145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106417080 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5155311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106414991 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5157603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114175733 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5160942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114836413 | Ongoing | 27000 | 0 | 2025-12-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5161098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113599004 | Ongoing | 27000 | 0 | 2025-08-30
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5163043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113597659 | Completed | 23490 | 0 | 2025-09-04 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5168170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105842373 | Completed | 23490 | 0 | 2025-12-05 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5169481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106807935 | Ongoing | 27000 | 0 | 2025-07-19
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5171678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106178676 | Completed | 23490 | 0 | 2025-09-07 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5173013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114836745 | Completed | 23490 | 0 | 2025-12-03 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5174067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141333143 | Ongoing | 27000 | 16500 | 2025-08-03
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5174071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106417368 | Completed | 23490 | 0 | 2025-09-12 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5175578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106414606 | Physically Completed | 27000 | 0 | 2025-08-03 | 2026-10-11
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5175628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113799372 | Ongoing | 27000 | 0 | 2025-09-13
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5194514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113588222 | Approved | 27000 | 0 | 2025-02-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5194592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113597889 | Ongoing | 27000 | 0 | 2025-10-07
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5196361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113597829 | Completed | 23490 | 0 | 2025-09-12 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5201535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106179271 | Ongoing | 27000 | 0 | 2025-09-13
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5212200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113815367 | Approved | 27000 | 0 | 2025-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5212701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113597650 | Ongoing | 27000 | 4200 | 2025-08-03
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5218795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107006162 | Ongoing | 27000 | 0 | 2025-12-03
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5222164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105844860 | Completed | 23490 | 0 | 2025-12-03 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5223568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113597862 | Ongoing | 27000 | 0 | 2025-12-03
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5224359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113588105 | Ongoing | 27000 | 16800 | 2026-07-22
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5234114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113588988 | Ongoing | 27000 | 8400 | 2025-12-03
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5237704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106179400 | Physically Completed | 27000 | 0 | 2025-08-27 | 2026-09-13
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5238417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113597836 | Approved | 27000 | 0 | 2025-02-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5242132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114834045 | Ongoing | 27000 | 0 | 2025-09-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5242195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113598990 | Ongoing | 27000 | 4200 | 2025-07-19
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5244258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113814683 | Completed | 23490 | 0 | 2025-08-03 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5434491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106307484 | Ongoing | 27000 | 0 | 2025-09-07
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5435107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114837222 | Approved | 27000 | 0 | 2025-04-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5435131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114834022 | Ongoing | 27000 | 4200 | 2025-07-28
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5436493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141333250 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5437596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114836760 | Completed | 23490 | 0 | 2025-08-29 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5437597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114836774 | Ongoing | 27000 | 0 | 2025-08-29
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5467457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113588498 | Physically Completed | 27000 | 8400 | 2026-07-22 | 2026-10-04
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5472109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106415671 | Ongoing | 27000 | 16500 | 2026-07-23
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5510946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113814127 | Completed | 23490 | 0 | 2025-07-09 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5511569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114834182 | Approved | 27000 | 0 | 2025-04-08
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5511570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114834279 | Physically Completed | 23490 | 8100 | 2026-07-22 | 2026-08-16
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5512657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113814663 | Physically Completed | 27000 | 0 | 2025-12-03 | 2026-10-04
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5591147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113588574 | Physically Completed | 27000 | 8700 | 2026-07-07 | 2026-09-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5591363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113598997 | Approved | 27000 | 0 | 2025-04-23
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5592497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114834165 | Ongoing | 27000 | 12600 | 2026-08-04
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5592498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114834216 | Ongoing | 27000 | 12600 | 2026-08-04
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5633946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113804728 | Ongoing | 27000 | 0 | 2026-08-04
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5635768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113815571 | Ongoing | 27000 | 12600 | 2026-09-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5635967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114834198 | Completed | 23490 | 0 | 2025-06-30 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5636150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113599002 | Physically Completed | 27000 | 0 | 2026-03-11 | 2026-09-13
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5803513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113800720 | Ongoing | 27000 | 12600 | 2026-08-04
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5803634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113815573 | Ongoing | 27000 | 0 | 2026-08-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5803716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106210918 | Approved | 27000 | 0 | 2025-04-16
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/5803803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106415999 | Ongoing | 27000 | 16800 | 2026-07-22
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006065/IF/IAY/6373710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115195232 | Approved | 27000 | 0 | 2026-07-30
DHAR / GANDHWANI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722006065/RC/22012034848611 — Construction Of CC Road Nirman Sarpanch Ke Kaka Ke Ghar Se Man Marg Tak Malhera | Approved | 57000 | 0 | 2025-08-15
DHAR / GANDHWANI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006065/RS/22012034577407 — SBM SSP Shokpit PATEL PURA MALHERA | Physically Completed | 11999.97 | 0 | 2021-10-19 | 2026-07-21
DHAR / GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1722006065/WC/22012034630534 — मैड बाधन कार्य समूह क़ 1 malhera | Ongoing | 137000.48 | 0 | 2021-06-16
DHAR / GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1722006065/WC/22012034646261 — CTRA GALLY PLUGS NIRMAN KARYA MAL WALA NALA | Ongoing | 315000.06 | 0 | 2021-04-20
DHAR / GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1722006065/WC/22012034646291 — CTRA GALLU PLAGS NIRMAN BEDIWALI MAL NIM WALA NALA | Ongoing | 339999.54 | 0 | 2021-04-20
DHAR / GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722006065/WC/22012034646373 — CTRA gabien streectur nirman maw wala nala MALHERA | Physically Completed | 309712.52 | 0 | 2021-05-04 | 2026-07-21
DHAR / GANDHWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722006065/WC/22012034962842 — CTRA NALA TRECHING DEM WALA NALA MALHERA | Ongoing | 710000.22 | 0 | 2022-05-27
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722006065/WC/22012035291164 — JGSA 2025 recharge structure sarvjanik kup nirman rawatpura malhera | Approved | 25899.46 | 0 | 2025-04-15
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006/IF/22012035016592 — Horticulture Plantation Bhuwansingh-Sokalya Malhera | Ongoing | 186344 | 0 | 2022-10-07
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006/IF/22012035016609 — Horticulture Plantation Bharat-fatu Malhera | Ongoing | 170944 | 0 | 2022-10-07
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006/IF/22012035021988 — Horticulture Plantation kailash-Natthu Malhera | Ongoing | 170944 | 0 | 2023-01-09
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006/IF/22012035022000 — Horticulture Plantation किशोर-जामसिंह मल्हेरा | Ongoing | 170944 | 0 | 2022-10-07
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006/IF/22012035028139 — Horticulture Thavriya-Dashriya Malhera | Ongoing | 221680 | 0 | 2023-01-13
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006/IF/22012035028143 — Horticulture Naharsingh-Dashriya Malhera | Ongoing | 170944 | 0 | 2022-12-13
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006/IF/22012035028148 — Horticulture Pratab-Sadriya Malhera | Ongoing | 213680 | 0 | 2022-11-25
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006/IF/22012035028160 — Horticulture Plantation Ranchod-Chottiya Malhera | Ongoing | 213680 | 0 | 2023-01-13
DHAR / GANDHWANI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722/WC/22012034430916 — NISTAR TALAB MALHERA | Ongoing | 4834000 | 0 | 2019-05-31