## Work List
Exported on: 2026-09-11 11:00:33
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: VASLI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1722006067/DP/22012034575970 — सार्वजनीक कुप कॉलेज के पास वासली | Physically Completed | 430264.36 | 318238.58 | 2023-06-09 | 2026-06-08
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1722006067/DP/22012034589073 — Plantation Work Meri Mati Mera Desh Colege Parisar Vasli | Physically Completed | 55847.4 | 29440 | 2023-08-18 | 2026-06-08
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035079453 — kapildhara kup nirman Revabai | Deleted | 0 | 0 | 2023-04-17
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035079462 — कपिलधारा कूप केकडिया पिता रतन वासली | Closed | 230856.67 | 0 | 2023-04-17
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035080409 — कपिलधारा कुुप रूमाल फुलसिंह वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035080411 — कपिलधारा कुप गोपाल मदन वासली | Closed | 229999.9 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035080414 — कपिलधारा कुप बदा रामसिंह वासली | Closed | 229999.9 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035080418 — कपिलधारा कुप नारायण कनसिंह वासली | Completed | 229999.9 | 180802.2 | 2023-06-07 | 2025-08-06
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035080424 — कपिलधारा कुप गोविन्‍द गमीरा वासली | Ongoing | 229999.9 | 62698 | 2023-06-07
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035089684 — कपिल धारा कूप निर्माण मुकेश पिता नाथू वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035089691 — कपिल धारा कूप निर्माण मांगीलाल पिता लक्ष्मण वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035089692 — कपिल धारा कूप निर्माण कालीबाई पति गोमा वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035089702 — कपिल धारा कूप निर्माण सेकडिया पिता छगन वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035089704 — कपिल धारा कूप निर्माण बिरजबाई पति फाटू वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035089705 — कपिल धारा कूप निर्माण मगन पिता जामसिंह वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035089706 — कपिल धारा कूप निर्माण रमेश पिता गुलाब वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035089707 — कपिल धारा कूप निर्माण बालीबाई पति बल्लू वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035089710 — कपिल धारा कूप निर्माण हरसिंह पिता रूपसिंह वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035089713 — कपिल धारा कूप निर्माण भाचरिया पिता रूपला वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035093497 — कपिल धारा कूप निर्माण इंदरसिंह पिता रायसिंह वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035093502 — कपिल धारा कूप निर्माण रमेश पिता हरिया वासली | Closed | 0 | 0 | 2023-04-14
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035298536 — Kapil Dhara Kup Nirman Gopal Bhima Vasli | Approved | 0 | 0 | 2025-02-02
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035366437 — JGSA 2025 recharge kapil dhara kup nirman shobharam madan vasli | Ongoing | 25899.46 | 17472.9 | 2025-05-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035366501 — JGSA 2025 recharge kapil dhara kup nirman badri laxman vasli | New | 0 | 0 | 2025-04-17
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722006067/IF/22012035366629 — JGSA 2025 khet talab narayan gulab vasli | New | 0 | 0 | 2025-04-17
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035377780 — Kapil Dhara Kup Nirman Gopal Bhima Vasli | Ongoing | 214197.06 | 124236 | 2025-05-30
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722006067/IF/22012035421455 — JGSA 2025 KHET TALAB NIRMAN NARYAN GULAB VASLI | Physically Completed | 55865.38 | 46518 | 2025-05-01 | 2026-04-15
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722006067/IF/22012035421571 — JGSA 2025 KHET TALAB NIRMAN PADAM MANGILAL VASLI | Physically Completed | 55865.38 | 29031 | 2025-05-01 | 2026-04-15
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722006067/IF/22012035421721 — JGSA 2025 KHET TALAB NIRMAN BALLU NAGRIYA VASLI | Approved | 55865.38 | 0 | 2025-04-17
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722006067/IF/22012035421821 — JGSA 2025 KHET TALAB NIRMAN MUKESH NATHU VASLI | Approved | 55865.38 | 0 | 2025-04-17
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722006067/IF/22012035421866 — JGSA 2025 KHET TALAB NIRMAN JOWARSING RAMSING VASLI | Physically Completed | 55865.38 | 32364 | 2025-05-01 | 2026-04-15
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1722006067/IF/22012035553937 — Construction of Kapildhara Kup Nirman Manohar Ranjit Vashli | Deleted | 0 | 0 | 2025-05-23
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1722006067/IF/22012035553955 — Construction of Kapildhara Kup Nirman Narayan Gulab Vashli | Deleted | 0 | 0 | 2025-05-23
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035562350 — Construction of Kapildhara Kup Manohar Ranjit Vashli | Approved | 0 | 0 | 2025-05-28
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035562361 — Construction of Kapildhara Kup Santosh Narayan Vashli | Deleted | 0 | 0 | 2025-05-28
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006067/IF/22012035563873 — Construction of Kapildhara Kup Nirman Narayan Gulab Vashli | Approved | 0 | 0 | 2025-04-12
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006067/IF/22012035589482 — Ek Bagiya Ma Ke Name Shobha Bai Dodve MP2200604700148 | Ongoing | 286660.54 | 74382.97 | 2025-09-09
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006067/IF/22012035589487 — Ek Bagiya Ma Ke Name Rekha Bai MP2200604700173 | Ongoing | 283844.72 | 26652.54 | 2025-09-09
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006067/IF/22012035589515 — Ek Bagiya Ma Ke Name Gogal Bai MP22006047001 81 C | Ongoing | 283844.72 | 75426.97 | 2025-09-09
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006067/IF/22012035599657 — Ek Bagiya Maa Ke Naam Gogal MP22006047001 81C | Deleted | 0 | 0 | 2025-08-20
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006067/IF/22012035599664 — Ek Bagiya Maa Ke Naam Gogal MP22006047001 81C | Deleted | 0 | 0 | 2025-08-20
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006067/IF/22012035599674 — Ek Bagiya Maa Ke Naam Gogal MP22006047001 81C | Deleted | 0 | 0 | 2025-08-20
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006067/IF/22012035600943 — Ek Bagiya Maa ke Naam Gogal MP22006047001 81C | Deleted | 0 | 0 | 2025-07-15
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006067/IF/22012035600976 — Ek Bagiya Maa ke Naam Shobha Bai MP22006047001 48 | Deleted | 0 | 0 | 2025-07-15
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4400974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118318079 | Completed | 19890 | 18785 | 2023-10-04 | 2024-07-22
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4698935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119572443 | Physically Completed | 23490 | 22158 | 2024-10-04 | 2026-06-04
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4699156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119410392 | Completed | 21870 | 21384 | 2024-10-15 | 2025-02-17
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4702056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120863718 | Completed | 23490 | 23364 | 2025-03-21 | 2026-02-12
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4702619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119767216 | Completed | 21870 | 21627 | 2024-10-04 | 2025-02-17
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4705760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123016244 | Completed | 21870 | 21627 | 2024-10-04 | 2025-02-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4706899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123777703 | Completed | 21870 | 21870 | 2024-10-05 | 2025-02-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4708851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124292229 | Completed | 21870 | 21627 | 2024-10-05 | 2025-04-04
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4710317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123304337 | Completed | 21870 | 21870 | 2024-10-05 | 2025-02-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4710327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123312902 | Completed | 23490 | 22014 | 2024-10-15 | 2026-02-23
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4718503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664788 | Completed | 21870 | 21870 | 2024-10-04 | 2025-02-05
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4718504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664817 | Completed | 21870 | 21870 | 2024-10-04 | 2025-02-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4718505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664825 | Completed | 21870 | 21870 | 2024-10-04 | 2025-02-04
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4718506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664907 | Completed | 23490 | 21978 | 2024-10-15 | 2026-02-23
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4758499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119583064 | Completed | 21870 | 21627 | 2024-11-14 | 2025-02-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4759139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118319393 | Completed | 21870 | 21870 | 2024-11-14 | 2025-04-04
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4767565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123311980 | Completed | 23490 | 22194 | 2024-11-14 | 2026-02-23
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4786229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664761 | Completed | 21870 | 21870 | 2024-11-14 | 2025-03-18
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4866845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119766604 | Completed | 23490 | 22554 | 2024-12-23 | 2026-02-23
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4870379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123223527 | Completed | 23490 | 22536 | 2024-12-26 | 2026-02-23
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4883390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123304194 | Physically Completed | 23490 | 21978 | 2025-01-09 | 2026-06-04
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/4883428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664742 | Completed | 21870 | 21870 | 2025-01-09 | 2025-03-18
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5821421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126830001 | Physically Completed | 23490 | 23490 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5821851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123309868 | Physically Completed | 23490 | 23490 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5822127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120886327 | Physically Completed | 23490 | 21663 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5822128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120905454 | Physically Completed | 23490 | 16443 | 2025-10-30 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5822298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118312346 | Physically Completed | 23490 | 14094 | 2025-10-25 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5822751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118312011 | Ongoing | 23490 | 1827 | 2025-10-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5822877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119408606 | Ongoing | 23490 | 23490 | 2025-10-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5822880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119413197 | Physically Completed | 23490 | 21924 | 2025-10-29 | 2026-04-19
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5822957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119627216 | Physically Completed | 23490 | 21402 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5823086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123308513 | Ongoing | 23490 | 23490 | 2025-10-01
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5823151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123305785 | Ongoing | 23490 | 23229 | 2025-10-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5823196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120883385 | Physically Completed | 23490 | 21924 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5823200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120892285 | Ongoing | 23490 | 19836 | 2025-10-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5823396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119406497 | Completed | 23490 | 23490 | 2025-10-08 | 2026-02-12
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5823452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119407752 | Physically Completed | 23490 | 23490 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5823797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123297734 | Physically Completed | 23490 | 23490 | 2025-10-08 | 2026-06-29
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5824242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123312124 | Physically Completed | 23490 | 23490 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5824922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119591470 | Physically Completed | 23490 | 23490 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5825014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119633429 | Physically Completed | 23490 | 23490 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5825295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123297310 | Completed | 23490 | 23490 | 2025-10-08 | 2026-02-12
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5825296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123313007 | Physically Completed | 23490 | 23490 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5825354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119411750 | Physically Completed | 23490 | 23490 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5825513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123230269 | Physically Completed | 23490 | 23229 | 2025-10-08 | 2026-04-19
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5825630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119598714 | Physically Completed | 23490 | 23210 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5825830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119583228 | Ongoing | 23490 | 22707 | 2025-10-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5826064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119409822 | Physically Completed | 23490 | 23229 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5826252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119577317 | Physically Completed | 23490 | 20358 | 2025-10-08 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5826253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119577376 | Physically Completed | 23490 | 23490 | 2025-10-08 | 2026-05-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5828010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119623050 | Physically Completed | 23490 | 23490 | 2025-10-08 | 2026-05-31
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5843755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120847414 | Physically Completed | 23490 | 23229 | 2025-10-29 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5844280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664342 | Physically Completed | 23490 | 23229 | 2025-10-25 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5844281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664757 | Physically Completed | 23490 | 23490 | 2025-10-30 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5844282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664759 | Ongoing | 23490 | 23229 | 2025-11-08
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5844283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664771 | Physically Completed | 23490 | 21924 | 2025-10-29 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5844284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664775 | Physically Completed | 23490 | 23229 | 2025-10-25 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5844285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664811 | Completed | 23490 | 23490 | 2025-10-25 | 2026-02-12
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5844286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664836 | Physically Completed | 23490 | 23229 | 2025-10-25 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5844362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119769100 | Physically Completed | 23490 | 20358 | 2025-10-29 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5845212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119766831 | Physically Completed | 23490 | 23490 | 2025-10-30 | 2026-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5845490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119407427 | Physically Completed | 23490 | 23490 | 2025-10-25 | 2026-06-29
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/5845900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131665219 | Ongoing | 23490 | 21924 | 2025-10-29
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6126402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120927641 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6126407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120934457 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6126814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120867928 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6127312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120943070 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6128429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123228948 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6130245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123777175 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6133619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119618008 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6133988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119407988 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6133990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119408933 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6133991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119409210 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6133992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119409232 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6133993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119410074 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6133994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119411109 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6133996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119412605 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6135358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123308162 | Approved | 23490 | 0 | 2026-03-12
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6135359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123308335 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6135361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123311184 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6135362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123311314 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6136084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123203895 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6138586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119407313 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6138587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119407541 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6138598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119408190 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6139465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119610322 | Approved | 23490 | 0 | 2026-03-12
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6139525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119589373 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6143644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124285292 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6143729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119577171 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6145194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123240747 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6145370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118302964 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6146247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119601788 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6146830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119767096 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6147594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123310836 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6151737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123311830 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6153395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119409501 | Approved | 23490 | 0 | 2026-03-12
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6153396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119409723 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6153984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119610223 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6154243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119768916 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6154245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119769207 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6157338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664735 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6157339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664748 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6157340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664779 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6157341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664785 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6157342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664833 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6158924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131664570 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6159516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123312764 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6159541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123297519 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6159995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120921753 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6162712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123299589 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6162713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123299807 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6164698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120911248 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6164711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123230733 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6166328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123238599 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6171650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124713415 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6171929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119410932 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6172972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119622642 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6174545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123199025 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6174598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123309733 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6174599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123310009 | Approved | 23490 | 0 | 2026-02-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6174602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123310153 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6175330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123209712 | Approved | 23490 | 0 | 2026-03-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006067/IF/IAY/6175854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120919127 | Approved | 23490 | 0 | 2026-02-26
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1722006067/LD/22012034594247 — Med bandhan Ram Lalsingh Vasli | Closed | 0 | 0 | 2023-08-15
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1722006067/LD/22012034594248 — Med bandhan Laxman chaina Vasli | Closed | 0 | 0 | 2023-08-15
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1722006067/LD/22012034594249 — Med bandhan Gulsingh Bansingh Vasli | Closed | 0 | 0 | 2023-08-15
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1722006067/LD/22012034594251 — Med Bandhan Sobharam madan Vasli | Closed | 0 | 0 | 2023-08-15
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1722006067/LD/22012034594252 — Med bandhan Ballu madan Vasli | Closed | 0 | 0 | 2023-08-15
DHAR / GANDHWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722006067/RC/22012034666832 — Construction of CC Road Nirman Men Road Se Padam Ke Ghar Taraf Vashli | Closed | 32000 | 0 | 2023-09-13
DHAR / GANDHWANI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722006067/RC/22012034666853 — Construction of CC Road Nirman Men Road Se Kelsingh Ke Ghar Taraf Vashli | Ongoing | 36000 | 34506 | 2024-07-20
DHAR / GANDHWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006067/RS/22012034693669 — ISB Shok Pit Grup 01 No 50 Baydipura Vasli | Closed | 0 | 0 | 2023-04-13
DHAR / GANDHWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006067/RS/22012034693670 — ISB Shok Pit Grup 01 No 50 Nadipura Vasli | Ongoing | 350004.13 | 297138.25 | 2023-08-19
DHAR / GANDHWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006067/RS/22012034693672 — ISB Shok Pit Grup 03 No 50 Behadapura Vasli | Ongoing | 350004.13 | 289845.25 | 2023-09-03
DHAR / GANDHWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006067/RS/22012034693676 — SSP Shok Pit Grup 01 No 10 Vasli | Closed | 0 | 0 | 2023-04-13
DHAR / GANDHWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1722006067/RS/22012035118175 — Community Sanitary Complex Vasli | Ongoing | 51000 | 49084 | 2023-10-07
DHAR / GANDHWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1722006067/RS/22012035118236 — Community Sanitary Complex Vashli Patelpura | Ongoing | 51000 | 49747 | 2023-10-07
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1722006067/WC/22012035059342 — नाला ट्रेन्चिंग तालाब वाला नाला वासली | Completed | 499999.78 | 377902.1 | 2023-10-07 | 2025-05-06
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1722006067/WC/22012035099071 — CTRA Constr.Gully Plug At Gothan wala bayda vasli | Physically Completed | 143837.33 | 132350.28 | 2023-10-07 | 2026-04-15
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1722006067/WC/22012035099072 — CTRA Constr. of Gully Plug At Mthrala bayda 01 vasli | Physically Completed | 176514.29 | 159941.22 | 2023-10-07 | 2026-04-15
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1722006067/WC/22012035099073 — CTRA Constr. of Gully Plug At Mthrala bayda 02 vasli | Closed | 0 | 0 | 2023-08-17
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722006067/WC/22012035138717 — Construction of RMS Nirman Anil Ke Khet Ke Paas Wala Nala Vasli | Physically Completed | 1472739.22 | 1395129.33 | 2023-10-08 | 2026-04-15
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006067/WC/22012035142475 — RMS nirman kary anil ke khet pass wale nale pr Vasli | Closed | 0 | 0 | 2023-08-16
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006067/WC/22012035164330 — Boulder Check dem Matraliya bayda Gp Vasli | New | 0 | 0 | 2024-04-12
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722006067/WC/22012035212414 — Const of Nala tranching nirman kary Kakad wala nala vasli | Approved | 0 | 0 | 2024-06-25
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006067/WC/22012035226535 — Construction of Bolder Chek Dem Matrala Pahadi No 01 Vashli | Approved | 0 | 0 | 2024-10-15
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006067/WC/22012035231416 — Constr Of Talai Nirman Kary Emli wala Nala Vasli | Physically Completed | 385010.5 | 366773.34 | 2024-12-26 | 2026-04-15
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006067/WC/22012035231437 — Construction Of Talai Nirman Kary Vasli | Physically Completed | 375121.18 | 364853.04 | 2024-12-04 | 2026-04-15
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006067/WC/22012035238433 — construction of Talai nirman Matrala Pahadi Bahadur Ke Khat Ke Pass | New | 0 | 0 | 2024-11-05
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006067/WC/22012035238442 — construction of Talai nirman Matrala Pahadi Ramesh Ke Khat Ke Pass | Physically Completed | 315248.07 | 300668.15 | 2025-01-15 | 2026-04-15
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006067/WC/22012035238447 — construction of Talai nirman Matrala Pahadi Bahadur Ke Khat Ke Pass | Physically Completed | 315693.12 | 300430.78 | 2025-01-30 | 2026-04-15
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006067/WC/22012035238457 — construction of Talai nirman Matrala Pahadi Kishor Ke Ke Khat Ke Pass | Physically Completed | 315693.12 | 279861.99 | 2025-01-05 | 2026-04-15
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006067/WC/22012035274995 — Construction Of Talai Nirman Gothan Baydi Vasli | Approved | 0 | 0 | 2025-04-20
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006067/WC/22012035275006 — Construction Of Talai Nirman Anil Ke Khet Pas Mathrala Pahadi Vasli | Approved | 470028.73 | 0 | 2025-04-20
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006/IF/22012035155108 — Horticulture plantation Madan Ratan Vasli | Deleted | 394870 | 0 | 2023-08-17
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006/IF/22012035155114 — Horticulture plantation jheta Lalsingh vasli | Deleted | 394870 | 0 | 2023-08-17
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006/IF/22012035155116 — H orticulture plantation Bharat Hatiya Vasli | Deleted | 318556 | 0 | 2023-08-17
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006/IF/22012035156314 — Horticulture plantation Madan - Ratan vasli | Ongoing | 394870 | 141447 | 2023-12-13
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006/IF/22012035156326 — Horticulture plantation jheta Lalsingh vasli | Ongoing | 394870 | 146732 | 2023-12-15
DHAR / GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722006/IF/22012035156334 — Horticulture plantation Bharat - Hatiya vasli | Ongoing | 318335 | 89780 | 2023-12-13