## Work List
Exported on: 2026-09-29 23:18:22
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Chamjhar
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / BAGH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1722007016/DP/22012034521142 — निर्मल नीर कूप पटेलपुरा फल्या | Ongoing | 470874.11 | 0 | 2020-12-28
DHAR / BAGH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722007016/IF/22012034642400 — पशु शेट निर्माण भंगु गुलसिंह बगोली | Ongoing | 101804.91 | 0 | 2021-01-14
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722007016/IF/22012035458059 — JGSA FARM POND Devasingh Dongarsingh Chamjhar | Ongoing | 147621.16 | 0 | 2025-05-06
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722007016/IF/22012035458092 — JGSA FARM POND Meerabai Padam Chamjhar | Ongoing | 147621.16 | 0 | 2025-05-06
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722007016/IF/22012035458325 — JGSA FARM POND Deelip Kalu Ghuddaliya | Ongoing | 147621.16 | 0 | 2025-05-27
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722007016/IF/22012035458357 — JGSA FARM POND Menu Badan Ghuddaliya Chamjhar | Ongoing | 147621.16 | 0 | 2025-05-06
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/4579832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119320207 | Approved | 27000 | 0 | 2024-09-11
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/4624762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127093212 | Ongoing | 27000 | 0 | 2025-04-03
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/4633174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128264094 | Ongoing | 27000 | 0 | 2025-07-30
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/4707847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123547921 | Approved | 27000 | 0 | 2024-09-20
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/4784034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125969077 | Completed | 23490 | 0 | 2025-07-11 | 2026-07-24
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5163947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123558758 | Completed | 23490 | 0 | 2025-05-27 | 2026-07-24
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5385190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128264470 | Ongoing | 27000 | 4800 | 2025-08-18
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5393417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117430591 | Approved | 27000 | 0 | 2025-02-19
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5395057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117430476 | Ongoing | 27000 | 2400 | 2025-04-24
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5397285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124426886 | Completed | 23490 | 0 | 2025-07-11 | 2026-07-25
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5397350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126204359 | Completed | 23490 | 0 | 2025-04-16 | 2026-07-25
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5400063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123761864 | Completed | 27000 | 0 | 2025-05-27 | 2026-09-22
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5401744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124412069 | Completed | 23490 | 0 | 2025-07-11 | 2026-07-25
DHAR / BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5403626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123561353 | Ongoing | 27000 | 0 | 2026-06-04
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5409924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124411125 | Physically Completed | 27000 | 2400 | 2025-07-11 | 2026-09-01
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5435268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114981321 | Physically Completed | 27000 | 2400 | 2025-05-27 | 2026-09-01
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5437156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126128730 | Completed | 23490 | 0 | 2025-05-27 | 2026-07-24
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5438364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114981480 | Physically Completed | 27000 | 4800 | 2025-08-18 | 2026-09-01
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5441025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119527577 | Completed | 23490 | 0 | 2025-05-28 | 2026-07-25
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5536153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126902597 | Physically Completed | 27000 | 4800 | 2025-05-28 | 2026-09-13
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5574349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118781474 | Completed | 23490 | 0 | 2025-05-28 | 2026-07-25
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5574399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119300276 | Ongoing | 27000 | 2400 | 2025-05-28
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5575000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126900838 | Physically Completed | 27000 | 4800 | 2025-05-28 | 2026-09-20
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5865391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125966044 | Physically Completed | 27000 | 0 | 2025-02-15 | 2026-09-20
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007016/IF/IAY/5865441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114981427 | Physically Completed | 23490 | 0 | 2025-03-04 | 2026-07-12
DHAR / BAGH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722007016/RC/22012034665810 — पुलिया निर्माण तालाब वाला नाला सिंघाचौरी | Completed | 1497529.18 | 0 | 2024-01-13 | 2026-08-25
DHAR / BAGH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722007016/RC/22012034665814 — पुलिया निर्माण स्कूल वाला नाला बगोली | Completed | 1497435.37 | 0 | 2025-02-24 | 2026-08-18
DHAR / BAGH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722007016/WC/22012035236391 — निस्तार टैंक मेहदा फलिया हुकू के खेत के पास वाला नाला | Approved | 0 | 0 | 2024-12-20
DHAR / BAGH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722/WC/22012035138041 — PULIYA SAH STOP DAM NIRMAN KARY DEVKAPURA NALA | Ongoing | 3223000 | 0 | 2025-03-27
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722/WC/22012035320889 — निस्तार तालाब निर्माण गांवदा फल्या वाला नाला चामझर | Ongoing | 3964000 | 0 | 2026-01-03
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722/WC/22012035320890 — निस्तार तालाब निर्माण कार्य नीम वाला नाला चामझर | Ongoing | 3923000 | 0 | 2026-01-03
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722/WC/22012035320891 — निस्तार तालाब निर्माण कार्य सागरीया वाला नाला चामझर | Ongoing | 3933000 | 0 | 2026-01-09
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722/WH/22012034945530 — निस्तार तालाब निर्माण गांवदा फल्या वाला नाला चामझर | Approved | 3964000 | 0 | 2025-04-15
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722/WH/22012034945531 — निस्तार तालाब निर्माण कार्य नीम वाला नाला चामझर | Approved | 3923000 | 0 | 2025-04-15
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722/WH/22012034945532 — निस्तार तालाब निर्माण कार्य सागरीया वाला नाला चामझर | Approved | 3933000 | 0 | 2025-04-15