## Work List
Exported on: 2026-09-05 13:55:52
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Dhana
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722007018/IF/22012035422186 — JGSA Udaysingh Ratan Pipalwa | Ongoing | 25899.46 | 0 | 2025-05-29
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722007018/IF/22012035422284 — JGSA Bharatsingh Thakur Pipalwa | Ongoing | 25899.46 | 0 | 2025-05-27
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722007018/IF/22012035422324 — JGSA Kekadiya Bhursingh Pipalwa | Ongoing | 25899.46 | 0 | 2025-05-29
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722007018/IF/22012035422364 — JGSA Bhursingh Naka Pipalwa | Ongoing | 25899.46 | 0 | 2025-05-27
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722007018/IF/22012035422532 — JGSA Sankar Indarsingh Thana | Ongoing | 25899.46 | 0 | 2025-05-27
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/4537542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105755855 | Physically Completed | 23490 | 0 | 2024-10-01 | 2026-08-12
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/4559751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115276781 | Ongoing | 27000 | 0 | 2024-12-01
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/4560869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114875640 | Completed | 23490 | 0 | 2024-09-26 | 2026-07-27
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/4576179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118427879 | Completed | 23490 | 4800 | 2024-09-26 | 2026-08-17
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/4579960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119347689 | Completed | 23490 | 0 | 2024-09-26 | 2026-07-27
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/4678280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126045037 | Completed | 23490 | 0 | 2024-10-09 | 2026-08-05
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/4703492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120721950 | Ongoing | 27000 | 0 | 2025-01-16
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/4739883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106053339 | Ongoing | 27000 | 0 | 2024-12-01
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/4786669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131992032 | Completed | 23490 | 0 | 2024-12-01 | 2026-08-05
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/4822911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387030 | Completed | 23490 | 9600 | 2024-12-01 | 2026-08-17
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/4831108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131992013 | Ongoing | 27000 | 0 | 2024-12-01
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5120591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125089455 | Ongoing | 27000 | 0 | 2025-07-25
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5253226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105787576 | Completed | 23490 | 0 | 2025-07-25 | 2026-08-05
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5280660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119345326 | Ongoing | 27000 | 0 | 2025-05-07
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5283636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105783475 | Physically Completed | 23490 | 0 | 2025-02-19 | 2026-08-09
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5285656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119941560 | Completed | 23490 | 4800 | 2025-07-21 | 2026-08-17
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5285800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126069791 | Completed | 23490 | 0 | 2025-06-01 | 2026-08-12
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5298613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126053268 | Completed | 23490 | 4800 | 2025-05-07 | 2026-08-17
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5300341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387036 | Ongoing | 27000 | 0 | 2025-07-21
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5342328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126070308 | Completed | 23490 | 0 | 2025-07-20 | 2026-07-17
DHAR / BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5699714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120721724 | Completed | 23490 | 0 | 2025-09-12 | 2026-07-27
DHAR / BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5816231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115277913 | Approved | 27000 | 0 | 2025-02-19
DHAR / BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5816613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137215101 | Ongoing | 27000 | 0 | 2026-04-10
DHAR / BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5866072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137215279 | Ongoing | 27000 | 0 | 2026-04-10
DHAR / BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007018/IF/IAY/5871855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120722076 | Ongoing | 27000 | 0 | 2026-06-03
DHAR / BAGH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1722007018/WC/22012034622263 — nalatenching pipalwa wala nala | Ongoing | 322051.2 | 0 | 2021-04-17
DHAR / BAGH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Pebble graded Bund for Community / Construction of Pebble graded Bund for Community | Construction of Bund | 1722007018/WC/22012034622267 — Nala Trenching masaniyanala | Ongoing | 487102.44 | 0 | 2021-04-27
DHAR / BAGH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Upland Bench Terrace Terrace for Comm / Construction of Upland Bench Terrace for Community | Terracing | 1722007018/WC/22012034624183 — nala trenching imlipura thana | Ongoing | 336543.5 | 0 | 2021-04-17
DHAR / BAGH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1722007018/WC/22012034658926 — ctra bolder chak sagon wala bayda | Ongoing | 6415.89 | 0 | 2021-04-27
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722007018/WC/22012035244626 — Nistar Talab jhari wala nala thana | Ongoing | 2282026.42 | 6900 | 2026-02-24
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722007018/WC/22012035299480 — JGSA Dugwell Recharge Neermal neer Khedadevipura Pipalwa | Approved | 25899.46 | 0 | 2025-04-14
DHAR / BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722007018/WC/22012035299485 — JGSA Dugwell Recharge Neermal Neer Natarpura Thana | Approved | 25899.46 | 0 | 2025-04-14