## Work List
Exported on: 2026-10-13 15:56:25
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Jogardi
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / KUKSHI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008006/IF/22012034355255 — फलोधान उधानिकी विभाग हितग्राही संख्‍या 4 क्रमांक 2 जोगडदी | Ongoing | 581000 | 0 | 2018-03-08
DHAR / KUKSHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1722008006/IF/22012034587838 — GKRA Cattals Shead Bharat Versingh Jogardi | Ongoing | 101273.16 | 0 | 2020-11-25
DHAR / KUKSHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1722008006/IF/22012034587839 — GKRA Cattals Shead Kalu Bherusingh Jogardi | Ongoing | 101273.16 | 0 | 2020-11-25
DHAR / KUKSHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722008006/IF/22012034587852 — GKRA Cattals Shead Mukam Vesta Jogardi | Ongoing | 101273.16 | 0 | 2020-11-25
DHAR / KUKSHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Masonry/CC Anicut for Individuals / Construction of Masonry Check Dam for Individual | Construction of Check Dam/Stop Dam | 1722008006/IF/22012034587854 — GKRA Cattals Shead Bhursingh Aapsingh Jogardi | Ongoing | 101273.16 | 0 | 2021-02-01
DHAR / KUKSHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Masonry/CC Anicut for Individuals / Construction of Masonry Check Dam for Individual | Construction of Check Dam/Stop Dam | 1722008006/IF/22012034587856 — GKRA Cattals Shead Richu Jhalu Jogardi | Ongoing | 101273.16 | 0 | 2021-02-02
DHAR / KUKSHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722008006/IF/22012035047541 — Kapil Dhara Kup Paanbai w/o Madan Mandloi Jogardi | Ongoing | 292822.01 | 0 | 2023-02-04
DHAR / KUKSHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722008006/IF/22012035121810 — कपिलधारा कुप गेन्दाबाई पति बालूसिंह जोगडदी | Ongoing | 240359.37 | 0 | 2023-08-25
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/38032 — Construction of IAY House -IAY REG. NO. MP-22-008-006-002/23 | Ongoing | 27000 | 0 | 2025-07-07
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4536991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103465700 | Ongoing | 27000 | 0 | 2024-10-08
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4537240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105453215 | Completed | 23490 | 0 | 2025-07-07 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4537786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103555226 | Ongoing | 27000 | 0 | 2025-07-07
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4538385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103434017 | Ongoing | 27000 | 0 | 2025-07-07
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4540144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105549399 | Completed | 23490 | 0 | 2025-07-07 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4540146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105549493 | Completed | 23490 | 0 | 2025-07-07 | 2026-07-30
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4541799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105012876 | Completed | 23490 | 0 | 2025-07-07 | 2026-07-22
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4542076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105332800 | Physically Completed | 23490 | 0 | 2025-08-05 | 2026-07-26
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4542077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105332972 | Ongoing | 27000 | 0 | 2026-06-24
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4543360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105337640 | Physically Completed | 23490 | 0 | 2025-08-05 | 2026-07-19
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4543391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105343094 | Completed | 23490 | 0 | 2025-08-06 | 2026-07-27
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4543394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105343254 | Approved | 27000 | 0 | 2024-09-13
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4548476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106874178 | Completed | 23490 | 0 | 2025-08-05 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4685038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103491385 | Physically Completed | 23490 | 0 | 2025-10-05 | 2026-07-12
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4735906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103759584 | Approved | 27000 | 0 | 2024-10-03
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4854367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105262563 | Ongoing | 27000 | 0 | 2026-07-10
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4858981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103588254 | Physically Completed | 23490 | 0 | 2025-08-02 | 2026-07-12
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/4859509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106715533 | Physically Completed | 23490 | 0 | 2025-08-12 | 2026-07-26
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5248413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105454506 | Ongoing | 27000 | 0 | 2025-08-12
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5251399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102935602 | Completed | 23490 | 0 | 2025-08-12 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5252677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102944202 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5254453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105345635 | Completed | 23490 | 0 | 2025-09-07 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5256075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103448786 | Ongoing | 27000 | 0 | 2025-08-12
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5257804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105342039 | Physically Completed | 23490 | 0 | 2026-06-24 | 2026-08-09
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5261251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103584451 | Physically Completed | 27000 | 0 | 2025-08-06 | 2026-09-03
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5268371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103554508 | Physically Completed | 23490 | 0 | 2025-08-06 | 2026-07-19
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5269717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102907742 | Ongoing | 27000 | 0 | 2026-06-24
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5274668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102993362 | Completed | 23490 | 0 | 2025-08-05 | 2026-07-30
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5276142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106732766 | Ongoing | 27000 | 0 | 2026-05-05
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5279884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105260718 | Physically Completed | 27000 | 0 | 2025-08-05 | 2026-09-11
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5282055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105333247 | Ongoing | 27000 | 0 | 2025-08-05
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5285968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105332661 | Ongoing | 27000 | 0 | 2025-08-06
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5288426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105335564 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-30
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5289449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102949369 | Physically Completed | 27000 | 0 | 2025-08-18 | 2026-09-03
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5291332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103466325 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-30
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5292279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105013203 | Ongoing | 27000 | 0 | 2025-08-12
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5293498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105262482 | Ongoing | 27000 | 0 | 2026-06-24
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5294308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105453908 | Ongoing | 27000 | 0 | 2025-08-06
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5297145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105262090 | Completed | 23490 | 0 | 2025-08-06 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5300061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105261971 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5300345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105484376 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5301036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103032257 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5301367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103527847 | Physically Completed | 27000 | 0 | 2025-08-12 | 2026-09-03
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5308503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103433624 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5309578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106713389 | Ongoing | 27000 | 0 | 2025-08-12
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5312015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103720169 | Ongoing | 27000 | 0 | 2025-08-18
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5315556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105343620 | Physically Completed | 23490 | 0 | 2025-08-06 | 2026-07-19
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5324149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105260413 | Ongoing | 27000 | 0 | 2026-05-05
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5325917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105343950 | Completed | 23490 | 0 | 2025-08-05 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5328726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103421602 | Ongoing | 27000 | 0 | 2025-08-05
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5332268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105343868 | Ongoing | 27000 | 0 | 2025-08-06
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5332884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105333175 | Ongoing | 27000 | 0 | 2025-08-06
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5336079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102628358 | Ongoing | 27000 | 0 | 2025-08-18
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5336396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105549659 | Physically Completed | 23490 | 0 | 2025-10-06 | 2026-07-19
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5337743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105336367 | Physically Completed | 23490 | 0 | 2025-08-06 | 2026-07-19
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5338526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103587550 | Ongoing | 27000 | 0 | 2025-08-06
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5362389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103554940 | Ongoing | 27000 | 0 | 2025-09-07
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5364243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105012512 | Ongoing | 27000 | 0 | 2025-08-18
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5366365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103127819 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-27
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5367299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102997007 | Ongoing | 27000 | 0 | 2026-09-29
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5371926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105332362 | Ongoing | 27000 | 0 | 2025-08-06
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5372489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103449009 | Completed | 23490 | 0 | 2025-10-05 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5373046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103127994 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5374163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103759176 | Physically Completed | 23490 | 0 | 2025-08-06 | 2026-08-09
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5374573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105342612 | Physically Completed | 23490 | 0 | 2025-10-05 | 2026-07-26
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5375445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105503854 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-30
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5376989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114131853 | Physically Completed | 23490 | 0 | 2025-06-08 | 2026-08-02
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5380336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105262732 | Completed | 23490 | 0 | 2025-06-08 | 2026-07-30
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5386264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105454155 | Completed | 23490 | 0 | 2025-06-08 | 2026-07-30
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5388076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105455952 | Completed | 23490 | 0 | 2025-06-08 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5388077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105458143 | Completed | 23490 | 0 | 2025-06-08 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5388273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105013560 | Completed | 23490 | 0 | 2025-06-08 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5395555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105551143 | Completed | 23490 | 0 | 2025-06-08 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5396456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105148716 | Ongoing | 27000 | 0 | 2025-08-06
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5396851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102907952 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-27
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5397658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106729126 | Ongoing | 27000 | 0 | 2026-05-05
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5397716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103452636 | Ongoing | 27000 | 0 | 2026-05-05
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5399055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102985486 | Ongoing | 27000 | 0 | 2025-08-12
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5406385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105335759 | Completed | 23490 | 0 | 2025-08-06 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5407578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105453591 | Ongoing | 27000 | 0 | 2025-08-12
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5407744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102908288 | Physically Completed | 27000 | 0 | 2025-09-07 | 2026-09-03
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5407871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103761181 | Physically Completed | 23490 | 0 | 2026-05-05 | 2026-07-19
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5408220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105454680 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5430820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103466070 | Ongoing | 27000 | 0 | 2025-08-18
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5511869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105332494 | Physically Completed | 27000 | 0 | 2025-05-21 | 2026-09-03
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5519807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105453340 | Completed | 23490 | 0 | 2025-05-21 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5553945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105262396 | Completed | 23490 | 0 | 2025-05-21 | 2026-07-30
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5553949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105287840 | Completed | 23490 | 0 | 2025-05-21 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5618101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102915914 | Ongoing | 27000 | 0 | 2025-05-21
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5618366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102916827 | Physically Completed | 23490 | 0 | 2025-05-21 | 2026-07-30
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5618725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114154337 | Physically Completed | 23490 | 0 | 2025-05-21 | 2026-08-02
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5634496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102986651 | Ongoing | 27000 | 0 | 2025-08-12
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5634513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103432521 | Physically Completed | 23490 | 0 | 2025-08-12 | 2026-08-09
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5634880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103448368 | Ongoing | 27000 | 0 | 2025-08-06
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5636767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106699776 | Physically Completed | 27000 | 0 | 2026-05-05 | 2026-10-04
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5636768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105453767 | Physically Completed | 23490 | 0 | 2025-08-12 | 2026-08-02
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5636875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105346000 | Completed | 23490 | 0 | 2025-08-12 | 2026-07-27
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5701131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103469203 | Ongoing | 27000 | 0 | 2025-08-12
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5782060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105550499 | Ongoing | 27000 | 0 | 2026-06-24
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5822474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103759921 | Ongoing | 27000 | 0 | 2026-09-29
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5822826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105549604 | Approved | 27000 | 0 | 2025-05-09
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5824702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105549990 | Ongoing | 27000 | 0 | 2026-09-29
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5827116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105262267 | Ongoing | 27000 | 0 | 2026-06-24
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/5828456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102985693 | Approved | 27000 | 0 | 2025-04-01
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/6246925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105335311 | Ongoing | 27000 | 0 | 2026-10-13
DHAR / KUKSHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008006/IF/IAY/6248845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106729186 | Ongoing | 27000 | 0 | 2026-10-13
DHAR / KUKSHI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wastelands Block Plantation-Farm Forestry -Comm / Agro Forestry Block Plantation in Waste Lands for Community | Plantation | 1722008006/LD/22012034565323 — वृक्षारोपण माध्यमिक विद्यालय यूनिट 1 संख्या 200 जोगडदी | Ongoing | 394489.84 | 0 | 2021-07-01
DHAR / KUKSHI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722008006/WC/22012034676741 — CTRA PERCOLATION TANK KHADAPURA JOGARDI | Ongoing | 1129900.19 | 0 | 2021-09-11
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Gully Plug for Community | Construction of Check Dam/Stop Dam | 1722008006/WC/22012035100466 — RMS nirman safal singh pita dhansingh ke khet ke pass | Physically Completed | 1479981.86 | 0 | 2024-08-12 | 2026-07-21
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722008006/WC/22012035163310 — अर्थन डेम निर्माण | New | 0 | 0 | 2024-04-01
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008006/WC/22012035251901 — तालाब निर्माण अमरसिंह फतिया के खेत के पास | Approved | 0 | 0 | 2025-01-27
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008006/WC/22012035251902 — तालाब निर्माण सुभान पिता उगरसिंह खेत के पास | Approved | 0 | 0 | 2025-01-27
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008006/WC/22012035254817 — तालाब निर्माण टपकनिया नाले पर क्रमांक 1 जोगडदी | Approved | 0 | 0 | 2025-01-26
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008006/WC/22012035254819 — तालाब निर्माण टपकनिया नाले पर क्रमांक 2 जोगडदी | Approved | 0 | 0 | 2025-01-26
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008006/WC/22012035278087 — तालाब निर्माण नदी वाला नाला | Ongoing | 989434.54 | 0 | 2025-06-20
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008006/WC/22012035278097 — तालाब निर्माण मालखोदरा के पास | Ongoing | 994664.86 | 0 | 2025-06-11
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008006/WC/22012035305763 — निस्तार तालाब निर्माण सुभानसिह पिता उगरसिह के खेत के पास वाला नाला जोगडदी | Approved | 904997.72 | 0 | 2025-04-14
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008006/WC/22012035319886 — तालाब निर्माण कार्य हानुमान मन्दिर नाले पर जोगडदी | Approved | 0 | 0 | 2025-04-14
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008006/WC/22012035319888 — तालाब निर्माण कार्य झिरी वाले नाले पर जोगडदी | New | 0 | 0 | 2025-04-14
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008006/WC/22012035319890 — तालाब निर्माण कार्य झिरी वाले नाले पर जोगडदी | Approved | 0 | 0 | 2025-04-14
DHAR / KUKSHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722/WC/22012035099970 — construction of RMS Devziri Nalla Jogardi | Ongoing | 3106000 | 0 | 2023-09-10
DHAR / KUKSHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722/WC/22012035102752 — construction of pipe Culvert at Shamshan Ghat Road Khadapura Jogardi | Ongoing | 2725000 | 0 | 2023-09-10