## Work List
Exported on: 2026-09-07 08:15:35
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Badgyar
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / KUKSHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1722008023/DP/22012034584548 — वृक्षारोपण कार्य अमृत वाटिका बडग्यार बड़ा तालाब हाई स्कूल के पास बडग्यार | Ongoing | 56000.42 | 0 | 2024-01-20
DHAR / KUKSHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1722008023/DP/22012034610332 — निर्मल नीर कूप निर्माण स्कूल के पास बडग्यार | Physically Completed | 599950.51 | 0 | 2024-01-28 | 2026-07-29
DHAR / KUKSHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722008023/IF/22012034440406 — कपिल धारा कूप छोटु गोमा बडग्‍यार | Ongoing | 200000 | 0 | 2022-05-20
DHAR / KUKSHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722008023/IF/22012034440408 — कपिल धारा कूप माधु फुलसिेह बडग्‍यार | Ongoing | 200000 | 0 | 2022-05-24
DHAR / KUKSHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722008023/IF/22012034642723 — कपिलधारा कूप निर्माण रामलाल उदेयसिंह बडग्यार | Physically Completed | 246126.86 | 0 | 2021-02-05 | 2026-07-28
DHAR / KUKSHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722008023/IF/22012034660965 — कपिलधारा कूप निर्माण भागवन्तिबाई रामसिंह बड़ग्यार | Ongoing | 250732.62 | 0 | 2022-04-14
DHAR / KUKSHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722008023/IF/22012034748001 — GKRA cattals shead bharat manohar badgyar | Physically Completed | 102033.26 | 0 | 2021-05-27 | 2026-07-28
DHAR / KUKSHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722008023/IF/22012034920529 — Kapil Dhara Kup Chiranjiv s/o Chhitu B | Ongoing | 250732.62 | 0 | 2023-07-29
DHAR / KUKSHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722008023/IF/22012034937348 — Kapil Dhara Govind s/o Taja | Ongoing | 257014.43 | 0 | 2022-05-20
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008023/IF/22012035012685 — नंदन फलोउद्यान राजू पिता उगरसिंघ | Ongoing | 155560.72 | 0 | 2024-06-14
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008023/IF/22012035012688 — नंदन फलोउद्यान रीछु पिता हरसिंघ | Ongoing | 155560.72 | 0 | 2024-07-03
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008023/IF/22012035012689 — नंदन फलोउद्यान देवराज पिता नारायण | Ongoing | 155560.72 | 0 | 2025-04-02
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722008023/IF/22012035367310 — JGSA खेत तालाब निर्माण कार्य लक्ष्मण पिता खुमसिग के खेत में ब्डग्यार | Ongoing | 147621.16 | 0 | 2025-04-25
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722008023/IF/22012035367403 — JGSA खेत तालाब निर्माण कार्य शान्तिलाल पिता टिकम के खेत में ब्डग्यार | Ongoing | 147621.16 | 0 | 2025-04-25
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722008023/IF/22012035367447 — JGSA खेत तालाब निर्माण कार्य धनसिह पिता बाला के खेत में ब्डग्यार | Ongoing | 147621.16 | 0 | 2025-04-25
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722008023/IF/22012035383256 — JGSA डगवेल रिचार्ज पीट निर्माण गवरीबाई पति राजु के खेत में ब्डग्यार | Physically Completed | 25899.46 | 0 | 2025-04-25 | 2026-07-19
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722008023/IF/22012035411618 — JGSA Khat Talab Gamir Bharla Badgyar | Ongoing | 147621.16 | 0 | 2025-05-04
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722008023/IF/22012035412246 — JGSA Khat Talab Kalesh Sanker Badgyar | Approved | 0 | 0 | 2025-04-14
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722008023/IF/22012035461104 — JGSA Khet Talab Gulab Dabra Badgyar | Ongoing | 147621.16 | 0 | 2025-05-13
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722008023/IF/22012035461331 — JGSA Khet Talab Shukliya faatu Badgyar | Ongoing | 147621.16 | 0 | 2025-05-09
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722008023/IF/22012035468744 — JGSA DugWell Rechargh Pit Jitendra Chgan Badgyar | Physically Completed | 25899.46 | 0 | 2025-05-09 | 2026-07-19
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722008023/IF/22012035468765 — JGSA DugWell Rechargh Pit Gopal Hirla Badgyar | Physically Completed | 25899.46 | 0 | 2025-05-09 | 2026-09-04
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722008023/IF/22012035468802 — JGSA DugWell Rechargh Pit Dasrat Bharusingh Badgyar | Physically Completed | 25899.46 | 0 | 2025-05-09 | 2026-09-01
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722008023/IF/22012035477442 — JGSA khet talab nirman rangubai Pati Shankar badgyar | Ongoing | 147621.16 | 0 | 2025-05-13
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722008023/IF/22012035477475 — JGSA khet talab nirman sitaram ramsingh badgyar | Ongoing | 147621.16 | 0 | 2025-05-13
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722008023/IF/22012035477484 — JGSA khet talab nirman lakhansingh ramsingh badgyar | New | 0 | 0 | 2025-04-14
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722008023/IF/22012035477486 — JGSA khet talab nirman lakhansingh ramsingh badgyar | Approved | 147621.16 | 0 | 2025-04-14
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722008023/IF/22012035477641 — JGSA khet talab nirman kailash sardar badgyar | Ongoing | 147621.16 | 0 | 2025-05-13
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008023/IF/22012035590312 — EK Bagiya Maa Ke Naam Siyanibai Indersingh Badgyar | New | 0 | 0 | 2025-04-14
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008023/IF/22012035591389 — Ek Bagiya Maa ke Naam Siyani Bai Inder singh Badgya | Ongoing | 176928.95 | 2097.69 | 2025-09-24
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008023/IF/22012035603452 — Ek Bagiya Maa ke Naam Ramkany Bai Badgyar | Ongoing | 269386.03 | 0 | 2025-09-03
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008023/IF/22012035603455 — Ek Bagiya Maa ke Naam Ranga Bai Badgyar | New | 0 | 0 | 2025-04-14
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008023/IF/22012035604212 — EK Bagiya Maa Ke Naam BABITA MUZHALDA Badgyar | Ongoing | 269386.03 | 0 | 2025-09-03
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008023/IF/22012035604233 — EK Bagiya Maa Ke Naam SUKLI BAI Badgyar | Ongoing | 269386.03 | 0 | 2025-09-03
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008023/IF/22012035605677 — EK Bagiya Maa Ke Naam RANGA BAI Badgyar | Ongoing | 269386.03 | 0 | 2025-09-04
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008023/IF/22012035609095 — Ek Bagiya Maa ke Naam Birli Bai Desai Badgyar | Ongoing | 269386.03 | 0 | 2025-09-24
DHAR / KUKSHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/3696410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102895396 | Approved | 27000 | 0 | 2022-04-28
DHAR / KUKSHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/3704692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105506208 | Approved | 27000 | 0 | 2022-04-29
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4548813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107041531 | Completed | 23490 | 0 | 2025-08-06 | 2026-08-11
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4548814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107041555 | Approved | 27000 | 0 | 2024-09-14
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4556249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113911039 | Approved | 27000 | 0 | 2024-09-13
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4685253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103128176 | Approved | 27000 | 0 | 2024-09-25
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4685411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105974569 | Completed | 23490 | 0 | 2024-12-26 | 2026-07-28
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4686381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105244174 | Physically Completed | 27000 | 0 | 2025-01-30 | 2026-09-05
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4686794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103971313 | Ongoing | 27000 | 0 | 2025-01-02
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4736155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104905995 | Completed | 21870 | 0 | 2025-01-21 | 2026-08-11
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4736164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104908046 | Approved | 27000 | 0 | 2024-09-14
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4737481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105663538 | Completed | 23490 | 0 | 2025-01-21 | 2026-08-11
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4738301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105190556 | Completed | 23490 | 0 | 2024-12-26 | 2026-07-28
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4738644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106181918 | Completed | 21870 | 0 | 2025-01-09 | 2026-07-28
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4740580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106826920 | Physically Completed | 27000 | 0 | 2025-01-02 | 2026-09-05
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4743210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113863742 | Approved | 27000 | 0 | 2024-09-13
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4743481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113910920 | Approved | 27000 | 0 | 2024-09-23
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4783181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126510476 | Physically Completed | 27000 | 0 | 2025-01-21 | 2026-09-05
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4854141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105973782 | Approved | 27000 | 0 | 2024-09-25
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4855379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105663836 | Approved | 27000 | 0 | 2024-10-03
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4858484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105973143 | Physically Completed | 27000 | 0 | 2025-02-06 | 2026-09-05
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4858485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105974591 | Completed | 23490 | 0 | 2024-12-26 | 2026-07-28
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4859235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102227947 | Completed | 23490 | 0 | 2024-12-26 | 2026-07-28
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4859267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107041540 | Completed | 23490 | 0 | 2025-01-02 | 2026-08-11
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4864030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118176493 | Ongoing | 27000 | 0 | 2025-01-30
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/4864299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118499141 | Approved | 27000 | 0 | 2024-10-22
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/5386457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104907533 | Approved | 27000 | 0 | 2024-09-13
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/5387555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103526765 | Completed | 23490 | 0 | 2025-05-28 | 2026-08-11
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722008023/IF/IAY/5488438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113863726 | Completed | 23490 | 0 | 2025-05-16 | 2026-07-22
DHAR / KUKSHI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722008023/RC/22012034837352 — सुदूर सड़क निर्माण बडग्यार मैन रोड से नदीपुरा तक बडग्यार | Approved | 0 | 0 | 2025-01-26
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1722008023/WC/22012035114280 — पुलिया निर्माण नदीपुर रोड बडग्‍यार | Ongoing | 1455162.85 | 0 | 2024-12-26
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722008023/WC/22012035163194 — अर्थन डेम निर्माण | New | 0 | 0 | 2024-04-01
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722008023/WC/22012035223963 — अर्थन डेम निर्माण ग्वाल बयडा सुकलिया फत्तु के खेत के पास बडग्यार भाग 1 | Approved | 0 | 0 | 2024-07-01
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722008023/WC/22012035223965 — अर्थन डेम छगन चिमा के खेत के पास बडग्यार | New | 0 | 0 | 2024-07-01
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722008023/WC/22012035223966 — अर्थन डेम छगन चिमा के खेत के पास बडग्यार | Approved | 0 | 0 | 2024-07-01
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722008023/WC/22012035223969 — अर्थन डेम ग्वाल बयडा बडग्यार | Approved | 0 | 0 | 2024-07-01
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722008023/WC/22012035234539 — तालाब निर्माण छगन चिमा के मकान तक बयडीपुरा बडग्यार | Approved | 0 | 0 | 2024-07-01
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722008023/WC/22012035234650 — तालाब निर्माण राहुल के खेत के पास बडग्यार | Approved | 0 | 0 | 2024-07-01
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722008023/WC/22012035234651 — तालाब निर्माण चिरंजिव छितु के खेत के पास नाले पर बडग्यार | Approved | 0 | 0 | 2024-07-01
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722008023/WC/22012035234655 — तालाब निर्माण भगवंतिवाई के खेत के पास बडग्यार | Approved | 848595.32 | 0 | 2024-07-01
DHAR / KUKSHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722/WC/22012035139937 — Pipe puliya Nirman Karya Kaliyakhodra Nale Par Badgyar | Ongoing | 3880000 | 0 | 2023-10-09