## Work List
Exported on: 2026-10-26 14:48:03
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Girvanya
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / KUKSHI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1722008025/AV/22012034565920 — बाउण्ड्री वाल हाई स्कूल गिरवान्या | Physically Completed | 1192011.71 | 0 | 2021-08-26 | 2026-07-21
DHAR / KUKSHI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food Grain Storage Building for Community | Constr of Food Grain storage | 1722008025/AV/22012034571096 — स्कुल डायनिंग शासकीय हाईस्कुल गिरवान्या | Physically Completed | 32165.87 | 0 | 2021-08-26 | 2026-07-21
DHAR / KUKSHI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1722008025/AV/22012034589336 — boundriwall middile school girvaniya | Ongoing | 260199.54 | 0 | 2021-11-09
DHAR / KUKSHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722008025/DP/22012034530037 — निर्मल नीर हनुमान मंदीर के पास पटेलपुरा गिरवान्या | Ongoing | 478796.2 | 0 | 2021-09-03
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722008025/IC/22012034888441 — निर्मल नीर कुप निर्माण कार्य शान्तिधाम पर गिरवान्या | New | 0 | 0 | 2025-01-26
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722008025/IC/22012034891651 — कुप निर्माण सिंचाई हेतु समुदाय के लिए शांति धाम नदी के पास गिरवान्या | Physically Completed | 736900.62 | 0 | 2025-06-05 | 2026-07-21
DHAR / KUKSHI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722008025/IF/22012034418977 — कपील धाारा कुप अनिल विक्रम गिरवान्‍या | Ongoing | 200000 | 0 | 2018-08-23
DHAR / KUKSHI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722008025/IF/22012034418978 — कपीलधारा कुप कमलबाई कमलेश गिरवान्‍या | Completed | 200000 | 0 | 2018-12-06 | 2026-08-09
DHAR / KUKSHI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722008025/IF/22012034418982 — कपीलधारा कुप दुरसिंग नालु | Completed | 200000 | 0 | 2018-07-17 | 2026-08-09
DHAR / KUKSHI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722008025/IF/22012034418987 — कपीलधारा कुप बल्‍ला हेमता गिरवान्‍या | Completed | 200000 | 0 | 2018-08-14 | 2026-08-09
DHAR / KUKSHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722008025/IF/22012034860822 — कपिलधारा कूप निर्माण कुसूमबाई प्रध्युमन गिरवान्या | Physically Completed | 250732.62 | 0 | 2021-10-27 | 2026-07-21
DHAR / KUKSHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722008025/IF/22012034860849 — कपिलधारा कूप निर्माण रेशमबाई भुवान गिरवान्या | Ongoing | 250732.62 | 0 | 2021-10-23
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008025/IF/22012035620290 — Ek Bagiya Maa ke Naam Sangeeta Dawar Girwanya | Ongoing | 269386.03 | 0 | 2026-02-05
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008025/IF/22012035620300 — Ek Bagiya Maa ke Naam Kalm Bai Solanki Girwanya | Ongoing | 269386.03 | 0 | 2025-11-22
DHAR / KUKSHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/3646455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5545742 | Approved | 27000 | 0 | 2022-02-18
DHAR / KUKSHI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/37958 — इंदिरा आवास कालीबाई केरूसिह गिरवान्‍यां | Approved | 27000 | 0 | 2015-12-24
DHAR / KUKSHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4398063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116801957 | Approved | 27000 | 0 | 2023-01-31
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4570846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116791100 | Ongoing | 27000 | 0 | 2024-11-04
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4598671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122882890 | Physically Completed | 23490 | 0 | 2025-04-17 | 2026-07-30
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4612285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125623404 | Completed | 23490 | 0 | 2025-03-08 | 2026-07-30
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4613639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125636009 | Ongoing | 27000 | 0 | 2024-11-04
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4619903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126631291 | Physically Completed | 23490 | 0 | 2024-11-06 | 2026-07-30
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4657010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147755525 | Completed | 23490 | 0 | 2025-02-01 | 2026-07-30
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4688775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106649778 | Ongoing | 27000 | 0 | 2025-04-03
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4692894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116086698 | Approved | 27000 | 0 | 2024-09-20
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4698352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115118099 | Completed | 23490 | 0 | 2025-09-06 | 2026-07-30
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4704824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121552642 | Ongoing | 27000 | 0 | 2025-06-10
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4709700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124621444 | Physically Completed | 27000 | 0 | 2025-04-17 | 2026-10-25
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4712247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126188454 | Completed | 23490 | 0 | 2025-02-15 | 2026-07-30
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4749325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115073271 | Completed | 23490 | 0 | 2025-04-03 | 2026-07-30
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/4866023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125634350 | Ongoing | 27000 | 0 | 2025-06-10
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/5529424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147652330 | Approved | 27000 | 0 | 2025-02-24
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/5701553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115351967 | Physically Completed | 27000 | 0 | 2024-09-24 | 2026-10-25
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/5824231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114999675 | Physically Completed | 27000 | 0 | 2026-02-18 | 2026-10-25
DHAR / KUKSHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/5826117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123376276 | Approved | 27000 | 0 | 2024-09-24
DHAR / KUKSHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722008025/IF/IAY/5827263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106382356 | Ongoing | 27000 | 0 | 2026-02-10
DHAR / KUKSHI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Stone graded Bund for Community / Repair and Maintenance of Stone graded Bund for Community | Repair & Maint of Bund | 1722008025/LD/22012034571334 — वोल्डर वाल निर्माण बयडिया क्रमांक-2 गिरवान्या | Ongoing | 846573.62 | 0 | 2021-10-23
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1722008025/LD/22012034955453 — तालाब निर्माण कार्य नदीपार के पास गिरवान्या | Approved | 0 | 0 | 2025-04-26
DHAR / KUKSHI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722008025/RS/22012034616293 — SBM ISP व्यक्तिगत सोक पिट ( हितग्राही संख्या 10) यूनिट -8 गिरवानिया | Physically Completed | 128064.22 | 0 | 2021-11-21 | 2026-07-21
DHAR / KUKSHI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722008025/RS/22012034616301 — SBM ISP व्यक्तिगत सोक पिट ( हितग्राही संख्या 10) यूनिट 9 गिरवानिया | Physically Completed | 128064.22 | 0 | 2021-11-21 | 2026-07-21
DHAR / KUKSHI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722008025/WC/22012034939146 — अमृत सरोवर तालाब निर्माण देवी मंदीर के नीचे वाला नाला गिरवान्या | Ongoing | 1454636.55 | 0 | 2022-05-14
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008025/WC/22012035231631 — तालाब निर्माण कार्य चापरिया नाला पर गिरवान्या | Approved | 0 | 0 | 2024-07-01
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008025/WC/22012035248802 — तालाब निर्माण कार्य नदीपार के पास गिरवान्या | Approved | 0 | 0 | 2025-01-26
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008025/WC/22012035248805 — तालाब निर्माण कार्य सेमलीपुरा गिरवान्या | Approved | 0 | 0 | 2025-01-26
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008025/WC/22012035248807 — तालाब निर्माण कार्य राजु ऐडु के खेत के पास इमलीपुरा गिरवान्या | Approved | 0 | 0 | 2025-01-26
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008025/WC/22012035248810 — तालाब निर्माण कार्य गिट्टी मशीन के पास गिरवान्या | Approved | 0 | 0 | 2025-01-26
DHAR / KUKSHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008025/WC/22012035248813 — तालाब निर्माण कार्य चचर खेल्ली गिरवान्या | Approved | 0 | 0 | 2025-01-26
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008025/WC/22012035300746 — तालाब निर्माण कार्य चचर खेल्ली गिरवान्या | Ongoing | 1000519.62 | 0 | 2025-10-06
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008025/WC/22012035300765 — तालाब निर्माण कार्य चापरिया नाले पर गिरवान्या | Ongoing | 1005148.72 | 0 | 2025-09-13
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008025/WC/22012035300794 — तालाब निर्माण कार्य सेमलीपुरा गिरवान्या | Ongoing | 1132994.34 | 0 | 2025-11-17
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008025/WC/22012035315038 — तालाब निर्माण कार्य नदी पार के पास गिरवान्या | Ongoing | 1438995.59 | 0 | 2025-10-24
DHAR / KUKSHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722008025/WC/22012035315040 — तालाब निर्माण कार्य गिट्टी मशीन के पास गिरवान्या | Approved | 1393996.32 | 0 | 2025-04-26
DHAR / KUKSHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722008/IF/22012034836779 — plantation horticulture केशरबाई /अजय ग्राम गिरवान्या | Ongoing | 143340 | 0 | 2021-11-24
DHAR / KUKSHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722008/WC/22012034614594 — Nistar Talab Nirman Kakad Wala Nala Girwaniya | Physically Completed | 2475000 | 0 | 2021-02-11 | 2026-08-02