## Work List
Exported on: 2026-10-05 04:10:42
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Palasi
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / DAHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722009001/DP/22012034486905 — Nirmal neer Samsan Ghate mai palasi | Ongoing | 464568.96 | 0 | 2020-05-06
DHAR / DAHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1722009001/DP/22012034584297 — VASUDHA VANDAN NISTAR TALAB CHIRLIYAKHODRI PALASHI | Ongoing | 54564.94 | 0 | 2023-08-24
DHAR / DAHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009001/IF/22012034637514 — KAPILDHARA KUP NIRMAN RAMESH KULHA PALASI | Ongoing | 246126.86 | 0 | 2020-12-23
DHAR / DAHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009001/IF/22012034637521 — KAPILDHARA KUP NIRMAN MADAN DALA PALASI | Ongoing | 246126.86 | 0 | 2020-12-23
DHAR / DAHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009001/IF/22012034997761 — KAPILDHARA KUP MUKAM SINGH SOLANKI PALASI | Ongoing | 257014.43 | 0 | 2022-10-31
DHAR / DAHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009001/IF/22012034999497 — KAPIL DHARA KUP KALUSINGH TADWAL PALASI | Ongoing | 257014.43 | 0 | 2022-10-31
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035068502 — PASHU SHED NIRMAN NARSINGH RAMSINGH PALASHI | Ongoing | 122042.42 | 0 | 2023-08-06
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035131436 — CATTLE SHED BONDARSINGH MOHANSINGH PALASI | Physically Completed | 121042.42 | 0 | 2023-08-06 | 2026-08-04
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035140485 — CATTLE SHED PRAKASH MAGAN PALASI | Physically Completed | 72618.65 | 0 | 2023-10-07 | 2026-08-04
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035141313 — CATTLE SHED MOHAN SOLANKI PALASI | Physically Completed | 72618.65 | 0 | 2023-10-06 | 2026-08-04
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035141315 — CATTLE SHED KESHARSINGH NAVALSINGH PALASI | Physically Completed | 72618.65 | 0 | 2024-01-13 | 2026-08-04
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035157641 — CATTLESHED MUKESH NARAYAN PALASI | Ongoing | 72618.65 | 0 | 2023-10-07
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035157644 — CATTLESHED DEDHU HARESINGH PALASI | Physically Completed | 72618.65 | 0 | 2023-10-07 | 2026-08-04
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035157645 — CATTLE SHED SUSHILA AMARSINGH PALASI | Physically Completed | 72618.65 | 0 | 2023-10-07 | 2026-08-04
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035157648 — CATTLE SHED VERSINGH MOHAN PALASI | Physically Completed | 72618.65 | 0 | 2023-10-07 | 2026-08-04
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035157651 — CATTLE SHED MADAN GOKHALE PALASI | Physically Completed | 72618.65 | 0 | 2023-10-07 | 2026-08-04
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035157656 — CATTLE SHED PREMSINGH DASHRATH PALASI | Ongoing | 72618.65 | 0 | 2023-10-07
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035159026 — CATTLE SHED MITHUSINGH JAMOD PALASI | Physically Completed | 72618.65 | 0 | 2023-10-07 | 2026-08-04
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035159180 — CATTLE SHED GANPAT JAMOD PALASI | Ongoing | 72618.65 | 0 | 2024-01-13
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035310213 — पशु शेड निर्माण राजू पिता वेस्ता | Approved | 0 | 0 | 2024-10-02
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035310217 — पशु शेड निर्माण बोंदर सिंह पिता रतनसिंह | Approved | 0 | 0 | 2024-10-02
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035310884 — पशु शेड निर्माण धर्मन्द्र पिता कलसिंह जामोदा | Approved | 0 | 0 | 2024-10-02
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009001/IF/22012035310885 — पशु शेड निर्माण शेरसिंह पिता कुवरसिंह | Approved | 0 | 0 | 2024-10-02
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722009001/IF/22012035458136 — JGSA RECHARGE PIT NIRMAN DHEDUSINGH HARSINGH | Physically Completed | 25899.46 | 0 | 2025-05-09 | 2026-08-03
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722009001/IF/22012035458186 — JGSA RECHARGE PIT NIRMAN ABHAYSINGH DITU | Physically Completed | 25899.46 | 0 | 2025-07-15 | 2026-08-03
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722009001/IF/22012035458349 — JGSA RECHARGE PIT NIRMAN GOVIND GUMAN | New | 0 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722009001/IF/22012035458378 — JGSA RECHARGE PIT NIRMAN GOVIND GUMAN | New | 0 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722009001/IF/22012035458498 — JGSA RECHARGE PIT NIRMAN GUMAN SOKLIYA | Physically Completed | 25899.46 | 0 | 2025-05-09 | 2026-08-03
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722009001/IF/22012035458544 — JGSA RECHARGE PIT NIRMAN DEVRAM VESTA | New | 0 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722009001/IF/22012035578083 — JGSA DUGWELL RICHARGE PIT MOHAN /CHAGANSING PALASI | Approved | 0 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722009001/IF/22012035578084 — JGSA DUGWELL RICHARGE PIT KESARSING/NAWALSING PALASI | Approved | 0 | 0 | 2025-04-14
DHAR / DAHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722009001/IF/22012035586532 — pm awas mukesh/ rupsing palasi | Ongoing | 23450 | 0 | 2026-06-21
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009001/IF/22012035604706 — kapil dhara kup pratap/chamar palasi | Approved | 0 | 0 | 2025-08-18
DHAR / DAHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722009001/IF/22012035608464 — ek bagiya maa k naam birli bai palasi | Ongoing | 269386.03 | 0 | 2026-05-29
DHAR / DAHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722009001/IF/22012035608466 — ek bagiya maa k naam mamta solanki palasi | Ongoing | 269386.03 | 0 | 2026-05-30
DHAR / DAHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722009001/IF/22012035614750 — PM AWAS DURSING/ TUDLA PALASI PMID MP 115342620 | Ongoing | 23500 | 0 | 2026-06-21
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009001/IF/22012035622235 — KAPILDHARA KUP KESHARSING/NAWALSING PALASI | Approved | 0 | 0 | 2025-08-18
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009001/IF/22012035623879 — KAPIL DHARA KUP NIRMAN SUNDERSING/ NAWALSING PLASI | Approved | 0 | 0 | 2025-08-18
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4542726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106010695 | Completed | 23490 | 0 | 2024-10-06 | 2026-07-29
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4543916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106434086 | Ongoing | 27000 | 0 | 2024-10-06
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4544956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106308870 | Completed | 23490 | 0 | 2024-10-06 | 2026-07-29
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4547430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106667984 | Completed | 23490 | 0 | 2024-10-06 | 2026-07-29
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4547557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106689135 | Completed | 23490 | 0 | 2024-10-06 | 2026-08-04
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4548410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106866600 | Completed | 23490 | 0 | 2024-10-06 | 2026-08-04
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4548949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106412268 | Completed | 23490 | 0 | 2024-10-06 | 2026-07-29
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4549643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106734875 | Completed | 23490 | 0 | 2024-10-06 | 2026-07-29
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4549734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106747579 | Ongoing | 27000 | 0 | 2024-10-06
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4550263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113463789 | Completed | 23490 | 0 | 2024-10-06 | 2026-07-29
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4560470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115095097 | Completed | 23490 | 0 | 2024-10-06 | 2026-08-04
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4560541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115103831 | Completed | 23490 | 0 | 2024-10-24 | 2026-07-29
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4608493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114706855 | Completed | 23490 | 0 | 2024-10-06 | 2026-07-29
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4670326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107052413 | Completed | 23490 | 0 | 2024-10-06 | 2026-07-29
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4670330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107055741 | Completed | 23490 | 0 | 2024-10-06 | 2026-08-04
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4672036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114998673 | Completed | 23490 | 0 | 2025-02-17 | 2026-07-29
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/4742175 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113449969 | Ongoing | 27000 | 0 | 2025-02-17
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5187315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114750473 | Physically Completed | 23490 | 0 | 2025-08-14 | 2026-07-29
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5387064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114990992 | Completed | 23490 | 0 | 2025-04-19 | 2026-07-29
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5400903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114731367 | Ongoing | 27000 | 0 | 2025-07-11
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5404234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113869020 | Ongoing | 27000 | 0 | 2025-06-11
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5408209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304254 | Ongoing | 27000 | 0 | 2025-08-04
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5408718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114792518 | Ongoing | 27000 | 0 | 2025-04-19
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5622329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114727871 | Physically Completed | 23490 | 0 | 2025-06-25 | 2026-07-29
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5622634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115012032 | Completed | 23490 | 0 | 2025-06-25 | 2026-07-29
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5622959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115138005 | Completed | 23490 | 0 | 2025-06-25 | 2026-08-03
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5623357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115127637 | Ongoing | 27000 | 0 | 2025-06-08
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5624268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115182132 | Ongoing | 27000 | 0 | 2025-06-25
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5711241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115096300 | Ongoing | 27000 | 0 | 2025-10-09
DHAR / DAHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5718424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115093836 | Ongoing | 27000 | 0 | 2026-07-16
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009001/IF/IAY/5735197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114729806 | Ongoing | 27000 | 0 | 2025-10-09
DHAR / DAHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722009001/WC/22012034966520 — NSP PRACOLATION TANK TIKLIBAYDI PALASHI | Ongoing | 533626.63 | 0 | 2023-10-09
DHAR / DAHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722009001/WC/22012035111008 — RMS SAH PULIYA NIRMAN DUKALSINGH GHAR PAS PALASI | Ongoing | 1256134.02 | 0 | 2023-10-05
DHAR / DAHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722009001/WC/22012035163581 — PARCOLATION TANK PALASI | New | 0 | 0 | 2024-01-27
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722009001/WC/22012035320211 — TALAB NIRMAN NEW MALIPURA PALASI | Approved | 0 | 0 | 2025-08-18
DHAR / DAHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722/RC/22012034663561 — Slab Culvert Sah R-Wall Nirman Karya Char Chauraha Per Palasi | Ongoing | 4832000 | 0 | 2023-10-06