## Work List
Exported on: 2026-10-11 04:05:56
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Atarsuma
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / DAHI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1722009024/AV/22012034635266 — PULIYA NIRMAN SHAMSHANGHAT MANKARPURA ATARSUMA | Ongoing | 1030659.46 | 0 | 2023-07-01
DHAR / DAHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722009024/DP/22012034556397 — NIRMAL NIR PATELPURA ATARSUMA | Ongoing | 489496.27 | 0 | 2023-10-27
DHAR / DAHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1722009024/DP/22012034584903 — VASUDHA VANDAN AGANWADI BHAWAN KE PASS ATARSUMA | Ongoing | 55740.22 | 0 | 2024-03-29
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Groups / Construction of Irrigation Well for Groups | Construction of Well | 1722009024/IC/22012034891830 — NIRMAL NEER KUP BARA PURA ATARSUMA | New | 0 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Groups / Construction of Irrigation Well for Groups | Construction of Well | 1722009024/IC/22012034891912 — NIRMAL NEER KUP NIRMAN BANDIYAPURA ATARSUMA | New | 0 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722009024/IC/22012034893374 — Nirmal neer kup nirman Kadiya khodara Atarsuma | New | 0 | 0 | 2026-01-28
DHAR / DAHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012034473698 — कपिल धारा कूप सेवलीय भारत अतरसुमा | Ongoing | 200000 | 0 | 2020-05-24
DHAR / DAHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012034638343 — KAPIL DHARA KUP AMARSINGH JHETRIYA ATARSUMA | Physically Completed | 246126.86 | 0 | 2021-05-25 | 2026-09-10
DHAR / DAHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012034638344 — KAPIL DHARA GANGARAM MALU ATARSUMA | Ongoing | 246126.86 | 0 | 2021-02-15
DHAR / DAHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012034639777 — KAPIL DHARA EDLA RATNYA ATARSUMA | Ongoing | 246126.86 | 0 | 2020-12-30
DHAR / DAHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012034641868 — KAPIL DHARA BHUPENDRA MADHAWSINGH ATARSUMA | Ongoing | 246126.86 | 0 | 2021-01-11
DHAR / DAHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012034641871 — KAPIL DHARA AMANSIGH GULABSINGH ATARSUMA | Ongoing | 246126.86 | 0 | 2021-01-11
DHAR / DAHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012034641872 — KAPIL DHARA KAILASH NURU ATARSUMA | Physically Completed | 246126.86 | 0 | 2021-04-01 | 2026-09-10
DHAR / DAHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012034641873 — KAPIL DHARA SURMAL JOGDA ATARSUMA | Ongoing | 246126.86 | 0 | 2021-02-13
DHAR / DAHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012034642450 — PASHU SHED NIRMAN LATA LAXMAN ATRSUMA | Ongoing | 101804.91 | 0 | 2021-09-25
DHAR / DAHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012034642452 — PASHU SHED DEDU NAHARSINGH ATARSUMA | Physically Completed | 101804.91 | 0 | 2021-10-04 | 2026-08-10
DHAR / DAHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012034642453 — PASHU SHED CHANDERSINGH MAKANA ATARSUMA | Ongoing | 101804.91 | 0 | 2021-06-17
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012034642454 — PASHU SHED SURESH IDLA ATARSUMA | Physically Completed | 101804.91 | 0 | 2024-04-17 | 2026-08-10
DHAR / DAHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012034642455 — PASHU SHED SURPAL JOGDA ATARSUMA | Physically Completed | 101804.91 | 0 | 2021-10-04 | 2026-08-10
DHAR / DAHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012034642456 — PASHU SHED ARJUN BHUWANSINGH ATARSUMA | Ongoing | 101804.91 | 0 | 2021-08-21
DHAR / DAHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012034642458 — PASHU SHED BHAYLA MALU ATARSUMA | Physically Completed | 101804.91 | 0 | 2021-10-04 | 2026-08-10
DHAR / DAHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012034819320 — KAPIL DHARA LALSINGH ANGARSINGH ATARSUMA | Physically Completed | 250732.62 | 0 | 2023-02-01 | 2026-09-10
DHAR / DAHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1722009024/IF/22012034901952 — BAKARI SHED KUSMA BEWA BABU ATRSUMA | Ongoing | 47439.69 | 0 | 2021-12-04
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012034993900 — KAPIL DHARA KUP BHANGDA HATIYA ATARSUMA | Ongoing | 244512.73 | 0 | 2023-06-18
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012034993927 — PASHU SHED NIRMAN KAVITA DILIP ATARSUMA | Physically Completed | 128997.74 | 0 | 2023-08-06 | 2026-08-10
DHAR / DAHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012034993933 — PASHU SHED NIRMAN GENSINGH HARI ATARSUMA | Physically Completed | 103482.45 | 0 | 2023-01-12 | 2026-09-10
DHAR / DAHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012034993944 — PASHU SHED NIRMAN DHURJI BALU ATARSUMA | Physically Completed | 103482.45 | 0 | 2023-01-07 | 2026-08-10
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012034995003 — PASHU SHED NIRMAN BHUPENDRA ATARSUMA | Ongoing | 103482.45 | 0 | 2023-06-18
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012034995424 — PASHU SHED NIRMAN MAGAN SUKA ATARSUMA | Ongoing | 103482.45 | 0 | 2023-08-11
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012035000785 — PASHU SHED HIMMAT RAMSINGH ATRSUMA | Physically Completed | 128688.04 | 0 | 2023-08-06 | 2026-08-24
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012035001874 — PASHU SHED SUNITA RAKESH ATARSUMA | Physically Completed | 128122.31 | 0 | 2023-08-06 | 2026-08-10
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012035092442 — KAPILDHARA REMSINGH MANDLOI ATARSUMA | Ongoing | 238294.3 | 0 | 2025-05-31
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722009024/IF/22012035132814 — CATTLE SHED JUGDA SUKLA ATARSUMA | Ongoing | 128688.04 | 0 | 2025-03-21
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012035472906 — JGSA Dugwell Richarge Pit Bhangda Balu Thandla | New | 0 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722009024/IF/22012035486411 — JGSA Dugwell Richarge Pit Madhu Jogda Atarsuma | Approved | 25899.46 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722009024/IF/22012035486415 — JGSA Dugwell Richarge Pit Bhangda Balu Atarsuma | Approved | 25899.46 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722009024/IF/22012035486421 — JGSA Dugwell Richarge Pit Kansingh Jogda Atarsuma | Approved | 25899.46 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722009024/IF/22012035486427 — JGSA Dugwell Richarge Pit Gensingh Harliya Atarsuma | Approved | 25899.46 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722009024/IF/22012035492232 — JGSA Khet Talab Himmatsingh Ramsingh Atarsuma | Approved | 147621.16 | 0 | 2025-04-14
DHAR / DAHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722009024/IF/22012035492238 — JGSA Khet Talab Bahadur Dhurja Atarsuma | Ongoing | 147621.16 | 0 | 2026-07-07
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012035533888 — KAPILDHARA KUP SAMRAT/DASHRIYA ATARSUMA | New | 0 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012035535710 — KAPIL DHARA KUP DHARMENDRASING/GAMIRSING ATARSUMA | Approved | 0 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012035548769 — खेत तालाब निर्माण राजेश पिता गोपाल | New | 0 | 0 | 2025-04-26
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/22012035570489 — kapildhara kup DHURJI/ BALU ATARSUMA | New | 0 | 0 | 2025-04-14
DHAR / DAHI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722009024/IF/9993741731 — KAPIL DHARA SOMLA RATAN ATRASUMA | Ongoing | 200000 | 0 | 2016-06-10
DHAR / DAHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/3289750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3578019 | Ongoing | 27000 | 0 | 2023-11-21
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/4550192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456906 | Physically Completed | 27000 | 0 | 2025-11-20 | 2026-10-04
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/4561965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115124581 | Physically Completed | 21870 | 0 | 2024-12-19 | 2026-08-24
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/4564570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116277095 | Physically Completed | 23490 | 0 | 2025-04-10 | 2026-08-10
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/4581903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119559771 | Approved | 27000 | 0 | 2024-09-10
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/4672937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117419594 | Ongoing | 27000 | 0 | 2024-10-24
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/4673699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119564505 | Approved | 27000 | 0 | 2024-09-10
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/4675230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119589124 | Completed | 23490 | 0 | 2024-10-24 | 2026-09-16
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/4689804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107081186 | Physically Completed | 23490 | 0 | 2024-10-24 | 2026-08-10
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/4694355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116195345 | Completed | 23490 | 0 | 2025-03-21 | 2026-07-28
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/4698959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119582808 | Physically Completed | 23490 | 0 | 2024-11-19 | 2026-08-10
DHAR / DAHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/4793824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145668257 | Completed | 23490 | 0 | 2024-11-19 | 2026-07-28
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5165852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119622798 | Completed | 23490 | 0 | 2025-09-09 | 2026-07-28
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5211290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116254915 | Physically Completed | 27000 | 0 | 2025-07-09 | 2026-09-27
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5224501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119628399 | Completed | 23490 | 0 | 2025-09-09 | 2026-07-28
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5244747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116301463 | Physically Completed | 23490 | 0 | 2025-10-31 | 2026-08-10
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5254984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126311378 | Physically Completed | 23490 | 0 | 2025-10-31 | 2026-08-10
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5262366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117475196 | Physically Completed | 27000 | 0 | 2025-05-27 | 2026-09-23
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5296317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115008508 | Physically Completed | 23490 | 0 | 2025-05-02 | 2026-08-10
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5297067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117800151 | Physically Completed | 23490 | 0 | 2025-10-31 | 2026-08-24
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5307034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107414806 | Physically Completed | 23490 | 0 | 2025-05-21 | 2026-08-10
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5315634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126640386 | Ongoing | 27000 | 0 | 2025-07-26
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5316664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126312536 | Ongoing | 27000 | 0 | 2025-09-09
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5335798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115150269 | Completed | 23490 | 0 | 2025-07-12 | 2026-09-16
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5338585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113942956 | Physically Completed | 23490 | 0 | 2025-07-09 | 2026-08-10
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5388040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119591088 | Physically Completed | 23490 | 0 | 2025-10-31 | 2026-08-10
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5544269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133265546 | Physically Completed | 27000 | 0 | 2025-09-09 | 2026-09-15
DHAR / DAHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5609951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116290824 | Ongoing | 27000 | 0 | 2026-09-30
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5717980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113463365 | Ongoing | 27000 | 0 | 2025-08-20
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5809734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145669898 | Physically Completed | 23490 | 0 | 2025-10-31 | 2026-08-05
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5864728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145668244 | Physically Completed | 27000 | 0 | 2025-04-16 | 2026-09-27
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5864871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107040687 | Physically Completed | 27000 | 0 | 2026-01-20 | 2026-09-23
DHAR / DAHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5879936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116195341 | Ongoing | 27000 | 0 | 2026-09-30
DHAR / DAHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722009024/IF/IAY/5880117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113451616 | Approved | 27000 | 0 | 2025-05-24
DHAR / DAHI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722009024/RS/22012034530708 — SBM SP SOKHTA GADDA 5 UNIT NO 1 MALIPURA ATARSUMA | Ongoing | 60038.85 | 0 | 2022-09-20
DHAR / DAHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Masonry/CC Anicut for Community / Repair & Maintenance of Masonry Check Dam for Community | Repair & maint of Water Harvesting Structures | 1722009024/WC/22012034586359 — RMS NIRMAN MANAKPURA NALA BAPUSINGH KE GHAR KE PAAS ATARSUMA | Ongoing | 1497063.54 | 0 | 2023-10-14
DHAR / DAHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722009024/WC/22012034586361 — RMS NIRMAN MANKARPURA GHATI ATARSUMA | Ongoing | 1471018.81 | 0 | 2023-07-23
DHAR / DAHI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722009024/WC/22012034859380 — CTRA ROOFTOP WATER HARVESTING NEW ATIRIKT PRATHMIK SCHOOL MANKARPURA | Physically Completed | 32875.28 | 0 | 2021-11-22 | 2026-09-10
DHAR / DAHI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722009024/WC/22012035022113 — Parcolation Tank Tetiya Radtiya ke khet ke pas Wala Nala Atarsuma | Ongoing | 867807.88 | 0 | 2022-12-07
DHAR / DAHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722009024/WC/22012035125527 — RMA NIRMAN UTARU NLA ATARSUMA | Ongoing | 1915000 | 0 | 2023-10-16
DHAR / DAHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722009024/WC/22012035141270 — PARCOLATION TANK NIRMAN RAHUL KE KHET KE PASS | Ongoing | 995000 | 0 | 2023-12-07
DHAR / DAHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722009024/WC/22012035161709 — PERCOLATION TANK ATARSUMA | New | 0 | 0 | 2024-01-27
DHAR / DAHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722009024/WC/22012035243290 — Earthen Dam Nirman Karya Shivam Badri Ke Khet Pass Atarsuma | Ongoing | 499999.58 | 0 | 2025-03-03
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722009024/WC/22012035303430 — Percolation Tank Nirman Ganesh Ke Khet Pass Atarsuma | Approved | 349998.92 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722009024/WC/22012035303431 — Percolation Tank Nirman Mukesh Ke Khet Pass Atarsuma | Ongoing | 499998.34 | 0 | 2025-05-31
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722009024/WC/22012035307495 — TALAB NIRMAN MALIPURA ATARSUMA | Approved | 0 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722009024/WC/22012035308983 — TALAB NIRMAN BAHADUR KE KHET KE PASS ATARSUMA | Approved | 0 | 0 | 2025-04-14
DHAR / DAHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722009024/WC/22012035329283 — talab Nirman Karya Sur singh Ke Khet Pass Atarsuma | Approved | 0 | 0 | 2026-01-28