## Work List
Exported on: 2026-10-01 14:30:30
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Nanoda
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / NISARPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722010012/AV/22012034615704 — Hoj Nirman Hanuman Mandeer Nanoda | Physically Completed | 8000 | 0 | 2022-03-20 | 2026-09-22
DHAR / NISARPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722010012/AV/22012034615705 — Hoj Nirman Surpal Mohalla Nanoda | Physically Completed | 8000 | 0 | 2022-03-20 | 2026-09-22
DHAR / NISARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1722010012/DP/22012034534978 — SBM SKGP P.S.NANODA | Ongoing | 11397.42 | 0 | 2021-11-27
DHAR / NISARPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1722010012/DP/22012034568605 — Plantation shitlamata mandir Gorvement Land Par 625 | Ongoing | 713691.92 | 300 | 2022-09-15
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722010012/IF/22012035639079 — MP119627107 Himmat Rukhadiya | Ongoing | 23490 | 0 | 2025-12-03
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/3287769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1496329 | Ongoing | 27000 | 0 | 2024-10-23
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4079322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119649496 | Ongoing | 27000 | 0 | 2024-10-23
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4554306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114736817 | Ongoing | 27000 | 0 | 2024-10-23
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4757480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118550253 | Ongoing | 27000 | 0 | 2025-02-18
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4757487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118551447 | Ongoing | 27000 | 0 | 2025-02-18
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4757518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118557145 | Ongoing | 27000 | 0 | 2025-02-18
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4757532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118562186 | Ongoing | 27000 | 0 | 2024-12-25
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4758402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119558925 | Approved | 27000 | 0 | 2024-09-16
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4758497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119582638 | Ongoing | 27000 | 0 | 2025-02-18
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4758532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119589244 | Approved | 27000 | 0 | 2024-09-21
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4759057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119665541 | Ongoing | 27000 | 0 | 2024-12-13
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4759078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119671105 | Ongoing | 27000 | 0 | 2024-12-01
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4765249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115386560 | Ongoing | 27000 | 0 | 2024-12-25
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/4778951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126474329 | Approved | 27000 | 0 | 2024-10-07
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5330683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119569208 | Approved | 27000 | 0 | 2025-02-28
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5357353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130484718 | Ongoing | 27000 | 2310 | 2025-07-27
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5362149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119642290 | Ongoing | 27000 | 0 | 2025-08-13
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5507050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120232046 | Completed | 27000 | 6900 | 2025-08-12 | 2026-09-28
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5511356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130473352 | Completed | 23490 | 0 | 2025-08-13 | 2026-07-29
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5605637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126256936 | Completed | 27000 | 4200 | 2025-07-27 | 2026-09-28
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5644996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130453004 | Ongoing | 27000 | 6600 | 2025-08-13
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5811738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131713346 | Approved | 27000 | 0 | 2025-05-02
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5811938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119557557 | Approved | 27000 | 0 | 2025-03-01
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5811940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119605480 | Approved | 27000 | 0 | 2025-02-25
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5811941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119612545 | Approved | 27000 | 0 | 2025-04-21
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5811942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119622795 | Ongoing | 27000 | 0 | 2025-11-01
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5811974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119620373 | Approved | 27000 | 0 | 2025-02-25
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5812217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130480816 | Approved | 27000 | 0 | 2025-04-04
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5812501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126633506 | Approved | 27000 | 0 | 2025-03-05
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5812523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118566757 | Approved | 27000 | 0 | 2025-03-10
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/5812569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126618480 | Ongoing | 27000 | 0 | 2025-10-17
DHAR / NISARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010012/IF/IAY/6396797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127782650 | Approved | 27000 | 0 | 2026-08-12
DHAR / NISARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722010012/RC/22012034619635 — C.C Road Primary School Se Bhuvan Ke Makan Tak Motlapura Nanoda | Completed | 63000 | 0 | 2022-11-17 | 2026-09-28
DHAR / NISARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1722010012/RC/22012034829464 — Vraksharopan karya Hanuman Mandir se Vijay sencha ke kothar tak | Ongoing | 453563.17 | 0 | 2024-11-27
DHAR / NISARPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722010012/RC/22012034841368 — cc road sarkari kup say bayraw mandir tak nanoda | New | 0 | 0 | 2025-04-01
DHAR / NISARPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722010012/RC/22012034841839 — सीसी रोड निर्माण कुवे से मंदिर रोड नैनोदा | Approved | 0 | 0 | 2025-04-01
DHAR / NISARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1722010012/RS/22012034578914 — SBM-कंपोस्ट पिट नानोदा | Ongoing | 16547.73 | 0 | 2024-11-27
DHAR / NISARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722010012/RS/22012034674253 — Nali Nirman Rumal Ke Makan Se Naale Tak Nanoda | Physically Completed | 37000 | 0 | 2022-12-02 | 2026-09-28
DHAR / NISARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722010012/RS/22012034674255 — Nali Nirman Omkar Ke Makan Se Lokesh Ke Makan Tak Nanoda | Physically Completed | 21000 | 0 | 2022-11-30 | 2026-09-28
DHAR / NISARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722010012/WC/22012035195657 — नाला टेंचिंग किशोर के खेत से बडे नाले तक | Physically Completed | 133578.12 | 0 | 2024-04-19 | 2026-07-27
DHAR / NISARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722010012/WC/22012035237499 — पर्कोलेशन टेक शासकीय भूमि पर नैनोदा | Ongoing | 203862.4 | 0 | 2025-01-22
DHAR / NISARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035016155 — उद्यानिकी निजी खेत पौधरोपण कार्य निर्मला ननोदा | Physically Completed | 745348 | 0 | 2022-09-20 | 2026-07-19
DHAR / NISARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035025527 — उद्यानिकी निजी खेत पौधरोपण कार्य जयंती ननोदा | Ongoing | 559011 | 0 | 2022-10-15
DHAR / NISARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722010/WC/22012034602988 — RFR Antargat RMS Cum Retaining Wall Nirman Nanoda | Physically Completed | 3687000 | 0 | 2020-12-20 | 2026-09-22