## Work List
Exported on: 2026-09-30 07:03:34
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Konda
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / NISARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722010025/AV/22012034648754 — Construction of Retaining Wall angawadi Bhawan Se Puliya Tak | Ongoing | 735000 | 0 | 2023-10-07
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722010025/IF/22012035352403 — खेत तालाब निर्माण निर्भय सिंह मुतरिया | Approved | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722010025/IF/22012035354977 — खेत तालाब निर्माण रायली पति प्रभु | New | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722010025/IF/22012035393636 — डगवेल कूप रिचार्ज लाला आला | Approved | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722010025/IF/22012035393653 — डगवेल कूप रिचार्ज शांताबाई रामा | Approved | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722010025/IF/22012035409267 — कपिलधारा कूप निर्माण सिंचाई हेतु इन्दरसिंह रणछोड़ कोणदा | New | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722010025/IF/22012035409292 — कपिलधारा कूप निर्माण सिंचाई हेतु इन्दरसिंह रणछोड़ कोणदा | Approved | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722010025/IF/22012035409373 — कपिलधारा कूप निर्माण धनकीबाई बेवा चेनाजी कोणदा | Approved | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1722010025/IF/22012035456721 — डगवेल कूप रिचार्ज प्रभु मुतरिया | New | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722010025/IF/22012035459985 — कपिलधारा कूप निर्माण कंचन बाई नाथिया कोणदा | Approved | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722010025/IF/22012035548560 — डगवेल कूप रिचार्ज डोंगरसिंह नरसिंह | Approved | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722010025/IF/22012035548590 — खेत तालाब निर्माण डोंगरसिंह नरसिंह | Approved | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722010025/IF/22012035556285 — डगवेल कूप रिचार्ज राजाराम कोरजी | Approved | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722010025/IF/22012035556328 — डगवेल कूप रिचार्ज दयाराम कोरजी | Approved | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722010025/IF/22012035556358 — डगवेल कूप रिचार्ज दशरथ हरिया | Approved | 0 | 0 | 2025-04-15
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035597759 — एक बगिया माँ के नाम लक्ष्मीबाई MP22010025001280 | Ongoing | 269386.03 | 10800 | 2025-12-25
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035598873 — एक बगिया माँ के नाम चुनकी बाई MP22010025001276 | Approved | 269386.03 | 0 | 2025-08-20
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035605325 — एक बगिया माँ के नाम राधा बाई लूनाजी MP22010025001197 | Ongoing | 269386.03 | 0 | 2025-12-25
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035605358 — एक बगिया माँ के नाम राधा ममता पडियार काना MP22010025001914 | Approved | 269386.03 | 0 | 2025-08-20
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035605430 — एक बगिया माँ के नाम सुनीता बर्फा गोविन्द MP22010025001913 | Approved | 269386.03 | 0 | 2025-08-20
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035605468 — एक बगिया माँ के नाम मडिबाई नारायण MP22010025001281 | Ongoing | 269386.03 | 10500 | 2025-12-25
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035605504 — एक बगिया माँ के नाम गीताबाई गोपाल MP22010025001296 | Ongoing | 269386.03 | 7200 | 2025-12-25
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035605559 — एक बगिया माँ के नाम मंगतीबाई चेनाजी MP22010025001282 | Ongoing | 269386.03 | 5700 | 2025-12-25
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035605644 — एक बगिया माँ के नाम पुष्पाबाई संजय MP22010025001274A | Ongoing | 269386.03 | 11400 | 2025-12-25
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035605686 — एक बगिया माँ के नाम घिशलिबाई प्रभु MP22010025001344A | Approved | 269386.03 | 0 | 2025-08-20
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035605759 — एक बगिया माँ के नाम पिंकी दीपक MP22010025001221 | Approved | 269386.03 | 0 | 2025-08-20
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035605782 — एक बगिया माँ के नाम सुन्दरबाई बाबु MP22010025001337 | New | 0 | 0 | 2025-08-20
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035605803 — एक बगिया माँ के नाम धनु बाई MP22010025001305 | Ongoing | 269386.03 | 0 | 2026-02-19
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010025/IF/22012035605866 — एक बगिया माँ के नाम ज्योति बाई MP22010025001377 | Ongoing | 269386.03 | 10800 | 2026-02-19
DHAR / NISARPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722010025/IF/IAY/567187 — Construction of IAY House -IAY REG. NO. MP3939491 | Approved | 27000 | 0 | 2017-01-12
DHAR / NISARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722010/WC/22012034602993 — RFR Antargat RMS Cum Pipe Culvert Nirman Prabhu Mutriya Ke Khet Pas No.1 Konda | Ongoing | 4154000 | 0 | 2021-04-12