## Work List
Exported on: 2026-10-05 02:27:00
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Chandankhedi
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / NISARPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen Shed for Government School for Community | Constr of Kitchen Shed | 1722010031/AV/22012034572992 — Dining Hall P.S.Chandankhedi | Completed | 21360.92 | 0 | 2021-08-07 | 2026-08-04
DHAR / NISARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1722010031/DP/22012034495836 — Plantation karya panchayat bhawan ke pas chandankhedi | Ongoing | 390826.48 | 0 | 2020-09-13
DHAR / NISARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation of Forestry-Community / Canal Line Plantation for Community | Plantation | 1722010031/DP/22012034580792 — वृक्षारोपण कार्य मेघनाथ घाट चंदनखेडी | Ongoing | 427106.07 | 14400 | 2023-10-08
DHAR / NISARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Avenue Plantation for Community | Plantation | 1722010031/DP/22012034584995 — मेरी माटी मेरा देश अंतर्गत वृक्षारोपण कार्य तालाब के पास चंदनखेडी | Ongoing | 54564.94 | 0 | 2023-08-09
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722010031/IF/22012035325433 — kapil dhara kup nirman gulab bhurla Chandankhedi | Ongoing | 265095.76 | 0 | 2025-04-23
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722010031/IF/22012035326155 — kapil dhara kup nirman Nahla Ditya Chandankhedi | Ongoing | 267533.14 | 0 | 2025-04-24
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722010031/IF/22012035364162 — khet talab nirman Dinesh Ramsingh chandankhedi | Ongoing | 150317.4 | 0 | 2025-04-22
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722010031/IF/22012035419742 — kapil dhara kup nirman Shriram bhadaru Chandankhedi | Approved | 0 | 0 | 2025-04-14
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010031/IF/22012035600866 — EK BAGIYA MAA KE NAAM SHYANIBAI CHHABADA | New | 0 | 0 | 2025-08-01
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010031/IF/22012035600900 — EK BAGIYA MAA KE NAAM KASTURI RAMSINGH | New | 0 | 0 | 2025-08-01
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010031/IF/22012035605099 — EK BAGIYA MAA KE NAAM KALI BAI SURESH CHANDANKHEDI | New | 0 | 0 | 2025-08-01
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010031/IF/22012035605129 — EK BAGIYA MAA KE NAAM BUDIBAI HARESINGH CHANDANKHEDI | Ongoing | 269386.03 | 0 | 2025-11-08
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010031/IF/22012035605153 — EK BAGIYA MAA KE NAAM KALI BAI SURESH CHANDANKHEDI | Approved | 0 | 0 | 2025-08-01
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010031/IF/22012035610282 — EK BAGIYA MAA KE NAAM VALI BAI SURESH CHANDANKHEDI | Ongoing | 269386.03 | 0 | 2025-11-08
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722010031/IF/22012035638352 — Construction of PMAY/State House for Individuals PMAY G REG NO MP133138750 | Ongoing | 23490 | 0 | 2025-11-18
DHAR / NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010031/IF/IAY/1168295 — Construction of IAY House -IAY REG. NO. MP3124580 | Approved | 27000 | 0 | 2017-06-05
DHAR / NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010031/IF/IAY/1180555 — Construction of IAY House -IAY REG. NO. MP1832722 | Approved | 27000 | 0 | 2017-07-29
DHAR / NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010031/IF/IAY/1196927 — Construction of IAY House -IAY REG. NO. MP4373862 | Approved | 27000 | 0 | 2017-11-23
DHAR / NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010031/IF/IAY/1196944 — Construction of IAY House -IAY REG. NO. MP5291328 | Approved | 27000 | 0 | 2017-11-23
DHAR / NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010031/IF/IAY/1196945 — Construction of IAY House -IAY REG. NO. MP5311780 | Approved | 27000 | 0 | 2017-11-23
DHAR / NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010031/IF/IAY/1196947 — Construction of IAY House -IAY REG. NO. MP5319527 | Approved | 27000 | 0 | 2017-11-23
DHAR / NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010031/IF/IAY/1196948 — Construction of IAY House -IAY REG. NO. MP5334222 | Approved | 27000 | 0 | 2017-11-23
DHAR / NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010031/IF/IAY/1196952 — Construction of IAY House -IAY REG. NO. MP5401735 | Approved | 27000 | 0 | 2017-11-23
DHAR / NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010031/IF/IAY/5579631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119672485 | Approved | 27000 | 0 | 2025-04-03
DHAR / NISARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010031/IF/IAY/5922540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115036482 | Completed | 23490 | 0 | 2026-04-02 | 2026-07-23
DHAR / NISARPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722010031/RS/22012034585046 — SBM SLP सामुदायिक शोकता गड्डा यूनिट 10 चन्दनखेड़ी | Ongoing | 64050.57 | 0 | 2021-10-14
DHAR / NISARPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035172940 — उद्यानिकी निजी खेत पौधरोपण हारला केमता चन्दनखेडी | Ongoing | 254668 | 0 | 2023-10-08
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035256291 — उद्यानिकी निजी खेत रोपण केरिया मकना चंदनखेडी | Ongoing | 169589 | 0 | 2024-10-15
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035256310 — उद्यानिकी निजी खेत रोपण दिनेश रामसिंह चंदनखेडी | Ongoing | 169589 | 0 | 2024-09-18
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035256311 — उद्यानिकी निजी खेत रोपण पदमसिंह चंदनखेडी | Ongoing | 169589 | 0 | 2024-10-01
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035256313 — उद्यानिकी निजी खेत रोपण गमुबाई लक्षमण चंदनखेडी | Ongoing | 169589 | 0 | 2024-09-19
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035256314 — उद्यानिकी निजी खेत रोपण कालूसिंह चंदर चंदनखेडी | Ongoing | 169589 | 0 | 2024-10-01
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035256316 — उद्यानिकी निजी खेत रोपण करण सरदार चंदनखेडी | Ongoing | 169589 | 0 | 2024-10-01
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035256317 — उद्यानिकी निजी खेत रोपण मेहताब नानसिंह चंदनखेडी | Ongoing | 169589 | 0 | 2024-09-18
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035256318 — उद्यानिकी निजी खेत रोपण रामसिंह नहारसिंह चंदनखेडी | Ongoing | 169589 | 0 | 2024-10-01
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035256319 — उद्यानिकी निजी खेत रोपण राकेश हीरालाल चंदनखेडी | Ongoing | 169589 | 0 | 2024-10-15
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035256320 — उद्यानिकी निजी खेत रोपण बल्लु चंदरसिंह चंदनखेडी | Ongoing | 169589 | 0 | 2024-10-15
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035258184 — उद्यानिकी निजी खेत रोपण नवसीबाई डोंगरसिंह चंदनखेडी | Ongoing | 211476 | 0 | 2024-10-15
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035258193 — उद्यानिकी निजी खेत रोपण किसन हारला चंदनखेडी | Ongoing | 254262 | 0 | 2024-09-20
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035258575 — उद्यानिकी निजी खेत रोपण काशीराम उर्फ़ छाबड़ा चंदनखेडी | Ongoing | 254262 | 0 | 2024-10-15
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035258708 — उद्यानिकी निजी खेत रोपण सुमेरसिंह नूरसिंह चंदनखेडी | Ongoing | 296805 | 0 | 2024-10-01
DHAR / NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035259949 — उद्यानिकी निजी खेत रोपण लिम्बु सुका चंदनखेडी | Ongoing | 169589 | 0 | 2024-10-15
DHAR / NISARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722010/WC/22012034604252 — RFR Antargat RMS Cum Pipe Culvert Nirman Kolyabari Nala Chandankhedi | Completed | 2487000 | 0 | 2021-02-13 | 2026-08-17
DHAR / NISARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722010/WC/22012034604254 — RFR Antargat RMS Cum Retaining Wall Nirman Ambakhodra Nala Balaji Ke Khet Pas Chandankhedi | Completed | 2493000 | 0 | 2021-02-13 | 2026-08-17