## Work List
Exported on: 2026-10-10 14:09:42
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Pipalya
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / MANAWAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1722011024/AV/22012034566637 — Boundry Wall Nirmaan Middle School Parisar Pipalya | Ongoing | 922084.65 | 0 | 2022-01-17
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Plantation in Institutions for Community | Plantation | 1722011024/DP/22012034628751 — SNG maa ki bagiya Tonki | Approved | 0 | 0 | 2024-10-02
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722011024/IF/22012035249320 — Kapildar Kup Nirman Ranjit Sikdar Gram Loni | Approved | 0 | 0 | 2024-04-10
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722011024/IF/22012035249341 — Kapildar Kup NirmanGalsingh Tersingh Gram Loni | Approved | 0 | 0 | 2024-04-10
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722011024/IF/22012035249348 — Kapildar Kup Nirman Ramsingh Nyadar Gram Pipalya | Approved | 0 | 0 | 2024-04-10
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722011024/IF/22012035406783 — JGSA khet talab Ramesh /vijay gp pipalya | New | 0 | 0 | 2025-04-15
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722011024/IF/22012035438321 — JGSA khet talab nirman bawriya/rugnath gp piplya | Physically Completed | 147621.16 | 0 | 2025-05-16 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722011024/IF/22012035438380 — JGSA khet talab nirman santilal/ gp piplya | Ongoing | 147621.16 | 0 | 2025-05-16
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722011024/IF/22012035438659 — JGSA Dugwell richarge samudayak kup piplya gp piplya | New | 0 | 0 | 2025-04-15
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722011024/IF/22012035438664 — JGSA Dugwell richarge samudayak kup piplya gp piplya | New | 0 | 0 | 2025-04-15
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722011024/IF/22012035488844 — JGSA Richarge structure Samudayak kup pipalya | New | 0 | 0 | 2025-04-15
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4551525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113708025 | Completed | 23490 | 0 | 2024-10-05 | 2026-07-17
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4565605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115749595 | Completed | 23490 | 0 | 2024-10-03 | 2026-07-17
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4590837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121497942 | Ongoing | 27000 | 0 | 2024-11-21
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4669679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113694887 | Completed | 23490 | 0 | 2024-10-05 | 2026-08-03
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4670168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113479031 | Ongoing | 27000 | 0 | 2024-10-05
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4671450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113700581 | Ongoing | 27000 | 0 | 2024-10-05
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4676610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124658844 | Completed | 23490 | 0 | 2024-10-03 | 2026-08-03
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4679128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120570799 | Completed | 23490 | 0 | 2024-10-05 | 2026-07-17
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4700216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114032986 | Completed | 23490 | 0 | 2024-12-24 | 2026-07-17
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4701211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113699028 | Ongoing | 27000 | 0 | 2024-10-05
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4702401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119620571 | Ongoing | 27000 | 0 | 2024-10-03
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4707650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124655640 | Completed | 23490 | 0 | 2024-11-07 | 2026-07-17
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4719203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134120902 | Ongoing | 27000 | 0 | 2024-11-07
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/4773493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125642877 | Completed | 23490 | 0 | 2025-01-08 | 2026-07-17
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5247522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119623691 | Completed | 23490 | 0 | 2025-05-12 | 2026-07-28
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5275537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113887515 | Completed | 23490 | 0 | 2025-04-26 | 2026-07-17
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5298799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116244465 | Completed | 23490 | 0 | 2025-06-03 | 2026-07-17
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5304760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124653429 | Completed | 23490 | 0 | 2025-05-12 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5305192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113668447 | Completed | 23490 | 0 | 2025-04-09 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5318611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124655069 | Completed | 23490 | 0 | 2025-04-26 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5319095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113665682 | Completed | 23490 | 4200 | 2025-09-22 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5322494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124655369 | Completed | 23490 | 0 | 2025-04-26 | 2026-07-28
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5324369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113691197 | Completed | 23490 | 0 | 2025-11-08 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5325251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115758228 | Completed | 23490 | 0 | 2025-04-26 | 2026-07-28
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5329520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121673775 | Completed | 23490 | 0 | 2025-04-26 | 2026-07-28
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5339830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115747103 | Completed | 23490 | 0 | 2025-04-26 | 2026-07-28
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5341441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126545726 | Completed | 23490 | 0 | 2025-04-26 | 2026-07-28
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5364945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118551942 | Completed | 23490 | 0 | 2025-04-26 | 2026-07-17
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5369708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113670344 | Physically Completed | 23490 | 4200 | 2025-11-08 | 2026-08-09
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5370664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118549245 | Ongoing | 27000 | 0 | 2025-11-08
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5373454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113680707 | Completed | 23490 | 0 | 2025-04-26 | 2026-07-28
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5497966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116243759 | Completed | 23490 | 0 | 2025-04-26 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5498943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121652703 | Completed | 23490 | 0 | 2025-04-26 | 2026-07-28
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5500323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113695517 | Ongoing | 27000 | 8400 | 2026-05-29
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5501729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113876657 | Completed | 23490 | 0 | 2025-04-26 | 2026-07-17
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5502004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113909682 | Completed | 23490 | 0 | 2025-08-05 | 2026-07-17
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5558424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126536113 | Completed | 23490 | 0 | 2025-05-12 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5561064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113708178 | Ongoing | 27000 | 0 | 2025-06-14
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5565327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117273119 | Ongoing | 27000 | 4200 | 2025-08-05
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5579265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124659060 | Completed | 23490 | 0 | 2025-06-03 | 2026-08-03
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5579446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121497862 | Ongoing | 27000 | 8400 | 2026-09-08
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5580027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134120524 | Approved | 27000 | 0 | 2025-04-25
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5609248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126536768 | Ongoing | 27000 | 0 | 2025-06-14
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5626499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119642765 | Completed | 23490 | 8400 | 2025-06-30 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5626585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126604466 | Approved | 27000 | 0 | 2025-05-08
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5627377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121670107 | Completed | 23490 | 0 | 2025-06-14 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5627387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113486356 | Ongoing | 27000 | 0 | 2025-07-22
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5627466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118518384 | Completed | 23490 | 8400 | 2025-06-14 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5630895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118553735 | Completed | 23490 | 0 | 2025-06-14 | 2026-07-17
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5632406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115777429 | Completed | 23490 | 0 | 2025-06-03 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5661525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124652087 | Completed | 23490 | 0 | 2025-06-03 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5663017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127148372 | Ongoing | 27000 | 0 | 2025-06-14
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5663399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127140709 | Completed | 23490 | 0 | 2025-06-14 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5663550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134120600 | Ongoing | 27000 | 0 | 2025-07-22
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5696049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134120382 | Completed | 23490 | 0 | 2025-07-22 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5696651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118526461 | Ongoing | 27000 | 16800 | 2025-07-22
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5696909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124653091 | Physically Completed | 27000 | 4200 | 2025-07-22 | 2026-09-13
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5697046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121648621 | Completed | 23490 | 8260 | 2025-07-22 | 2026-08-03
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5697431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118540312 | Approved | 27000 | 0 | 2025-04-17
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/5846042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148215686 | Approved | 27000 | 0 | 2025-04-10
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6123672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134120669 | Ongoing | 27000 | 13800 | 2026-05-29
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6123673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134120692 | Physically Completed | 23490 | 4800 | 2026-05-29 | 2026-08-02
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6123674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134120787 | Ongoing | 27000 | 18000 | 2026-05-29
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6127091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126489519 | Ongoing | 27000 | 13200 | 2026-05-29
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6134972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134119863 | Completed | 23490 | 4800 | 2026-05-29 | 2026-09-22
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6134973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134119954 | Ongoing | 27000 | 13800 | 2026-05-29
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6134974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134120138 | Physically Completed | 23490 | 9600 | 2026-05-29 | 2026-08-16
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6134975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134120428 | Ongoing | 27000 | 22200 | 2026-05-29
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6143383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126562609 | Ongoing | 27000 | 13200 | 2026-05-29
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6143697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127151143 | Physically Completed | 27000 | 18600 | 2026-05-29 | 2026-09-22
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6146501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115743903 | Physically Completed | 27000 | 4160 | 2026-05-06 | 2026-09-06
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6272545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134120750 | Approved | 27000 | 0 | 2026-05-22
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6294635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118522594 | Approved | 27000 | 0 | 2026-05-22
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6294637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126599787 | Approved | 27000 | 0 | 2026-05-22
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011024/IF/IAY/6342425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119637529 | Approved | 27000 | 0 | 2026-02-27
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722011024/WC/22012035213762 — निस्तार तालाब निर्माण मोहन आपसिंह के खेत के पास पिपल्या | Approved | 0 | 0 | 2024-04-10
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722011024/WC/22012035213770 — निस्तार तालाब निर्माण कैलाश मांगीलाल के खेत के पास पिपल्या | Approved | 0 | 0 | 2024-04-10
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722011024/WC/22012035216912 — bhusankalan Nirman Mohan Ke Khet ke Pass Pipalya | Approved | 0 | 0 | 2024-06-10
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722011024/WC/22012035216913 — Bhusankalan Niraman Kailash ke Khet Ke Pass Pipalya | Approved | 0 | 0 | 2024-06-10
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722011024/WC/22012035217153 — Mini Percolation Nirman Mohan Apsingh Ke Khet Ke Pass Pipalya | Approved | 0 | 0 | 2024-04-10
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722011024/WC/22012035217156 — Mini Percolation Nirman Virendra Mangilal Ke Khet Ke Pass Pipalya | Approved | 509445.1 | 0 | 2024-04-10
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722011024/WC/22012035217157 — Mini Percolation Nirman Madhav Galya Ke Khet Ke Pass Pipalya | Approved | 530467.08 | 0 | 2024-04-10
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722011024/WC/22012035290321 — JGSA richarge structure samudayak kup piplya | New | 0 | 0 | 2025-04-15
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722011024/WC/22012035290323 — JGSA richarge structure samudayak kup piplya | Approved | 0 | 0 | 2025-04-15
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722011024/WC/22012035300722 — JGSA Richarge structure Samudayak kup pipalya | Approved | 0 | 0 | 2025-04-15