## Work List
Exported on: 2026-10-18 20:55:40
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: Kuradakhal
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / MANAWAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722011029/DP/665 — वृक्षारोपण कार्य (शा बयडी पर) कुराडाखाल (4.38) | Completed | 438000 | 100550 | 2010-08-02 | 2010-08-19
DHAR / MANAWAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722011029/DP/9993628544 — वृक्षारोपण (शोभाराम के खेत के पास) कुराडाखाल (7.77) | Completed | 777000 | 234545.3 | 2015-07-11 | 2018-02-05
DHAR / MANAWAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/1029 — कपिलधारा कूप (मांगीलाल रामा) कुराडाखाल (1.42) | Completed | 142000 | 112909 | 2012-03-16 | 2016-04-24
DHAR / MANAWAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/1031 — कपिलधारा कूप (हमीर रामसिंह) कुराडाखाल (1.42) | Completed | 142000 | 39096 | 2012-03-16 | 2017-01-04
DHAR / MANAWAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1722011029/IF/22012034358724 — PLANTAION KKM (OMPRAKASH AND GROUP) KURADAKHAL | Completed | 187600 | 10320 | 2017-07-01 | 2021-02-24
DHAR / MANAWAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1722011029/IF/22012034358731 — Plantaion KKM (Gangaram AND Group) KURADAKHAL | Completed | 187600 | 10320 | 2017-07-01 | 2025-01-28
DHAR / MANAWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722011029/IF/22012034414674 — Sochalay (BABULAL BHIMAJI) KURADAKHAL | Completed | 12000 | 7480 | 2018-06-16 | 2021-02-24
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011029/IF/22012035404272 — JGSA RECHARGE STRUCTURE KAILASH DAYARAM KURADAKHAL | Completed | 25899.46 | 14355 | 2025-05-06 | 2026-05-19
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011029/IF/22012035457576 — JGSA RECHARGE STRUCTURE NANURAM MUKUT KURADAKHAL | Completed | 25899.46 | 14355 | 2025-05-06 | 2026-05-19
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011029/IF/22012035457593 — JGSA RECHARGE STRUCTURE DINESH NARAYAN KURADAKHAL | Completed | 25899.46 | 14355 | 2025-05-06 | 2026-05-19
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011029/IF/22012035457652 — JGSA RECHARGE STRUCTURE KAILASH RAJARAM KURADAKHAL | Completed | 25899.46 | 14355 | 2025-05-06 | 2026-05-19
DHAR / MANAWAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/449 — कपिलधारा (सुरेश पोमलाल) कुराडाखाल (0.50) | Completed | 0 | 62944 | 2011-01-04 | 2011-01-16
DHAR / MANAWAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/451 — कपिलधारा (तेरसिंह हरेसिंह) कुराडाखाल (0.50) | Completed | 0 | 56294 | 2010-10-10 | 2010-10-22
DHAR / MANAWAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/452 — कपिलधारा (मुकुट धन्‍ना) कुराडाखाल (0.50) | Completed | 0 | 54030 | 2010-10-17 | 2010-12-28
DHAR / MANAWAR | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/453 — कपिलधारा (विक्रम सरदार) कुराडाखाल (0.50) | Completed | 0 | 90025.5 | 2007-06-14 | 2010-09-24
DHAR / MANAWAR | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/455 — कपिलधारा (भगवान नारायण) कुराडाखाल (0.50) | Completed | 0 | 104553 | 2007-06-14 | 2010-07-18
DHAR / MANAWAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/456 — कपिलधारा (वाला मोना) कुराडाखाल (0.50) | Completed | 0 | 41638 | 2011-01-18 | 2011-03-03
DHAR / MANAWAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/457 — कपिलधारा (लक्ष्‍मण मडिया) कुराडाखाल (0.50) | Completed | 0 | 64094 | 2011-02-10 | 2011-02-22
DHAR / MANAWAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/458 — कपिलधारा (मदन बावलिया) कुराडाखाल (0.50) | Completed | 0 | 48205.75 | 2011-01-27 | 2011-03-03
DHAR / MANAWAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/459 — कपिलधारा (राजाराम भीमा) कुराडाखाल (0.50) | Completed | 0 | 51420 | 2010-11-08 | 2010-12-29
DHAR / MANAWAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/460 — कपिलधारा (बाला छितु) कुराडाखाल (0.50) | Completed | 0 | 58605 | 2010-12-01 | 2010-12-28
DHAR / MANAWAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/461 — कपिलधारा (सुरेश गोकुल) कुराडाखाल (0.50) | Completed | 0 | 57062 | 2010-09-26 | 2011-01-20
DHAR / MANAWAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/462 — कपिलधारा (रूगनाथ दशरथ) कुराडाखाल (0.50) | Completed | 0 | 30083 | 2011-01-18 | 2011-01-23
DHAR / MANAWAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/463 — कपिलधारा (नारायण हिरा) कुराडाखाल (0.50) | Completed | 0 | 77876 | 2010-10-24 | 2011-03-03
DHAR / MANAWAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/662 — कपिलधारा (नानुराम मुकुट) कुराडाखाल (1.01) | Completed | 101000 | 101150 | 2011-06-29 | 2013-06-13
DHAR / MANAWAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722011029/IF/663 — मेढबंधान (राधेश्‍याम मुकुट) कुराडाखाल (0.23) | Completed | 23000 | 36460 | 2011-06-29 | 2011-07-06
DHAR / MANAWAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722011029/IF/664 — मेढबंधान (नानुराम मुकुट) कुराडाखाल (0.18) | Completed | 18000 | 20284 | 2011-07-13 | 2011-07-26
DHAR / MANAWAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722011029/IF/665 — मेढबंधान (कल्‍याण हमीर) कुराडाखाल (0.20) | Completed | 20000 | 19520 | 2011-06-01 | 2011-06-03
DHAR / MANAWAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/666 — कपिलधारा (राधेश्‍याम मुकुट) कुराडाखाल (1.01) | Completed | 101000 | 105460 | 2011-06-29 | 2013-06-13
DHAR / MANAWAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722011029/IF/667 — कपिलधारा (अजयसिंह मंगलसिंह) कुराडाखाल (1.01) | Completed | 101000 | 78184.85 | 2011-06-29 | 2015-04-03
DHAR / MANAWAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722011029/IF/668 — मेढबंधान (अजयसिंह मंगलसिंह) कुराडाखाल (0.28) | Completed | 28000 | 23756 | 2011-06-29 | 2011-07-03
DHAR / MANAWAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/957 — कपिलधारा (देवीसिंह नहारसिंह) कुराडाखाल (1.42) | Completed | 142000 | 105412 | 2011-12-15 | 2015-06-20
DHAR / MANAWAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011029/IF/958 — कपिलारा (रूखडिया हरेसिह) कुराडाखाल (1.42) | Completed | 142000 | 144952 | 2011-12-15 | 2013-06-20
DHAR / MANAWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1722011029/IF/9993701108 — मेडबंधान ( नेमा दुधा) कुराडाखाल | Completed | 45000 | 44043 | 2016-01-23 | 2016-05-24
DHAR / MANAWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1722011029/IF/9993701113 — Medbandhan ( Bhagwan Narayan) Kuradakhal | Completed | 31000 | 29415 | 2016-01-02 | 2016-04-21
DHAR / MANAWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1722011029/IF/9993701115 — Medbandhan ( Luna Subhan) Kuradakhal | Completed | 44000 | 39909 | 2016-01-23 | 2016-05-24
DHAR / MANAWAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/1251624 — Construction of IAY House -IAY REG. NO. MP1369441 | Completed | 15480 | 14616 | 2018-06-02 | 2018-10-16
DHAR / MANAWAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/200026 — Construction of IAY House -IAY REG. NO. MP-22-011-029-001/36 | Completed | 15030 | 14028 | 2016-07-02 | 2017-12-01
DHAR / MANAWAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/200027 — Construction of IAY House -IAY REG. NO. MP-22-011-029-001/37 | Completed | 15030 | 14028 | 2016-07-02 | 2016-11-01
DHAR / MANAWAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/205731 — Construction of IAY House -IAY REG. NO. MP-22-011-029-001/67 | Completed | 15030 | 14028 | 2016-10-22 | 2017-12-01
DHAR / MANAWAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/2394463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4189735 | Completed | 17100 | 15960 | 2020-07-18 | 2021-03-03
DHAR / MANAWAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/2422644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4821468 | Completed | 17100 | 15960 | 2020-07-18 | 2020-11-04
DHAR / MANAWAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/2431858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5240767 | Completed | 17100 | 15960 | 2020-07-18 | 2021-03-03
DHAR / MANAWAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/2437845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5538701 | Completed | 17100 | 14820 | 2020-07-18 | 2021-06-18
DHAR / MANAWAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/2572778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4436984 | Completed | 17100 | 15960 | 2020-07-25 | 2021-03-03
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4038073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105342265 | Completed | 18360 | 17748 | 2022-05-25 | 2023-09-11
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4038075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105358690 | Completed | 18360 | 18275 | 2022-06-09 | 2023-09-08
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4038602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100999561 | Completed | 18360 | 18156 | 2022-05-25 | 2022-09-19
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4045759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123502775 | Completed | 18360 | 18037 | 2022-05-25 | 2023-09-08
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4046552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128740748 | Completed | 18360 | 11907 | 2022-05-25 | 2025-03-18
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4046553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128742779 | Completed | 18360 | 17663 | 2022-05-25 | 2023-09-11
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4047566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126414330 | Completed | 18360 | 17923 | 2022-05-25 | 2025-02-15
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4047594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126441171 | Completed | 18360 | 17867 | 2022-05-25 | 2023-09-11
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4050173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127219628 | Completed | 18360 | 18139 | 2022-05-25 | 2023-09-08
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4050174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127221761 | Completed | 18360 | 18156 | 2022-05-25 | 2022-09-19
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4051465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125883488 | Completed | 18360 | 17544 | 2022-05-25 | 2023-09-11
DHAR / MANAWAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/412462 — Construction of IAY House -IAY REG. NO. MP1288785 | Completed | 15030 | 14545 | 2017-02-25 | 2017-10-30
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4289299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116257061 | Completed | 18360 | 17850 | 2022-11-21 | 2023-09-11
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4292352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134436126 | Completed | 18360 | 17731 | 2022-11-21 | 2023-09-11
DHAR / MANAWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4293125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147602421 | Completed | 18360 | 17901 | 2023-08-01 | 2024-04-30
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4294246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126439550 | Completed | 18360 | 17710 | 2022-12-21 | 2023-10-21
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4294288 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126534785 | Completed | 18360 | 18156 | 2022-11-04 | 2023-08-25
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4337518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100999504 | Completed | 18360 | 16847 | 2022-11-04 | 2023-09-11
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4352084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127238369 | Completed | 18360 | 17136 | 2022-11-04 | 2023-09-11
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4370806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125813227 | Completed | 18360 | 17714 | 2022-11-04 | 2023-09-11
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/4624426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127203989 | Completed | 23490 | 22968 | 2025-04-08 | 2025-11-04
DHAR / MANAWAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/481945 — Construction of IAY House -IAY REG. NO. MP2011946 | Completed | 15030 | 14545 | 2017-02-25 | 2017-11-20
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/5247983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128744578 | Completed | 23490 | 22968 | 2025-04-08 | 2025-11-04
DHAR / MANAWAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/615028 — Construction of IAY House -IAY REG. NO. MP2045747 | Completed | 15030 | 14575 | 2017-02-25 | 2017-11-20
DHAR / MANAWAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011029/IF/IAY/826468 — Construction of IAY House -IAY REG. NO. MP3185456 | Completed | 15480 | 15136 | 2017-05-27 | 2017-12-01
DHAR / MANAWAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722011029/LD/15 — ग्रामीण क्रिडांगन ( हाईस्‍कूल) कुराडाखाल (3.97) | Completed | 397000 | 385416 | 2011-06-17 | 2011-12-28
DHAR / MANAWAR | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1722011029/PG/9425894420 — Khel maidan(govt high school kuradakhal) | Completed | 187000 | 78814.86 | 2017-03-05 | 2025-01-28
DHAR / MANAWAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/1029 — सुधार मार्ग कुराडाखाल से गुलाटी (कुराडाखाल) | Completed | 376400 | 102060 | 2006-12-18 | 2007-01-06
DHAR / MANAWAR | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/1094 — पहुंचमार्ग बावडी से शमशानघाट (कुराडाखाल) | Completed | 197600 | 0 | 2007-06-15 | 2008-06-27
DHAR / MANAWAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/1095 — पहुंचमार्ग फाटे से बोरली (कुराडाखाल) | Completed | 334000 | 0 | 2006-12-27 | 2008-01-03
DHAR / MANAWAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/2140 — पहुंचमार्ग (टिकम से राजू का खेत) कुराडाखाल | Completed | 476000 | 276300 | 2008-04-02 | 2008-05-12
DHAR / MANAWAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722011029/RC/22012034186548 — पंचपरमेश्‍वर खरंजा (आदिवासी बस्‍ती ) कुराडाखाल | Completed | 193000 | 7592 | 2013-09-28 | 2018-06-10
DHAR / MANAWAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722011029/RC/22012034213548 — खेतसडक (प्रकाश के खेत से गटिया के खेत तक) कुराडाखा | Completed | 1174000 | 867363.72 | 2014-03-15 | 2016-12-14
DHAR / MANAWAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722011029/RC/22012034213549 — खेतसडक( कुराडाखाल फाटा से गोपाल के खेत तक) कुराडाख | Completed | 1137000 | 860693.37 | 2014-03-09 | 2016-12-14
DHAR / MANAWAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/2210 — पहुंचमार्ग (रामेश्‍वर खेत से राधेश्‍याम खेत तक) कुराडाखाल (4.70) | Completed | 454000 | 381259 | 2009-04-01 | 2009-08-11
DHAR / MANAWAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/2220 — पहुंचमार्ग (नर्सरी से देवलाफाटा) कुराडाखाल (4.63) | Completed | 447000 | 200497 | 2009-08-16 | 2009-08-28
DHAR / MANAWAR | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/2241 — पहुंचमार्ग (गोपाल के खेत से बाबू का खेत) कुराडाखाल (4.10) | Completed | 0 | 168780 | 2007-08-02 | 2007-09-07
DHAR / MANAWAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/2264 — पहुंचमार्ग (बालाजी के खेत से हाईस्‍कूल तक) कुराडाखाल (4.70) | Completed | 470000 | 398814 | 2009-12-15 | 2010-02-06
DHAR / MANAWAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/2285 — पहुंचमार्ग (गोपाल के खेत से मोहन के खेत तक) कुराडाखाल (4.88) | Completed | 488000 | 440300 | 2010-05-08 | 2010-06-21
DHAR / MANAWAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/2312 — पहुंचमार्ग (प्रकाश के खेत से टीकम का खेत ) कुराडाखाल (4.34) | Completed | 434000 | 426000 | 2010-08-18 | 2010-10-08
DHAR / MANAWAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/2346 — पहुंचमार्ग (तेरसिंह के खेत से नारायण के खेत तक) कुराडाखाल (4.70) | Completed | 470000 | 404662 | 2011-03-02 | 2011-03-28
DHAR / MANAWAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/2357 — पहुंचमार्ग (पंचायतभवन से लालजी के खेत तक) कुराडाखाल 4.70 | Completed | 470000 | 471148 | 2011-04-27 | 2011-05-24
DHAR / MANAWAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/2415 — पहुंचमार्ग (शमशानघाट से भगवान के खेत तक) कुराडाखाल (4.70) | Completed | 470000 | 488628 | 2011-09-10 | 2011-12-28
DHAR / MANAWAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722011029/RC/2416 — पहुंचमार्ग (नर्सरी से कमल के खेत तक) कुराडाखाल (4.70) | Completed | 470000 | 492208 | 2011-09-08 | 2011-10-23
DHAR / MANAWAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722011029/RC/2504 — पंचपरमेश्‍वर (धर्मशाला से खोदरी तक) कुराडाखाल (1.6 | Completed | 168000 | 154460 | 2012-10-05 | 2013-10-10
DHAR / MANAWAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722011029/RS/22012034239525 — maryad sochalay nirman ( rakesh chagan magan sek | Completed | 54000 | 26955.85 | 2014-06-21 | 2025-01-28
DHAR / MANAWAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722011029/RS/22012034239527 — मर्यादा शोचालय ( गोपाल वाला लिला बाई समुह) कुराड | Completed | 54000 | 25933 | 2014-06-21 | 2025-01-28
DHAR / MANAWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722011029/RS/22012034416064 — Sochalay (बद्रीलाल & रूखडु) Kuradakhal | Completed | 24000 | 13916 | 2018-08-04 | 2025-01-28
DHAR / MANAWAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722011029/WC/1030 — भूसकंन पौण्‍ड कुराडाखाल | Completed | 300000 | 0 | 2006-05-13 | 2008-10-22
DHAR / MANAWAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Underground Dyke / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1722011029/WC/2197 — स्‍टापडेम (भाग 1) कुराडाखाल (4.98) RES | Completed | 481000 | 284268.1 | 2009-01-17 | 2013-03-22
DHAR / MANAWAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722011029/WC/2198 — स्‍टापडेम (भाग 2) कुराडाखाल (4.98) RES | Completed | 481000 | 406932.8 | 2009-01-31 | 2013-02-28
DHAR / MANAWAR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722011029/WC/22012034319344 — bhu sunkan pond near plantation | Completed | 179000 | 75484 | 2017-02-11 | 2018-06-10
DHAR / MANAWAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722011029/WC/22012034394739 — bhu sunken pond khatod ke khet ke pas | Completed | 218000 | 205200 | 2018-07-07 | 2021-06-18
DHAR / MANAWAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1722011029/WC/22012034501323 — Cantour Trench shaskiya bayadi par katod ke khet ke pass wali Khuradakhal | Completed | 353592.13 | 331130 | 2020-04-21 | 2021-06-18
DHAR / MANAWAR | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722011029/WC/2267 — निर्मलनीर (नयापुरा) कुराडाखाल | Completed | 250000 | 196234 | 2009-04-23 | 2010-07-01
DHAR / MANAWAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722011029/WC/2380 — सार्वजनिक कूप (बयडापार) कुराडाखाल 2.71 | Completed | 271000 | 286958.2 | 2011-04-01 | 2012-03-29
DHAR / MANAWAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722011029/WC/2440 — सार्वजनिक कूप (भील मोहल्‍ला) कुराडाखाल (3.90) | Completed | 390000 | 255616 | 2011-11-19 | 2017-02-16
DHAR / MANAWAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722011029/WC/2441 — सार्वजनिक कूप निर्माण (शांतिधाम) कुराडाखाल (3.90) | Completed | 390000 | 125520 | 2011-12-14 | 2017-02-16
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722011029/WC/9993626757 — भूसंकन पौण्‍ड (रोजाबयडा) कुराडाखाल | Completed | 221000 | 209744 | 2014-01-18 | 2014-05-22
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722011029/WC/9993626758 — भूसंकन पौण्‍ड (शास0 बयडी पर) कुराडाखाल (2.28) | Completed | 228000 | 208926 | 2013-06-01 | 2013-07-18
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722011029/WC/9993631938 — भु संकलन पोंण्‍ड (शासकीय बयडा पर ) कुराडाखाल | Completed | 228000 | 213014 | 2013-05-25 | 2013-07-18
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722011029/WC/9993631939 — भु संकलन पोंण्‍ड (शासकीय बयडा पर भाग 1) कुराडाखाल | Completed | 228000 | 218434 | 2013-05-25 | 2013-07-18
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722011029/WC/9993635400 — भूसंकन पौण्‍ड (सुखलाल के खेत के पास) कुराडाखाल ( | Completed | 230000 | 211948 | 2013-08-04 | 2013-09-19
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722011029/WC/9993635401 — भूसंकन पौण्‍ड (तालाब के पास) कुराडाखाल (2.30) | Completed | 230000 | 220416 | 2013-08-04 | 2013-09-19
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722011029/WC/9993635402 — सीपीटी (वक्षारोपण के पास ) कुराडाखाल (2.36) | Completed | 236000 | 191946 | 2013-09-28 | 2014-01-16
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722011029/WC/9993635403 — कंटूरट्रेंच (शा बयडे पर 500 नग) कुराडाखाल (0.97) | Completed | 97000 | 18980 | 2013-09-28 | 2013-10-03
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722011029/WC/9993635404 — कंटूरट्रेंच (शा बयडे पर 1000 नग) कुराडाखाल (1.94) | Completed | 194000 | 138802 | 2013-09-28 | 2014-01-16
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722011029/WC/9993636195 — भूसंकन पौण्‍ड (बिलमण के खेत के पास शा0 बयडे पर) कु | Completed | 221000 | 219686 | 2013-09-28 | 2014-01-16
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722011029/WC/9993639061 — भूसंकन पौण्‍ड (मोतीलाल के खेत के पास) कुराडाखाल ( | Completed | 221000 | 213974 | 2014-03-08 | 2014-05-29
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722011029/WC/9993639062 — भूसंकन पौण्‍ड (प्रताप के खेत के पास) कुराडाखाल (2. | Completed | 221000 | 212104 | 2014-03-08 | 2014-05-22
DHAR / MANAWAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722011029/WC/9993639063 — भूसंकन पौण्‍ड (गुलाब के खेत के पास) कुराडाखाल (2.2 | Completed | 221000 | 210990 | 2014-03-08 | 2014-05-16
DHAR / MANAWAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722011029/WC/9993664949 — Bhusunken pond ( Saskiy Bayde per Bhag-1) Kuradakhal | Completed | 250000 | 233412 | 2016-01-16 | 2016-04-11
DHAR / MANAWAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722011/IF/22012034836841 — Horticulture plantation bhana-rama kuradakhal | Completed | 371358 | 160233 | 2021-10-25 | 2024-01-20
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722011/IF/22012035016285 — horticulture plantation chhogalal -tikam gram kuradakhal | Completed | 298175 | 210292 | 2022-10-18 | 2024-08-12
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722011/IF/22012035016297 — horticulture plantation prakash -luna gram kuradakhal | Completed | 261201 | 112212 | 2022-10-18 | 2024-08-29
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722011/IF/22012035016317 — horticulture plantation ganesh -shankar gram kuradakhal | Completed | 186061 | 106428 | 2022-10-18 | 2024-09-30
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722011/IF/22012035016323 — horticulture plantation rajendra bhanaji gram kuradakhal | Completed | 372719 | 36016 | 2022-10-18 | 2024-10-05
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722011/IF/22012035016472 — horticulture plantation asha bai -onkar gram kuradakhal | Completed | 372719 | 36430 | 2022-11-07 | 2024-10-19
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722011/IF/22012035028022 — Horticulture Plantation natthu-bala gram kuradakhal | Completed | 186061 | 129264 | 2022-10-18 | 2024-10-14