## Work List
Exported on: 2026-10-15 14:33:07
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Limbi
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / MANAWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1722011040/DP/22012034563863 — व्रक्षारोपण निर्माण दुदिया बयडी लिम्‍बी | Ongoing | 718191.92 | 0 | 2022-09-06
DHAR / MANAWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1722011040/DP/22012034600361 — Block plantation Dudhiya baidi ahemadpur,limbi | Ongoing | 490153.62 | 22500 | 2023-10-09
DHAR / MANAWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1722011040/DP/22012034613425 — gully plug nirman parkolation ke pass limbi | New | 0 | 0 | 2024-01-27
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1722011040/IF/22012035362980 — JGSA DUGWELL RECHARGE KALU BISAN GP LIMBI | New | 0 | 0 | 2025-04-15
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722011040/IF/22012035363838 — JGSA DUGWELL RECHARGE SHOBHARAM NARAN GP LIMBI | Ongoing | 25399.46 | 0 | 2025-05-21
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722011040/IF/22012035398333 — JGSA KHET TALB NIRMAN SOHAN GANPAT GP LIMBI | Ongoing | 147621.16 | 0 | 2025-05-01
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722011040/IF/22012035478235 — JGSA KHET TALAB NIRMAN TARUBAI LALSINGH GP LIMBI | Approved | 0 | 0 | 2025-04-14
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722011040/IF/22012035478422 — JGSA KHET TALAB NIRMAN MOTILAL GOKUL GP LIMBI | Approved | 0 | 0 | 2025-04-14
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722011040/IF/22012035478467 — JGSA KHET TALAB NIRMAN MOHAN DHANNA GP LIMBI | Approved | 0 | 0 | 2025-04-14
DHAR / MANAWAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011040/IF/IAY/2540336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4953686 | Ongoing | 27000 | 0 | 2020-06-24
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011040/IF/IAY/4007986 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122212598 | Approved | 27000 | 0 | 2022-05-09
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011040/IF/IAY/4735551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100581194 | Ongoing | 27000 | 17400 | 2026-08-04
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011040/IF/IAY/5246906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121661947 | Ongoing | 27000 | 0 | 2025-04-21
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011040/IF/IAY/5272487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105058411 | Approved | 27000 | 0 | 2025-02-23
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011040/IF/IAY/5272857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115140808 | Ongoing | 27000 | 900 | 2026-09-30
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011040/IF/IAY/5303135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114956484 | Physically Completed | 27000 | 12000 | 2025-05-28 | 2026-10-09
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011040/IF/IAY/5416919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114097212 | Physically Completed | 27000 | 7800 | 2025-05-28 | 2026-10-09
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011040/IF/IAY/5694584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122004940 | Approved | 27000 | 0 | 2025-02-23
DHAR / MANAWAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1722011040/RC/22012034538074 — Construction of Khet Sadak from Main Road Nahar Singh ke Khet se Rajaram Bhavsingh ke Khet Tak,LIMBI | Ongoing | 1499222.4 | 0 | 2020-09-29
DHAR / MANAWAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722011040/RC/22012034845868 — CONSTRUCTION OF CC ROAD DEVISINGH KE GHAR SE LOKESH KE GHAR TAK GP LIMBI | Ongoing | 210000 | 0 | 2025-08-12
DHAR / MANAWAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722011040/WC/22012034640181 — (CTRA Contour Trench Work at Babblu-Shobharam Ke Khet Ke Pass) G.P.Limbi | Ongoing | 133080.13 | 0 | 2021-07-01
DHAR / MANAWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722011040/WC/22012035015233 — CCT Nirman Karya Dudiya Bayda pr Limbi GP LIMBI | Ongoing | 304000.18 | 0 | 2022-12-11
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722011040/WC/22012035236970 — CONTOUR TRENCH NIRMAN PAPPU BALLU KE KHET PAS LIMBI | Ongoing | 464233.84 | 0 | 2025-01-01
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722011040/WC/22012035236994 — CONTOUR TRENCH NIRMAN BRAHMANAD MUKATI KE KHET PAS LIMBI | Ongoing | 425378.68 | 0 | 2025-01-02