## Work List
Exported on: 2026-09-07 11:43:26
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Koswada
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / MANAWAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1722011044/AV/22012034565032 — BAUNDARY WALL MIDDLE SCHOOL PALASI | Ongoing | 324481.51 | 0 | 2021-04-15
DHAR / MANAWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1722011044/DP/22012034613433 — Plantation Work Middel School Palasi Koshawada | New | 0 | 0 | 2024-01-25
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722011044/IF/22012035398141 — JGAS KHET TALAB RADHESHYAM MADIYA KOSWADA | Ongoing | 147621.16 | 0 | 2025-05-03
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011044/IF/22012035480330 — JGSA R RICHARG PIT RAMESH GOPAL KOSWADA | Approved | 0 | 0 | 2025-05-05
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011044/IF/22012035480354 — JGSA RICHARG PIT RADHESHYAM LALSINGH KOSWADA | New | 0 | 0 | 2025-05-05
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722011044/IF/22012035483308 — JGSA KHET TALAB PALCHAND HARESINGH KOSWADA | Approved | 0 | 0 | 2025-05-06
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011044/IF/22012035591758 — EK BAGIYA MAA KE NAME SARASVATI ALAWA MP 22011044001/84A PALASI | New | 0 | 0 | 2025-08-01
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011044/IF/22012035591804 — EK BAGIYA MAA KE NAAM MP-22-011-044-001/32 DHANU BAI PALASI KOSWADA | Ongoing | 266577.25 | 0 | 2025-09-14
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011044/IF/22012035591833 — EK BAGIYA MAA KE NAme BASANTI BAI MP 22011044001/98 PALASI | New | 0 | 0 | 2025-08-01
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011044/IF/22012035591936 — EK BAGIYA MAA KE NAAM SARASWATI ALAWA MP22011044001/84A GP KOSWADA | New | 0 | 0 | 2025-08-01
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011044/IF/22012035599672 — EK BAGIYA MAA KE NAME KALA-Funda Bai, Anil, Resham Alawa, Loke-MP22011044001/30-GP-KOSWADA | Ongoing | 266577.25 | 0 | 2025-09-08
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011044/IF/22012035599683 — EK BAGIYA MAA KE NAME KALA-Ranjit, Basantibai, Arjun Mandloi-MP22011044001/98-GP-KOSWADA | Approved | 266577.25 | 0 | 2025-08-01
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011044/IF/22012035599700 — EK BAGIYA MAA KE NAME KALA-Bhim Singh, Kamla Bai, Dongar Singh-MP22011044001/84-A-GP-KOSWADA | Ongoing | 266577.25 | 0 | 2025-09-08
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011044/IF/22012035599750 — EK BAGIYA MAA KE NAME KALA-Devkor, Mona, Raju, Pinki, Rani-MP22011044001/40-GP-KOSWADA | Ongoing | 266577.25 | 0 | 2025-09-08
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011044/IF/22012035599765 — EK BAGIYA MAA KE NAME KALA-Fatusingh, Sajan, Nanuram, Priyanka-MP22011044001/50-GP-KOSWADA | Ongoing | 266577.25 | 0 | 2025-09-14
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011044/IF/22012035603658 — EK BAGIYA MAA KE NAAM MEERA BAI MP-22-011-044-001/21 PALASI GP- KOSWADA | Ongoing | 266577.25 | 0 | 2025-09-14
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011044/IF/IAY/5625670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128760742 | Ongoing | 27000 | 4200 | 2026-05-15
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011044/IF/IAY/5665305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127683188 | Physically Completed | 27000 | 5400 | 2025-09-26 | 2026-09-06
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011044/IF/IAY/5665900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127659117 | Ongoing | 27000 | 6300 | 2026-02-24
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011044/IF/IAY/5666000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126330982 | Physically Completed | 27000 | 2100 | 2025-09-11 | 2026-09-06
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011044/IF/IAY/5760474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126969769 | Completed | 23490 | 0 | 2026-01-29 | 2026-07-28
DHAR / MANAWAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722011044/WC/22012034603079 — Puliya Cum Ringbund (Pratap Narayan Ke khet ke Pass Palasi) Koswada | Ongoing | 1495000.45 | 0 | 2021-01-09
DHAR / MANAWAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722011044/WC/22012034603080 — Puliya Cum Ringbund (Halaw ke Pass Nale Per Palasi) Koswada | Ongoing | 1490000.39 | 0 | 2021-01-21
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722011044/WC/22012034634308 — CTRA FARMPOND PUNIYA KE KHET KE PASS PALASI | Ongoing | 110516.06 | 0 | 2025-06-12
DHAR / MANAWAR | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1722011044/WC/22012034638504 — CTRA GABION PUNIYA KE KHET KE PASS NALE ME PALASI | Ongoing | 41183.29 | 0 | 2021-04-15
DHAR / MANAWAR | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1722011044/WC/22012034638508 — CTRA GABION JAGDISH KE KHET KE PASS NALE ME PALASI | Ongoing | 39051.23 | 0 | 2021-04-15
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722011044/WC/22012035308591 — Bhusankalan ponnd Juwar singh kai khit kai pass gp koswada plashi mai | Approved | 0 | 0 | 2025-05-17
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722011044/WC/22012035308595 — Bhusankalan ponnd samsaan ghat kai pass gp koswada plashi mai | Approved | 0 | 0 | 2025-05-17