## Work List
Exported on: 2026-09-07 20:38:31
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Dongargaon
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / MANAWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1722011045/DP/22012034580489 — वृक्षारोपन कार्य माध्यमिक शाला के पास डोंगरगाँव | Ongoing | 293577.71 | 5100 | 2023-08-01
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1722011045/DP/22012034620798 — miyawaki plantation,DONGARGANV | Ongoing | 1325690.39 | 300 | 2024-07-13
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722011045/DP/22012034628495 — ब्लॉक प्लान्टेशन कार्य पिपलटोका ग्राम पंचायत डोंगरगांव | Ongoing | 839485.61 | 0 | 2024-11-06
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1722011045/DP/22012034628688 — Block plantation devziri k pas gram pipaltoka | Approved | 0 | 0 | 2024-08-17
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722011045/DP/22012034628689 — वृक्षारोपण कार्य शांतिधाम के पास ग्राम पिपलटोका | Approved | 0 | 0 | 2024-08-17
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722011045/IF/22012035468038 — JGSA khettalab Tulsiram hiralal dongarganv | Approved | 147621.16 | 0 | 2025-04-15
DHAR / MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011045/IF/22012035484552 — JGSA Dugwell Recharge linkan vadav dongarganv | Physically Completed | 25899.46 | 0 | 2025-05-10 | 2026-08-17
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/4036755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105977657 | Ongoing | 27000 | 0 | 2022-06-02
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/4038259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105727896 | Ongoing | 27000 | 0 | 2022-06-07
DHAR / MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/4241629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105728127 | Physically Completed | 23490 | 2400 | 2022-07-17 | 2026-08-18
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/4657666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147920350 | Approved | 27000 | 0 | 2024-09-16
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/4719937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132652526 | Physically Completed | 27000 | 0 | 2025-03-06 | 2026-09-06
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5246832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105916033 | Physically Completed | 27000 | 0 | 2025-08-01 | 2026-09-02
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5251872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105060719 | Ongoing | 27000 | 11700 | 2025-04-16
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5252497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105064386 | Ongoing | 27000 | 4800 | 2025-04-16
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5253256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105921124 | Physically Completed | 23490 | 0 | 2025-04-16 | 2026-07-28
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5255224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105915376 | Physically Completed | 23490 | 0 | 2025-04-16 | 2026-08-04
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5270391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105982930 | Ongoing | 27000 | 6900 | 2025-07-26
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5276098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105987706 | Ongoing | 27000 | 6900 | 2025-07-25
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5293332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105480003 | Ongoing | 27000 | 2100 | 2025-05-15
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5296890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105914981 | Physically Completed | 27000 | 3600 | 2026-02-11 | 2026-09-02
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5312206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105916197 | Ongoing | 27000 | 0 | 2025-08-22
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5318670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106010515 | Ongoing | 27000 | 6900 | 2025-08-22
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5319714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106010288 | Ongoing | 27000 | 11700 | 2025-08-23
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5339911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105189493 | Completed | 23490 | 0 | 2025-05-19 | 2026-07-28
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5357270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132491797 | Physically Completed | 27000 | 0 | 2025-07-25 | 2026-09-02
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5383040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105977591 | Physically Completed | 27000 | 900 | 2025-06-05 | 2026-09-02
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5418486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105060893 | Ongoing | 27000 | 0 | 2025-07-26
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5532635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105481558 | Ongoing | 27000 | 6900 | 2025-08-22
DHAR / MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5696523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105061096 | Ongoing | 27000 | 4800 | 2025-08-01
DHAR / MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5867689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105978469 | Approved | 27000 | 0 | 2025-03-12
DHAR / MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011045/IF/IAY/5887089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118315909 | Ongoing | 27000 | 0 | 2026-08-31
DHAR / MANAWAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722011045/RS/22012034598100 — SBM ISP व्यक्तिगत सोक पिट निर्माण कार्य संख्या 5 ग्राम पिपलटोका ग्राम पंचायत डोंगरगांव | Ongoing | 55849.09 | 0 | 2021-11-18
DHAR / MANAWAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722011045/RS/22012034598106 — SBM ISP व्यक्तिगत सोक पिट निर्माण कार्यइंदिराकॉलोनी संख्या 5 ग्राम पिपलटोका ग्राम पंचायत डोंगरगांव | Ongoing | 53399.09 | 0 | 2021-11-18
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722011045/WC/22012035257494 — Bhusankan pond nirman karya suresh k khet pas gram pipaltoka | Approved | 0 | 0 | 2025-03-08
DHAR / MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722011/DP/22012034628457 — Block plantation shantidam ke pas ke pas pipltoka dongarganv | Approved | 839485.61 | 0 | 2024-10-02