## Work List
Exported on: 2026-10-22 05:14:16
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Karondiya
Status: Ongoing
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722012006/IF/22012035327061 — करोदियाखुर्द कपिलधारा कुप निर्माण कार्य खुमान-दलसिंह | Ongoing | 215000.23 | 0 | 2025-05-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722012006/IF/22012035380080 — करोदियाखुद कपिल धारा कुप निर्माण कार्य फाटुसिह लालसिंह | Ongoing | 215000.23 | 0 | 2025-05-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722012006/IF/22012035468277 — JGSA Rama sekadiya ka khet talab gp karondiya khurd | Ongoing | 55865.38 | 0 | 2025-05-07
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722012006/IF/22012035470115 — जल गंगा सवर्धन योजना अन्तर्गत करोदियाखुर्द खेत तालाब गंगाराम-रूखड़िया | Ongoing | 55865.38 | 0 | 2025-05-26
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722012006/IF/22012035470143 — जल गंगा सवर्धन योजना अन्तर्गत करोदियाखुर्द खेत तालाब रामसिंह-सुभान | Ongoing | 55865.38 | 0 | 2025-05-27
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722012006/IF/22012035527198 — करोदियाखुर्द कपीलधारा कुप निर्माण कार्य गलसिंह-भगवान | Ongoing | 210000.36 | 1800 | 2026-05-05
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722012006/IF/22012035527201 — करोदियाखुर्द कपीलधारा कुप निर्माण कार्य अम्‍बाराम-नराण | Ongoing | 210000.36 | 7200 | 2025-06-06
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012006/IF/IAY/4571627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117364392 | Ongoing | 27000 | 0 | 2025-11-19
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012006/IF/IAY/5252239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115216722 | Ongoing | 27000 | 0 | 2025-11-19
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012006/IF/IAY/5259001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116219829 | Ongoing | 27000 | 0 | 2025-11-19
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012006/IF/IAY/5295869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117278522 | Ongoing | 27000 | 0 | 2025-11-19
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012006/IF/IAY/5315314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115214478 | Ongoing | 27000 | 0 | 2025-09-24
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012006/IF/IAY/5331708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115212471 | Ongoing | 27000 | 0 | 2025-11-19
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012006/IF/IAY/5337392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114996968 | Ongoing | 27000 | 0 | 2025-08-06
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012006/IF/IAY/5615813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114996225 | Ongoing | 27000 | 12600 | 2025-11-19
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012006/IF/IAY/5695523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117149655 | Ongoing | 27000 | 0 | 2025-07-17
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012006/IF/IAY/5697077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118360380 | Ongoing | 27000 | 0 | 2025-11-19
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012006/IF/IAY/5753148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114811434 | Ongoing | 27000 | 17700 | 2025-11-19
DHAR / UMARBAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722012006/WC/22012035132929 — Nistar Tank Neem Wala Nalla Karondiya Khurd | Ongoing | 1496726.51 | 0 | 2023-10-05