## Work List
Exported on: 2026-09-13 09:20:39
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Kothada
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / UMARBAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722012049/IF/22012035464048 — JGSA कुप रिचार्ज पिट सीताराम फक्कन | Approved | 25899.46 | 0 | 2025-04-14
DHAR / UMARBAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722012049/IF/22012035464119 — JGSA कुप रिचार्ज पिट जगदीश मोतीलाल | Approved | 25899.46 | 0 | 2025-04-14
DHAR / UMARBAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722012049/IF/22012035464121 — JGSA कुप रिचार्ज पिट बावलिया नरसिंग | Approved | 25899.46 | 0 | 2025-04-14
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722012049/IF/22012035472311 — JGSA खेत तालाब धनुबाई पन्नालाल | Approved | 55865.38 | 0 | 2025-04-14
DHAR / UMARBAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722012049/IF/22012035472860 — JGSA कुप रिचार्ज पिट हेमा अमरिया | Approved | 25899.46 | 0 | 2025-04-14
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722012049/IF/22012035600502 — EK BAGIYA MAA KE NAME-Kalabai Chouhan, Jagdish Chouhan, Santosh Chouhan, Minakshi Chouhan, Urvashi C | Ongoing | 266577.25 | 0 | 2026-02-12
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722012049/IF/22012035600504 — EK BAGIYA MAA KE NAME-Kailash Jat, Raju Bai, Shyam Jat, Ruchi Jat-MP22012049002/310-A-KOTHADA | Ongoing | 266577.25 | 0 | 2026-02-12
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722012049/IF/22012035600508 — EK BAGIYA MAA KE NAME-Nirmalabai Dhangar-MP22012049002/221-KOTHADA | Ongoing | 266577.25 | 0 | 2025-09-25
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722012049/IF/22012035600510 — EK BAGIYA MAA KE NAME-Ramesh, Indu Bai, Nidhi Jat, Deepesh Jat, Deepika Jat, Bhilibai-MP22012049002/ | Ongoing | 266577.25 | 0 | 2026-02-12
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722012049/IF/22012035600512 — EK BAGIYA MAA KE NAME-Vitthal Jat, Savitribai, Sourabh Jat-MP22012049002/262-KOTHADA | Ongoing | 266577.25 | 0 | 2025-09-25
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/2398865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4340798 | Ongoing | 27000 | 0 | 2025-11-27
DHAR / UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/4544840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106137902 | Physically Completed | 23490 | 0 | 2024-11-15 | 2026-07-22
DHAR / UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/4547033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106521051 | Completed | 23490 | 0 | 2024-11-08 | 2026-07-28
DHAR / UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/4557498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114144224 | Ongoing | 27000 | 0 | 2024-11-15
DHAR / UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/4634530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129268144 | Completed | 23490 | 0 | 2024-12-04 | 2026-08-18
DHAR / UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/4670589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113984405 | Ongoing | 27000 | 0 | 2024-12-03
DHAR / UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/4714870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128275386 | Completed | 23490 | 0 | 2024-11-08 | 2026-08-18
DHAR / UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/4765888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115800922 | Ongoing | 27000 | 0 | 2025-01-09
DHAR / UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/4783001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126163991 | Ongoing | 27000 | 0 | 2024-11-15
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/5301613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071989 | Ongoing | 27000 | 0 | 2025-04-16
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/5659636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148901867 | Ongoing | 27000 | 2100 | 2025-08-28
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/5693486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118822603 | Ongoing | 27000 | 2100 | 2025-08-12
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/5695717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128748764 | Ongoing | 27000 | 2100 | 2025-08-28
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6117715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376952 | Ongoing | 27000 | 0 | 2026-09-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6117720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126353965 | Ongoing | 27000 | 2100 | 2026-07-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6117721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126362930 | Approved | 27000 | 0 | 2026-03-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6117724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126383635 | Approved | 27000 | 0 | 2026-03-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6117981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128292788 | Approved | 27000 | 0 | 2026-03-12
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6117982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128293656 | Ongoing | 27000 | 2100 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6118093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126165309 | Ongoing | 27000 | 2100 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6118118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126349962 | Ongoing | 27000 | 2100 | 2026-07-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6118224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128743009 | Approved | 27000 | 0 | 2026-03-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6118225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128743621 | Ongoing | 27000 | 2100 | 2026-07-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6118297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115703265 | Approved | 27000 | 0 | 2026-03-10
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6118628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128426266 | Ongoing | 27000 | 2100 | 2026-07-16
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6118629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128427412 | Ongoing | 27000 | 2100 | 2026-07-24
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6118726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128736991 | Approved | 27000 | 0 | 2026-03-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6118727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128738844 | Ongoing | 27000 | 2100 | 2026-07-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6118728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128740950 | Approved | 27000 | 0 | 2026-03-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6118878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106138092 | Ongoing | 27000 | 2100 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6119338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115112401 | Ongoing | 27000 | 2100 | 2026-07-24
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6119408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148903853 | Approved | 27000 | 0 | 2026-03-10
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6119716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128036289 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6119757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126169201 | Approved | 27000 | 0 | 2026-03-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6119768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113464800 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6120120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128747079 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6120344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118823049 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6120345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118823270 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6120458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118822286 | Ongoing | 27000 | 0 | 2026-09-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6120488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129261306 | Ongoing | 27000 | 0 | 2026-07-24
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6120489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129264707 | Ongoing | 27000 | 2100 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6120490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129267301 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6120503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106520635 | Approved | 27000 | 0 | 2026-03-12
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6120804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113978930 | Ongoing | 27000 | 0 | 2026-09-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6120838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113644318 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6120861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128032929 | Approved | 27000 | 0 | 2026-03-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6120953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128428749 | Approved | 27000 | 0 | 2026-03-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6121089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129261787 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6121241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125128349 | Ongoing | 27000 | 0 | 2026-09-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6121278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129267468 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6121280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126116878 | Ongoing | 27000 | 0 | 2026-07-24
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6121281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114111670 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6121458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129268286 | Approved | 27000 | 0 | 2026-03-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6121459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129273463 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6121535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128437569 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6121547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118824224 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6121682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128742117 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6121972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113707580 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6121973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113707860 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6122069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128280845 | Ongoing | 27000 | 0 | 2026-07-24
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6122168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114141157 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6122226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126178095 | Approved | 27000 | 0 | 2026-03-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6122250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148573970 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6122260 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128274624 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6122309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113691158 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6123140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115199465 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6124039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126185594 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6129200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128748166 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6129469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146814274 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6129562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129264985 | Ongoing | 27000 | 0 | 2026-07-24
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6133729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118821957 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6133731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118822939 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6133733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118823507 | Ongoing | 27000 | 0 | 2026-07-16
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6135036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128280221 | Approved | 27000 | 0 | 2026-03-21
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6138699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118823883 | Ongoing | 27000 | 0 | 2026-09-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6139547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113648610 | Approved | 27000 | 0 | 2026-03-14
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6140724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129271204 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6140778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126179206 | Approved | 27000 | 0 | 2026-03-21
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6140991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114130679 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6143480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128742622 | Approved | 27000 | 0 | 2026-03-21
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6144191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126161418 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6144452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149008953 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6154612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113464726 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6157288 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116964051 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6157816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106139152 | Ongoing | 27000 | 0 | 2026-09-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6164069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128744885 | Approved | 27000 | 0 | 2026-03-14
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6166582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128740049 | Ongoing | 27000 | 0 | 2026-07-24
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6169601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128746152 | Approved | 27000 | 0 | 2026-03-14
DHAR / UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6169844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113473298 | Ongoing | 27000 | 0 | 2026-07-08
DHAR / UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722012049/IF/IAY/6175569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129267621 | Approved | 27000 | 0 | 2026-03-14
DHAR / UMARBAN | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722012049/RC/22012034570593 — SUDUR SADAK NIRMAN KARYA DEEPU KE KHE SE SHEETARAM KE KHET TAK | Physically Completed | 1499470.82 | 0 | 2021-05-13 | 2026-07-22
DHAR / UMARBAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722012049/WC/22012035102577 — BHILAT BABA MANDIRE KE PASS BOULDER WALL AND CPT G.P. KOTHADA | Ongoing | 231569.12 | 0 | 2023-09-14
DHAR / UMARBAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722012049/WC/22012035111068 — g.p. kothada me water pond nirman kary | Ongoing | 286191.38 | 0 | 2023-09-29
DHAR / UMARBAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722012049/WC/22012035248700 — Gram panchayat kothada mebhilat mandir water pond nirman | Approved | 0 | 0 | 2025-01-01
DHAR / UMARBAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722012049/WC/22012035248701 — Gram panchayat kothada water pond nirman | Ongoing | 556002.37 | 0 | 2025-07-29
DHAR / UMARBAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722012049/WC/22012035319101 — कोठडा सकर्ण पौण्ड निर्माण कार्य रामदेव के खेत के पास | Ongoing | 311864.93 | 0 | 2025-08-12