## Work List
Exported on: 2026-10-17 12:49:16
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Dongri Dasoda
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / DHARAMPURI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1722013034/DP/22012034530406 — CTRA G.P. DONGRI DASODA ME VRAKSHAROPAN KARYA MIDDILE SCHOOL KE PASS PART-4 | Physically Completed | 685575.78 | 0 | 2021-06-23 | 2026-10-06
DHAR / DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov building Block Plantation-Farm Forestry-Comm / Plantation in Institutions for Community | Plantation | 1722013034/DP/22012034625222 — GP Dongri Dasoda Khirchayli Baydi Hanuman Mandir Parisar Me Plantation | Ongoing | 453563.17 | 0 | 2024-09-10
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722013034/IF/22012034989973 — GP DONGARI DASODA ME KAPIL DHARA KUP NIRMAN PREMSINGH KALU KE KHET PAR | Ongoing | 219929.45 | 0 | 2025-07-23
DHAR / DHARAMPURI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013034/IF/22012035021393 — GP DONGARI DASODA (DEGAWA)ME PLANTATION UMESH RUKHADIYA KE KHET ME | Ongoing | 151856.72 | 0 | 2022-12-07
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013034/IF/22012035600530 — Ek Bagiya Maa Ke Naam Saku Bai Dhannalal Gp Dongri Dasouda | Ongoing | 266577.25 | 0 | 2025-09-10
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013034/IF/22012035600555 — Ek Bagiya Maa Ke Naam Mangi Bai Dashrath GP Dongri Dasouda | Ongoing | 266577.25 | 0 | 2025-09-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722013034/IF/22012035659987 — Gp Dongri Dasoda Me Kapil Dhara Kup Nirman Karya Rameshwar Rama | New | 0 | 0 | 2025-08-15
DHAR / DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/115286 — Construction of IAY House -IAY REG. NO. MP-22-013-034-003/98 | Approved | 27000 | 0 | 2015-12-31
DHAR / DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/115296 — Construction of IAY House -IAY REG. NO. MP-22-013-034-003/115 | Approved | 27000 | 0 | 2015-12-31
DHAR / DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/115297 — Construction of IAY House -IAY REG. NO. MP-22-013-034-003/128 | Approved | 27000 | 0 | 2015-12-31
DHAR / DHARAMPURI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/4289708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106142729 | Approved | 27000 | 0 | 2022-07-08
DHAR / DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/4687186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106142628 | Approved | 27000 | 0 | 2024-09-23
DHAR / DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/4696786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117370039 | Approved | 27000 | 0 | 2024-09-16
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/4724000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146601334 | Completed | 23490 | 0 | 2025-07-31 | 2026-07-24
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5371257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105599469 | Completed | 27000 | 27000 | 2026-08-04 | 2026-09-23
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5371992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106143557 | Ongoing | 27000 | 0 | 2025-08-11
DHAR / DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5373706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147968193 | Approved | 27000 | 0 | 2025-02-21
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5378634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105667662 | Ongoing | 27000 | 0 | 2025-08-08
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5383016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103428912 | Ongoing | 27000 | 5600 | 2025-08-04
DHAR / DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/54291 — Construction of IAY House -IAY REG. NO. MP-22-013-034-002/46 | Approved | 27000 | 0 | 2015-10-16
DHAR / DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/54293 — Construction of IAY House -IAY REG. NO. MP-22-013-034-002/47 | Approved | 27000 | 0 | 2015-10-16
DHAR / DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/54296 — Construction of IAY House -IAY REG. NO. MP-22-013-034-002/52 | Approved | 27000 | 0 | 2015-10-16
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5458775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105666553 | Ongoing | 27000 | 18900 | 2026-07-20
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5460962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105741297 | Ongoing | 27000 | 0 | 2026-05-05
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5462055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105911315 | Ongoing | 27000 | 16800 | 2026-03-09
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5508174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105915853 | Ongoing | 27000 | 0 | 2026-05-05
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5608031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105730605 | Completed | 23490 | 0 | 2025-09-10 | 2026-07-28
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5608413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105911068 | Completed | 23490 | 23100 | 2026-07-20 | 2026-09-19
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5626334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106143259 | Approved | 27000 | 0 | 2025-05-13
DHAR / DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5627482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106519781 | Approved | 27000 | 0 | 2025-02-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5656129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147918741 | Completed | 23490 | 0 | 2026-06-09 | 2026-07-28
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5658813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103661363 | Completed | 23490 | 2700 | 2025-09-10 | 2026-09-23
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5694222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105613184 | Approved | 27000 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5696199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106441170 | Approved | 27000 | 0 | 2025-06-19
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5696533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120096003 | Completed | 27000 | 27000 | 2026-07-20 | 2026-10-07
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5697896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106144819 | Completed | 23490 | 0 | 2026-06-09 | 2026-07-28
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5733650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120095885 | Physically Completed | 27000 | 17700 | 2026-06-09 | 2026-10-04
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5753114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105907021 | Ongoing | 27000 | 0 | 2026-05-05
DHAR / DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5776598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117359980 | Approved | 27000 | 0 | 2025-03-28
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5870724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103519360 | Ongoing | 27000 | 12600 | 2026-09-28
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5903515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105907436 | Completed | 27000 | 27000 | 2026-08-04 | 2026-09-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5903768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104937668 | Ongoing | 27000 | 5350 | 2026-06-08
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5906452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147840829 | Completed | 27000 | 27000 | 2026-08-04 | 2026-09-23
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5907101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105600560 | Approved | 27000 | 0 | 2026-02-02
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5907791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106519686 | Ongoing | 27000 | 11400 | 2026-06-08
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5907908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105568575 | Ongoing | 27000 | 0 | 2026-06-08
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5909119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104937060 | Completed | 27000 | 27000 | 2026-07-21 | 2026-10-07
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5909173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117360689 | Approved | 27000 | 0 | 2026-02-02
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5909209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103427946 | Completed | 27000 | 11400 | 2026-06-08 | 2026-09-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5910419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105568244 | Physically Completed | 27000 | 0 | 2026-06-08 | 2026-09-20
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5911014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118324184 | Approved | 27000 | 0 | 2026-02-02
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5911532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104938971 | Completed | 27000 | 27000 | 2026-08-04 | 2026-09-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5913193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106519697 | Ongoing | 27000 | 0 | 2026-06-08
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5914040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146064333 | Ongoing | 27000 | 5350 | 2026-06-08
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5914081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146601667 | Completed | 27000 | 27000 | 2026-08-04 | 2026-09-23
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5914543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106145005 | Approved | 27000 | 0 | 2026-02-02
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5914788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105782514 | Approved | 27000 | 0 | 2026-02-02
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5915116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119643761 | Completed | 23490 | 11200 | 2026-06-08 | 2026-09-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5915301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105568058 | Completed | 23490 | 11400 | 2026-06-08 | 2026-09-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5916448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104932245 | Ongoing | 27000 | 19800 | 2026-08-04
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5917152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118060370 | Completed | 23490 | 0 | 2026-06-08 | 2026-07-28
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5918154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147840687 | Completed | 27000 | 27000 | 2026-08-04 | 2026-09-23
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5918509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117370528 | Approved | 27000 | 0 | 2026-02-02
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5918534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105600088 | Ongoing | 27000 | 4200 | 2026-06-08
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5918599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114899973 | Ongoing | 27000 | 0 | 2026-06-08
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5918631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105600456 | Ongoing | 27000 | 4200 | 2026-06-08
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5920543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105782893 | Ongoing | 27000 | 10500 | 2026-06-08
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5921215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105568354 | Ongoing | 27000 | 5350 | 2026-06-08
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5921249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117359621 | Ongoing | 27000 | 11400 | 2026-06-08
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5922375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146601386 | Approved | 27000 | 0 | 2026-02-02
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5922800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117370733 | Completed | 27000 | 19800 | 2026-06-08 | 2026-10-16
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5925858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146064300 | Completed | 23490 | 5250 | 2026-06-08 | 2026-09-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5926063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114889174 | Ongoing | 27000 | 11400 | 2026-06-08
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5927090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105781691 | Completed | 27000 | 27000 | 2026-08-04 | 2026-09-10
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5927681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117360530 | Completed | 27000 | 12000 | 2026-06-08 | 2026-09-29
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5927858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114888924 | Ongoing | 27000 | 11400 | 2026-06-08
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/5931123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105599198 | Ongoing | 27000 | 5350 | 2026-06-08
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6129527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117359536 | Approved | 27000 | 0 | 2026-03-22
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6129831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147640962 | Approved | 27000 | 0 | 2026-03-22
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6136585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106142085 | Ongoing | 27000 | 11400 | 2026-06-08
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6139898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147840543 | Approved | 27000 | 0 | 2026-03-09
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6228824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106143003 | Ongoing | 23490 | 17400 | 2026-06-08
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6267438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127612589 | Approved | 27000 | 0 | 2026-03-23
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6344879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117370485 | Approved | 27000 | 0 | 2025-04-07
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6346756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117370102 | Approved | 27000 | 0 | 2025-05-13
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6364452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104938348 | Approved | 27000 | 0 | 2026-02-02
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6364930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114889308 | Approved | 27000 | 0 | 2026-03-22
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6365230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117359806 | Approved | 27000 | 0 | 2026-03-22
DHAR / DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6397948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104945240 | Approved | 27000 | 0 | 2025-03-28
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6398211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114888577 | Approved | 27000 | 0 | 2026-02-02
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6398220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117359959 | Approved | 27000 | 0 | 2026-02-02
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013034/IF/IAY/6398233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120096024 | Approved | 27000 | 0 | 2026-03-22
DHAR / DHARAMPURI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1722013034/LD/22012034548658 — G.P. DONGRI DASODA ME PLANTATION SUBHASH KE GHAR KE SAMNE PAHADI PAR | Ongoing | 685545.62 | 0 | 2021-06-19
DHAR / DHARAMPURI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722013034/RS/22012034547131 — SBM ISP G.P. DONGRI DASODA(DEGAON) ME UNIT-20 | Physically Completed | 179999.57 | 0 | 2023-07-11 | 2026-08-16
DHAR / DHARAMPURI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Bio-drainage Plantation for Community | Plantation | 1722013034/WC/22012034660261 — CTRA GP DONGRI DASODA ME CPT NIRMAN MADAL SCHOOL KE PASS PART 2 | Ongoing | 667753.56 | 0 | 2021-11-01
DHAR / DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722013034/WC/22012035106902 — GP DONGARI DASODA ME NALA GEHARIKARAN BALU BAI KE KHET SE | Ongoing | 426592.01 | 0 | 2023-10-08
DHAR / DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1722013034/WC/22012035106946 — GP DONGARI DASODA ME SANKAN POND SERU BHAI KE KET KE PAS | Ongoing | 326794.71 | 0 | 2023-10-08
DHAR / DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1722013034/WC/22012035143119 — GP DONGARI DASODA MEMADHUPUR SE PATELPURA MARG PAR RMS SAHA PULIYA NIRMAN DEGAWA | Ongoing | 1446064.89 | 0 | 2023-10-08
DHAR / DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair & Maintenance of Fishery Pond for Community | Repair & maint of Pond/ Tank | 1722013034/WC/22012035162961 — Gp Me Water Pond Nirman Kary | New | 0 | 0 | 2024-01-28
DHAR / DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722013034/WC/22012035206546 — GP dongari dasoda me water pond m.s.ke pas | Approved | 0 | 0 | 2024-06-11
DHAR / DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722013034/WC/22012035206946 — GP Dongri Dasoda Me Water Pond Nirman Karya Pahadi Par | Ongoing | 356086.53 | 1800 | 2024-07-29