## Work List
Exported on: 2026-09-26 17:38:24
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Hatnawar
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722013040/DP/22012034530105 — G P HATNAWAR ME SHAHPURA HANUMAN MANDIR KE SAMNE WALE PAHADI PER PLANTATION | Ongoing | 394489.84 | 0 | 2025-02-05
DHAR / DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722013040/DP/22012034595788 — Aanganwadi Bhavan ke pass plantation Punarwas | Ongoing | 55847.4 | 0 | 2023-09-10
DHAR / DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1722013040/DP/22012034607000 — Dilipsingh Mandloi ke Khale me plantation | Ongoing | 160586.73 | 0 | 2023-10-07
DHAR / DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1722013040/DP/22012034607001 — Narendra Chouhan ke khale me Plantation | Ongoing | 160586.73 | 0 | 2023-10-07
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035394140 — JGSA 2025 Med BandhanShyanibai ke khet me Shahpura | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035394150 — JGSA 2025 Med Bandhan Mansingh Nirmole ke khet me Hatnawar | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035394193 — Nirmal Nir kup Nirman Shantilal Dhangar ke khet me Shahpura | New | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035394231 — Nirmal Nir kup Nirman Shantilal Dhangar ke khet me Shahpura | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035422312 — Nirmal Nir kup Nirman Mulayam Lalsingh ke khet me Shahpura | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035422351 — Nirmal Nir kup Nirman Mangilal Dodve ke khet me ke khet me Hatnawar | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722013040/IF/22012035434573 — JGSA 2025 KEHT TALAB NIRMAN SANTILAL DHANGAR KHET PER GP HATNAWAR | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035476994 — Kapil Dhara kup Nirman Shantilal Dhangar ke khet me Hatnawar | Ongoing | 369765.76 | 25500 | 2025-07-24
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035476998 — Kapil Dhara kup Nirman Mangilal Dodve ke khet me Hatnawar | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035477003 — Mulayam Lalsingh ke khet me Kapil Dhara kup nirman Hatnawar | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035477010 — JGSA 2025 khet talab Jaysingh Tanwar ke khet me | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035477012 — JGSA 2025 khet talab Deelip Bhai ke khet me | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035477017 — JGSA 2025 khet talab Bhuresingh Fatehsingh ke khet me | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035477019 — JGSA 2025 khet talab Shuselabai Fatehsingh ke khet me | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035477024 — JGSA 2025 khet talab Jagdev Dagdu ke khet me | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035477030 — JGSA 2025 khet talab Sakharam Muwel ke khet me | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035477035 — Phulkourbai ke khet me kapildhara kup nirman Hatnawar | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035477038 — Jitendra Karansingh ke khet me Kapildhara kup Nirman | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035477046 — Shobhag Bhai ke khet me Kapildhara kup Nirman | Approved | 369765.76 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035491874 — JGSA 2025 Recharge pit Bhagwan Patel ke khet me Hatnawar | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035491890 — JGSA 2025 Recharge pit Mulayam Lalsingh ke khet me | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1722013040/IF/22012035491895 — JGSA 2025 Recharge pit Kantabai Ramesh ke khet me | Approved | 0 | 0 | 2025-04-14
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013040/IF/22012035600000 — Ek Bagiya Maa ke Naam Durgabai Tanvar MP22013040004/120A | Ongoing | 266577.25 | 0 | 2025-08-29
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5281824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114167328 | Ongoing | 27000 | 0 | 2025-04-29
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5455163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145462844 | Completed | 23490 | 0 | 2025-08-29 | 2026-07-27
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5456028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103530172 | Completed | 23490 | 0 | 2025-08-29 | 2026-07-27
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5903678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114167914 | Ongoing | 27000 | 0 | 2026-05-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5904276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126083744 | Ongoing | 27000 | 0 | 2026-05-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5905878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106495500 | Ongoing | 27000 | 0 | 2026-05-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5907410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103522825 | Ongoing | 27000 | 8400 | 2026-05-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5907604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113498850 | Ongoing | 27000 | 7854 | 2026-05-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5908270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102113877 | Ongoing | 27000 | 10227 | 2026-05-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5909465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106491218 | Ongoing | 27000 | 10227 | 2026-05-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5910597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106501669 | Ongoing | 27000 | 0 | 2026-05-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5910864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106493604 | Ongoing | 27000 | 5754 | 2026-05-23
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5911506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113510886 | Ongoing | 27000 | 0 | 2026-06-12
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5912465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113513973 | Ongoing | 27000 | 0 | 2026-06-12
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5914244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102113803 | Ongoing | 27000 | 2100 | 2026-06-12
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5914758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125342179 | Ongoing | 27000 | 12054 | 2026-06-02
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5915055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126022876 | Ongoing | 27000 | 0 | 2026-06-12
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5916227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103528331 | Ongoing | 27000 | 0 | 2026-06-12
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5917866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101004387 | Ongoing | 27000 | 8127 | 2026-02-26
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5920654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113516312 | Approved | 27000 | 0 | 2026-01-19
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5921175 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128723595 | Approved | 27000 | 0 | 2026-01-15
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5928672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126084183 | Ongoing | 27000 | 12327 | 2026-03-10
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5928923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113510560 | Ongoing | 27000 | 9954 | 2026-03-10
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5930926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106494111 | Ongoing | 27000 | 10227 | 2026-02-26
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5931197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101004374 | Ongoing | 27000 | 8127 | 2026-02-26
DHAR / DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/5931789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104956837 | Ongoing | 27000 | 16254 | 2026-02-26
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/6126318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102113787 | Ongoing | 27000 | 12054 | 2026-04-17
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/6128472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103520796 | Ongoing | 27000 | 0 | 2026-04-17
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/6138042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106503340 | Ongoing | 27000 | 0 | 2026-04-17
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/6139823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126087985 | Ongoing | 27000 | 0 | 2026-04-17
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/6148145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126082829 | Ongoing | 27000 | 0 | 2026-04-17
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/6156691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114167468 | Ongoing | 27000 | 8127 | 2026-04-17
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/6160352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113467924 | Ongoing | 27000 | 0 | 2026-04-17
DHAR / DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013040/IF/IAY/6169273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113472441 | Ongoing | 27000 | 0 | 2026-04-17
DHAR / DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1722013040/LD/22012034942698 — GP Hatnawar ke Bhairung Baba Baidi par Plantation | Ongoing | 453563.17 | 9600 | 2024-08-29
DHAR / DHARAMPURI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1722013040/RS/22012035133125 — samudayik swachhata parisar nirman punrvas panchayat bhawan parisar | Ongoing | 44000 | 0 | 2024-11-08
DHAR / DHARAMPURI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1722013040/WC/22012034567061 — G P HATNAWAR ME PLANTATIOPN NARMDA KE KINARE | Ongoing | 677985.75 | 0 | 2020-08-06
DHAR / DHARAMPURI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722013040/WC/22012034610655 — Gram Panchayat hatnawar me shahpura hanuman mandir me neagra vatika | Ongoing | 390851.61 | 0 | 2021-03-05
DHAR / DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722013040/WC/22012035162986 — Gp Me Water Pond Nirman Kary | New | 0 | 0 | 2024-01-27
DHAR / DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722013040/WC/22012035203796 — GP Hatnawar ke Shahpura me Waterpond | Approved | 0 | 0 | 2024-06-08
DHAR / DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722013040/WC/22012035220890 — GP Hatnawar me CTR Plantation ke pass 02 | Approved | 0 | 0 | 2024-08-15
DHAR / DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722013040/WC/22012035220891 — GP Hatnawar me CTR Plantation ke pass 01 | New | 0 | 0 | 2024-08-15