## Work List
Exported on: 2026-09-27 21:42:47
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PADLY BABAJI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHARGONE / BHIKANGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1724005038/DP/22012034487005 — Nirmal Nir Nirman Hasibi Ke Khet Ke Pas Kholwa Padliya Baba | Ongoing | 464568.96 | 0 | 2020-07-16
KHARGONE / BHIKANGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724005038/IF/22012034613934 — Phalodyan Pariyojna Aslam Hasan GP Kholwa Padliyababaji | Ongoing | 115360 | 0 | 2020-11-19
KHARGONE / BHIKANGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1724005038/IF/22012034652784 — Kapil Dhara Nirman Sanjay Chhitar Padliyababaji | Ongoing | 246126.86 | 0 | 2021-01-19
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724005038/IF/22012035638451 — एक बगिया मॉ के नाम सैजाद बी बैवा सईद खोलवा पाडल्‍याबाबाजी | Ongoing | 263511.37 | 0 | 2025-12-09
KHARGONE / BHIKANGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/2575517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4743755 | Ongoing | 27000 | 0 | 2022-09-02
KHARGONE / BHIKANGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/3099906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4034581 | Ongoing | 27000 | 0 | 2021-05-31
KHARGONE / BHIKANGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/3141526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4040585 | Ongoing | 27000 | 0 | 2021-06-21
KHARGONE / BHIKANGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/4172273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146403114 | Ongoing | 27000 | 0 | 2022-06-30
KHARGONE / BHIKANGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/4387959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126480762 | Approved | 27000 | 0 | 2022-11-21
KHARGONE / BHIKANGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/5431333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115719211 | Approved | 27000 | 0 | 2025-02-20
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/5797351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115719139 | Ongoing | 27000 | 0 | 2025-09-12
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115747467 | Ongoing | 27000 | 4500 | 2026-08-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115726924 | Ongoing | 27000 | 17700 | 2026-06-04
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115726963 | Ongoing | 27000 | 0 | 2026-09-26
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115727003 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115727492 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115727782 | Physically Completed | 27000 | 17700 | 2026-06-04 | 2026-09-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115735249 | Ongoing | 27000 | 0 | 2026-06-04
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115728355 | Ongoing | 27000 | 9000 | 2026-08-24
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115737763 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115738082 | Ongoing | 27000 | 9000 | 2026-08-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115738636 | Ongoing | 27000 | 9000 | 2026-08-24
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115738683 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115739053 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115739206 | Ongoing | 27000 | 0 | 2026-06-04
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115739726 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117737254 | Ongoing | 27000 | 9000 | 2026-08-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6118735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115739449 | Ongoing | 27000 | 18000 | 2026-07-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6119119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117737964 | Ongoing | 27000 | 4500 | 2026-08-24
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6119832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115719067 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6119833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115751483 | Ongoing | 27000 | 0 | 2026-06-04
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6119868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117738094 | Ongoing | 27000 | 18000 | 2026-07-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6120571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115747229 | Ongoing | 27000 | 13200 | 2026-06-04
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6120736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115727630 | Ongoing | 27000 | 13200 | 2026-06-04
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6121023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115735512 | Ongoing | 27000 | 9000 | 2026-08-24
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6121637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117860827 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6121683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115751124 | Ongoing | 27000 | 9000 | 2026-08-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6122058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115728169 | Ongoing | 27000 | 9000 | 2026-08-24
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6122179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115726688 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6122180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115726810 | Ongoing | 27000 | 0 | 2026-09-26
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6122432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071354 | Ongoing | 27000 | 0 | 2026-09-26
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6122538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115746183 | Ongoing | 27000 | 4500 | 2026-08-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6122543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115727266 | Ongoing | 27000 | 9000 | 2026-08-24
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6122544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115737980 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6122545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115738566 | Physically Completed | 27000 | 17700 | 2026-06-04 | 2026-09-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6122546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117737480 | Completed | 23490 | 0 | 2026-04-23 | 2026-08-10
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6128538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126652883 | Ongoing | 27000 | 0 | 2026-06-04
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6133662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151371933 | Ongoing | 27000 | 9000 | 2026-08-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6137457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151346942 | Physically Completed | 27000 | 17700 | 2026-06-04 | 2026-09-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6138344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117742994 | Completed | 23490 | 0 | 2026-04-23 | 2026-08-10
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6141468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117977245 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6141643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126832930 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6142712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124160341 | Ongoing | 27000 | 13200 | 2026-06-04
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6142713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124160954 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6142859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121831557 | Ongoing | 27000 | 13200 | 2026-06-04
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6154783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126828820 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6155398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120967049 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6165567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124164951 | Approved | 27000 | 0 | 2026-03-07
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6168606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146423929 | Ongoing | 27000 | 0 | 2026-08-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6177858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117891401 | Ongoing | 27000 | 4500 | 2026-08-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6180277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115726650 | Ongoing | 27000 | 8700 | 2026-06-04
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6189191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115752584 | Ongoing | 27000 | 13200 | 2026-06-04
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6190352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126855694 | Ongoing | 27000 | 0 | 2026-09-26
KHARGONE / BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6211408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115738181 | Approved | 27000 | 0 | 2026-03-13
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6356307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115751371 | Approved | 27000 | 0 | 2026-07-24
KHARGONE / BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724005038/IF/IAY/6356467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146480714 | Approved | 27000 | 0 | 2026-07-24
KHARGONE / BHIKANGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1724005038/RC/22012034675923 — सीसी रोड निर्माण | New | 0 | 0 | 2023-10-02
KHARGONE / BHIKANGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1724005038/RS/22012034645763 — व्यक्तिगत सोक पिट SBM कांसम खां अब्‍दुल व ४ अन्‍य खोलवा पाडल्‍याबाबाजी | Ongoing | 20000 | 0 | 2022-05-07