## Work List
Exported on: 2026-09-15 17:05:46
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MANGRUL KHURD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHARGONE / GOGANWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1724007025/DP/22012034562612 — Bamboo Plantation Mangrul Khurd Nadi Ke Pass | Ongoing | 824805.86 | 0 | 2022-09-02
KHARGONE / GOGANWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1724007025/DP/22012034588744 — Plantation Work Meri Mati Mera Desh Gp Mangrul Khurd | Ongoing | 54577.96 | 3600 | 2023-08-11
KHARGONE / GOGANWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1724007025/IF/22012035132663 — BLOCK PLANTATION WATER POND KE PASS | Ongoing | 757490.82 | 25800 | 2023-08-11
KHARGONE / GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724007025/IF/22012035600736 — EK bagiya ma ke naam GIRJA SOLANKI MP-24-007-025-001/152-B | Ongoing | 261747.23 | 19800 | 2025-08-31
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6123129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119937123 | Completed | 23490 | 0 | 2026-04-17 | 2026-07-14
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6123755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115339737 | Ongoing | 27000 | 0 | 2026-05-08
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6123897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115339792 | Completed | 23490 | 0 | 2026-04-24 | 2026-07-14
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6127346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122466222 | Completed | 23490 | 1566 | 2026-04-17 | 2026-09-12
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6136192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117605571 | Completed | 23490 | 0 | 2026-04-17 | 2026-09-12
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6141066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127465491 | Completed | 23490 | 0 | 2026-04-17 | 2026-07-14
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6146151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119936941 | Completed | 23490 | 4437 | 2026-04-17 | 2026-09-12
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6160033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115339491 | Completed | 23490 | 3654 | 2026-04-17 | 2026-08-13
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6160035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115339526 | Completed | 23490 | 1566 | 2026-04-17 | 2026-08-13
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6160839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115891680 | Ongoing | 27000 | 10227 | 2026-05-15
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6166716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115768680 | Completed | 23490 | 1566 | 2026-04-17 | 2026-08-13
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6166717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115768710 | Completed | 23490 | 261 | 2026-04-17 | 2026-07-27
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6170795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120753869 | Completed | 23490 | 1566 | 2026-04-17 | 2026-08-13
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6175350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114091753 | Completed | 23490 | 3344 | 2026-04-17 | 2026-09-12
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6192032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125831570 | Completed | 23490 | 1566 | 2026-04-17 | 2026-08-13
KHARGONE / GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724007025/IF/IAY/6243155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115702086 | Ongoing | 27000 | 20181 | 2026-07-03
KHARGONE / GOGANWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1724007025/WC/22012035168592 — water pond | New | 0 | 0 | 2024-04-01