## Work List
Exported on: 2026-09-13 15:37:19
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MADANI KHURD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHARGONE / BHAGVANPURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1724008037/IF/22012034653477 — KUP NIRMAN KARY SAYARI BAI RICHHU | Ongoing | 246126.86 | 0 | 2021-06-01
KHARGONE / BHAGVANPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1724008037/IF/22012035531162 — JGSA Khet Talab Mahendra ke khet me | Approved | 0 | 0 | 2025-04-01
KHARGONE / BHAGVANPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1724008037/IF/22012035531194 — JGSA Khet Talab Shobharam ke khet me | Approved | 0 | 0 | 2025-04-01
KHARGONE / BHAGVANPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1724008037/IF/22012035531203 — JGSA Khet Talab Gem Singh ke khet me | Approved | 0 | 0 | 2025-04-01
KHARGONE / BHAGVANPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724008037/IF/22012035604554 — एक बगिया मां के नाम SHITAL MP-24-008-037-001/161-A | Ongoing | 266577.25 | 7500 | 2025-11-11
KHARGONE / BHAGVANPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724008037/IF/22012035604568 — एक बगिया मां के नाम RITA MP-24-008-037-001/229-A | Ongoing | 266577.25 | 1500 | 2025-11-11
KHARGONE / BHAGVANPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724008037/IF/IAY/4738307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105193630 | Completed | 23490 | 0 | 2025-03-20 | 2026-07-25
KHARGONE / BHAGVANPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724008037/IF/IAY/5153006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105192778 | Completed | 23490 | 0 | 2025-05-09 | 2026-07-27
KHARGONE / BHAGVANPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724008037/IF/IAY/5231902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140542912 | Ongoing | 27000 | 0 | 2025-05-09
KHARGONE / BHAGVANPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724008037/IF/IAY/5520980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115998354 | Completed | 23490 | 0 | 2025-05-30 | 2026-08-25
KHARGONE / BHAGVANPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724008037/IF/IAY/5621999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124484527 | Physically Completed | 23490 | 0 | 2025-05-26 | 2026-08-25
KHARGONE / BHAGVANPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724008037/IF/IAY/5744957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106955759 | Completed | 23490 | 0 | 2025-09-10 | 2026-07-25
KHARGONE / BHAGVANPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1724008037/IF/IAY/5748686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122172137 | Ongoing | 27000 | 0 | 2025-08-19
KHARGONE / BHAGVANPURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1724008037/RS/22012034609651 — samudayik swachhata parisar panchayat bhawan ke pass school parisar Madani Khurd | Ongoing | 65000 | 0 | 2021-11-18
KHARGONE / BHAGVANPURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1724008037/WC/22012034573969 — NIRMAL NEER KUP BHERURA RENJLA FALYA KE PAAS | Ongoing | 470874.11 | 0 | 2021-03-24
KHARGONE / BHAGVANPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1724008037/WC/22012035167141 — Percolation tank | New | 0 | 0 | 2024-04-01
KHARGONE / BHAGVANPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1724008037/WC/22012035218488 — Water pound nirman kary hiralal badole ke khet pass | Approved | 0 | 0 | 2024-07-06
KHARGONE / BHAGVANPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1724008037/WC/22012035218491 — Water pound nirman kary aasharam ghurkya ke khet pass | New | 0 | 0 | 2024-07-06
KHARGONE / BHAGVANPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1724008037/WC/22012035218492 — Water pound nirman kary aasharam ghurkya ke khet pass | Approved | 0 | 0 | 2024-07-06
KHARGONE / BHAGVANPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1724008037/WC/22012035268485 — Handpump Recharge Pit Badi Kinal Ke Paas | Approved | 25899.46 | 0 | 2025-04-01
KHARGONE / BHAGVANPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1724008037/WC/22012035324355 — परकोलेशन टेंक नदी पास मदनीखुर्द | Ongoing | 572203.38 | 18000 | 2026-02-07
KHARGONE / BHAGVANPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1724008037/WC/22012035325041 — परकोलेशन टेंक कमल के खेत पास मदनीखुर्द | Ongoing | 1154858.57 | 300 | 2026-05-09
KHARGONE / BHAGVANPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1724008037/WC/VB/22012035334318 — Contour Trench madnikhurd | Approved | 0 | 0 | 2026-04-01