## Work List
Exported on: 2026-10-12 11:16:02
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JASWADI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHANDWA / KHANDWA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of Workshed for SHG for Community | Construction of building/workshed for SHG | 1725005023/AV/22012034611619 — सेगरी केशन सेड निर्माण कार्य ग्राम पंचायत जसवाडी | Ongoing | 1042693.02 | 0 | 2022-01-03
KHANDWA / KHANDWA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1725005023/AV/22012034661988 — बाउंडीवाल निर्माण कार्य मा0 शा0 जसवाडी | Ongoing | 153000 | 0 | 2024-11-24
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1725005023/IF/22012035277152 — कपिलधारा कूप निर्माण कार्य लिमडा बलीराम ग्राम पंचायत जसवाड़ी | New | 0 | 0 | 2024-12-09
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005023/IF/22012035345797 — JGJSA 2025 Dug Well Recharge balmukund natthu Jaswadi | Approved | 25899.46 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005023/IF/22012035345820 — JGJSA 2025 Dug Well Recharge anand mangilal Jaswadi | Approved | 25899.46 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005023/IF/22012035345897 — JGJSA 2025 Dug Well Recharge narayan punya Jaswadi | Approved | 25899.46 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005023/IF/22012035435248 — JGJSA2025 khet talab kary mukesh nana ke khet me | New | 0 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005023/IF/22012035584651 — Ek Bagiya Ma ke nam meena bai | Ongoing | 237842.36 | 0 | 2025-08-23
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005023/IF/22012035584658 — Ek Bagiya Ma ke nam jyoti bai | Ongoing | 237842.36 | 0 | 2025-08-23
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005023/IF/22012035586696 — Ek Bagiya Ma ke Nam SUNITA JAYASWAL | Ongoing | 237842.36 | 0 | 2025-08-23
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005023/IF/22012035608789 — Ek Bagiya Ma ke Nam MAYA BAI | Ongoing | 240842.17 | 0 | 2025-09-10
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005023/IF/22012035615854 — Ek Bagiya Ma ke Nam MAYA BAI MP-25-005-023-001/226 | Ongoing | 199260.73 | 0 | 2025-10-18
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/4554702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113883418 | Completed | 23490 | 0 | 2024-11-18 | 2026-08-23
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/4743410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113899106 | Completed | 23490 | 0 | 2024-11-18 | 2026-08-23
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/5489753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118113524 | Approved | 27000 | 0 | 2025-02-11
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/5491613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114155499 | Completed | 23490 | 0 | 2025-07-03 | 2026-08-23
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/5493434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115656074 | Approved | 27000 | 0 | 2025-02-11
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/5881389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113870213 | Ongoing | 27000 | 0 | 2026-10-08
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/5881688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113867229 | Completed | 27000 | 26100 | 2026-07-10 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6123900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115347482 | Ongoing | 27000 | 3600 | 2026-09-28
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6129234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115913625 | Physically Completed | 27000 | 6000 | 2026-08-04 | 2026-09-28
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6129237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115916452 | Approved | 27000 | 0 | 2026-02-06
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6130747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116240076 | Ongoing | 27000 | 11160 | 2026-09-07
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6134383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114764115 | Ongoing | 27000 | 3600 | 2026-07-30
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6136056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113874608 | Ongoing | 27000 | 5400 | 2026-09-28
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6137689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128954937 | Ongoing | 27000 | 17400 | 2026-08-04
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6138583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116250962 | Approved | 27000 | 0 | 2026-02-06
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6143560 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118125060 | Ongoing | 27000 | 1800 | 2026-09-28
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6144362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115341280 | Approved | 27000 | 0 | 2026-02-06
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6144394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118083286 | Approved | 27000 | 0 | 2026-02-06
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6146167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113916426 | Completed | 27000 | 27000 | 2026-08-04 | 2026-09-30
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6148196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115901259 | Completed | 27000 | 27000 | 2026-08-04 | 2026-09-30
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6148709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116229674 | Ongoing | 27000 | 18000 | 2026-07-10
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6149797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115641159 | Ongoing | 27000 | 20700 | 2026-08-04
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6152879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113895683 | Ongoing | 27000 | 21600 | 2026-07-24
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6152964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114760118 | Completed | 27000 | 27000 | 2026-08-04 | 2026-09-30
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6173739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113906812 | Completed | 27000 | 27000 | 2026-08-04 | 2026-09-30
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6174551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117439524 | Approved | 27000 | 0 | 2026-02-06
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6174717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115355885 | Ongoing | 27000 | 0 | 2026-10-08
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6249237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113876800 | Ongoing | 27000 | 0 | 2026-10-12
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6249398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113875703 | Ongoing | 27000 | 0 | 2026-10-12
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6250307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113911630 | Ongoing | 27000 | 0 | 2026-10-12
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6251407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115885490 | Approved | 27000 | 0 | 2026-03-26
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6251409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115887233 | Approved | 27000 | 0 | 2026-03-26
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6251795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115339042 | Approved | 27000 | 0 | 2026-03-26
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6251861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115653348 | Approved | 27000 | 0 | 2026-03-26
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6251921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115657952 | Approved | 27000 | 0 | 2026-03-26
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6252113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116232509 | Ongoing | 27000 | 0 | 2026-10-12
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6253728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117449870 | Approved | 27000 | 0 | 2026-03-26
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6253846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117447992 | Approved | 27000 | 0 | 2026-03-30
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6254619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117443543 | Approved | 27000 | 0 | 2026-03-26
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6254895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118119856 | Approved | 27000 | 0 | 2026-03-27
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6255009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118133559 | Ongoing | 27000 | 0 | 2026-10-12
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6261923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124442855 | Approved | 27000 | 0 | 2026-03-26
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6280921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115884187 | Ongoing | 27000 | 0 | 2026-10-12
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6281818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118109286 | Approved | 27000 | 0 | 2026-03-26
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6286228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117440195 | Ongoing | 27000 | 0 | 2026-10-08
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6287163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115648992 | Ongoing | 27000 | 0 | 2026-10-12
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6296019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115645391 | Ongoing | 27000 | 0 | 2026-10-11
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6297115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115906095 | Ongoing | 27000 | 0 | 2026-10-12
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6297116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116244273 | Ongoing | 27000 | 0 | 2026-10-12
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6297123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118081809 | Approved | 27000 | 0 | 2026-03-26
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6299972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113904990 | Ongoing | 27000 | 0 | 2026-10-12
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6301487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125100402 | Ongoing | 27000 | 0 | 2026-10-12
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6302876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115346633 | Approved | 27000 | 0 | 2026-03-26
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6302878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115904437 | Ongoing | 27000 | 0 | 2026-10-12
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6302887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115654257 | Approved | 27000 | 0 | 2026-02-06
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6303062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115880769 | Approved | 27000 | 0 | 2026-03-11
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6400644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118128961 | Approved | 27000 | 0 | 2026-03-11
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005023/IF/IAY/6401758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118126022 | Approved | 27000 | 0 | 2026-07-30
KHANDWA / KHANDWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1725005023/RS/22012034522358 — कचरा संग्रहण सेगरिकेशन शेड निर्माण कार्य | Ongoing | 1036110.49 | 0 | 2021-06-22