## Work List
Exported on: 2026-10-10 11:24:10
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MUNDWADA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHANDWA / KHANDWA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1725005035/FP/22012034641792 — स्ट्रोम वाटर ड्रेन निर्माण कार्य खलील के खेत से फटाका फैक्टरी की ओर मूंदवाङा | Approved | 428934.16 | 0 | 2025-01-01
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1725005035/IF/22012035218349 — कपिल धारा कूप निर्माण कार्य इमरान सलीम | Ongoing | 405183.38 | 0 | 2024-06-29
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005035/IF/22012035417272 — JGJSA225 khet talab nirman kary UMAR AJIJ MUNDWAD | Approved | 202326.01 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005035/IF/22012035417277 — JGJSA225 khet talab nirman kary NOUSHAD HAMID MUNDWADA | Approved | 202326.01 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005035/IF/22012035417309 — JGJSA225 khet talab nirman kary SUGRA BAI GOVINDJUBEDA RAHIM MUNDWADA | Approved | 202326.01 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035490626 — JGJSA225 DUG WELL RECHARGE shaikh khalik shaikhh ibrahim | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035490673 — JGJSA225 DUG WELL RECHARGE majur khan mehrab khan | Approved | 25496.78 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035490694 — JGJSA225 DUG WELL RECHARGEanvar khan abdul rahman khan | Approved | 25496.78 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035490704 — JGJSA225 DUG WELL RECHARGE sultana bee vahid khan | Approved | 25496.78 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035490716 — JGJSA225 DUG WELL RECHARGE kalim lkhan rahim khan | Approved | 25496.78 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035552557 — JGJSA225 DUG WELL RECHARGE FAKIRA AJIJ | Approved | 25496.78 | 0 | 2025-05-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035552576 — JGJSA225 DUG WELL RECHARGE RAHIM KARIM | Approved | 25496.78 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005035/IF/22012035574912 — khet talab khalik khan | Approved | 55865.38 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035586551 — Ek Bagiya Ma ke Nam RAHISHA BEE | Ongoing | 280503.33 | 0 | 2025-08-20
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035587104 — Ek Bagiya ma ke nam RAEESA BEE | Ongoing | 280503.33 | 0 | 2025-08-20
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035587105 — Ek Bagiya ma ke nam Gulnaj Bee | Ongoing | 280503.33 | 0 | 2025-08-20
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035587108 — Ek Bagiya ma ke nam AMEENA BEE | Ongoing | 280503.33 | 0 | 2025-08-20
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035588173 — EK BAGIYA MA KE NAAM RAHISA JAHIR | Approved | 266577.25 | 0 | 2025-08-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1725005035/IF/22012035598324 — JGJSA 2025 DUG WELL RECHARGE manjur ke ket par | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600286 — JGJSA 2025 DUG WELL REGHAGE JAHIR KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600294 — JGJSA 2025 DUG WELL REGHAGE RAHIM KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600296 — JGJSA 2025 DUG WELL REGHAGE KALIM KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600298 — JGJSA 2025 DUG WELL RECHARGE FAKIRA ke ket par | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600299 — JGJSA 2025 DUG WELL REGHAGE IKLAK KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600301 — JGJSA 2025 DUG WELL REGHAGE IMRAN KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600302 — JGJSA 2025 DUG WELL REGHAGE SHARUKH KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600304 — JGJSA 2025 DUG WELL REGHAGE JARINA KALU KE KHET PAAS | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600307 — JGJSA 2025 DUG WELL REGHAGE YAKIN KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600308 — JGJSA 2025 DUG WELL REGHAGE LUKMAAN KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600310 — JGJSA 2025 DUG WELL REGHAGE YAKIN KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600311 — JGJSA 2025 DUG WELL REGHAGE SADID KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600314 — JGJSA 2025 DUG WELL REGHAGE ANWAR KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600315 — JGJSA 2025 DUG WELL REGHAGE SALIM M KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600318 — JGJSA 2025 DUG WELL REGHAGE SHIEK KHALIK KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600320 — JGJSA 2025 DUG WELL REGHAGE JAHIR KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600321 — JGJSA 2025 DUG WELL REGHAGE SHAHIR KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600323 — JGJSA 2025 DUG WELL REGHAGE SHEIKH KALIM KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600327 — JGJSA 2025 DUG WELL REGHAGE DILDAR WAHID KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600329 — JGJSA 2025 DUG WELL REGHAGE NAWAB HAMID KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600332 — JGJSA 2025 DUG WELL REGHAGE IKBALHAMID KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600334 — JGJSA 2025 DUG WELL REGHAGE IDRISB KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600338 — JGJSA 2025 DUG WELL REGHAGE RIJWANA KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600341 — JGJSA 2025 DUG WELL REGHAGE WAHID KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600346 — JGJSA 2025 DUG WELL REGHAGE SHOEL KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600349 — JGJSA 2025 DUG WELL REGHAGE MUSTKIM KE KHET PAAS | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600356 — JGJSA 2025 DUG WELL REGHAGEMUSTAKIM KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600357 — JGJSA 2025 DUG WELL REGHAGE AJAD KABIR KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600359 — JGJSA 2025 DUG WELL REGHAGE MAKSUD KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600360 — JGJSA 2025 DUG WELL REGHAGE TAKSIN KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600361 — JGJSA 2025 DUG WELL REGHAGE FARUK KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600363 — JGJSA 2025 DUG WELL REGHAGE BABU KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600365 — JGJSA 2025 DUG WELL REGHAGE ANTAR KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600367 — JGJSA 2025 DUG WELL REGHAGE SANJAY KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600368 — JGJSA 2025 DUG WELL REGHAGE AKHATR KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600370 — JGJSA 2025 DUG WELL REGHAGE WASELA KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600371 — JGJSA 2025 DUG WELL REGHAGE KARAN SHING KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600372 — JGJSA 2025 DUG WELL REGHAGE ASIF KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600373 — JGJSA 2025 DUG WELL REGHAGE KHALIL KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600375 — JGJSA 2025 DUG WELL REGHAGE YUNUS PATEL KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600379 — JGJSA 2025 DUG WELL REGHAGE SAKIL KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600382 — JGJSA 2025 DUG WELL REGHAGE NAVAB KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600384 — JGJSA 2025 DUG WELL REGHAGE NIJAM KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600388 — JGJSA 2025 DUG WELL REGHAGE JUBEDA KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600389 — JGJSA 2025 DUG WELL REGHAGE SHADIK KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600395 — JGJSA 2025 DUG WELL REGHAGE SIDDIK KE KHET PAAS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005035/IF/22012035600398 — JGJSA 2025 DUG WELL REGHAGE SARVAR KE KHET PAAS | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035604611 — Ek Bagiya Ma ke Naam SBIYABI SHEK MP-25-005-035-002/273 | Ongoing | 280324.03 | 0 | 2026-02-20
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035604620 — Ek Bagiya Ma ke Naam SALAMA BI MP-25-005-035-002/212-A | Ongoing | 280324.03 | 0 | 2025-09-04
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035611358 — Ek Bagiya Ma ke Nam NASRIN KHAN | Ongoing | 238731.49 | 0 | 2025-10-05
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035611380 — Ek Bagiya Ma ke Nam SALAMA BI | New | 0 | 0 | 2025-09-03
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035613726 — Ek Bagiya Ma ke Nam RABIYA BEE MP-25-005-035-002/279 | Ongoing | 199526.34 | 0 | 2026-01-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035615868 — Ek Bagiya Ma ke Nam SHAMIM BANO KHAN MP-25-005-035-002/68-A | Approved | 199526.34 | 0 | 2025-09-08
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035615891 — Ek Bagiya Ma ke Nam NAZNIN SHEKH MP-25-005-035-002/65 | Ongoing | 199253.31 | 0 | 2025-10-25
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035615931 — Ek Bagiya Ma ke Nam RAJIA BEE MP-25-005-035-002/27 | Ongoing | 199707.24 | 0 | 2025-10-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035615950 — Ek Bagiya Ma ke Nam sahida bee | Approved | 0 | 0 | 2025-09-03
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035616200 — Ek Bagiya Ma ke Nam SANIYA BEE MP-25-005-035-002/27 A | New | 0 | 0 | 2025-09-08
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005035/IF/22012035620164 — KHET TALAB NIRMAN KARY SHAYNA BEE MUNDWADA | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005035/IF/22012035620226 — KHET TALAB NIRMAN KARY SAHEEDA BEE MUNDWADA | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005035/IF/22012035620239 — KHET TALAB NIRMAN KARY ANISHA BEE MUNDWADA | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005035/IF/22012035620256 — KHET TALAB NIRMAN KARY JUBEDA BEE | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005035/IF/22012035620287 — KHET TALAB NIRMAN KARY JAHAGIR MUNDWADA | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005035/IF/22012035620297 — KHET TALAB NIRMAN KARY KHALIK MUNDWADA | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005035/IF/22012035620307 — KHET TALAB NIRMAN KARY ABDUL KHA MUNDWADA | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035621983 — Ek Bagiya Ma ke Nam SHAVIYA BEE MP-25-005-035-002/127-B | Approved | 199400.56 | 0 | 2025-08-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035629259 — EK BAGIYA MA KE NAAM SBIYABI SHEK MP-25-005-035-002/273 | New | 0 | 0 | 2025-08-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035629260 — EK BAGIYA MA KE NAAM ARFANA BEE MP-25-005-035-002/65-A | Approved | 199413.72 | 0 | 2025-08-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035629261 — EK BAGIYA MA KE NAAM NEELOFR KHAN MP-25-005-035-002/240 | Ongoing | 199413.72 | 0 | 2026-01-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035629262 — EK BAGIYA MA KE NAAM FEMIDA KHAN MP-25-005-035-002/242 | Approved | 199413.72 | 0 | 2025-08-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035629264 — EK BAGIYA MA KE NAAM AMREEN BEE MP-25-005-035-002/22 | Approved | 199413.72 | 0 | 2025-08-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035629265 — EK BAGIYA MA KE NAAM CHHOTI BEE SHEKH MP-25-005-035-002/222-A | Approved | 199413.72 | 0 | 2025-08-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035636468 — Ek Bagiya Ma ke Nam SABNAM BEE MP-25-005-035-002/27-A | New | 0 | 0 | 2025-10-28
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005035/IF/22012035636469 — Ek Bagiya Ma ke Nam SABNAM BEE MP-25-005-035-002/27-A | Ongoing | 266578.64 | 300 | 2025-11-11
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/4548198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106711937 | Completed | 23490 | 0 | 2024-11-14 | 2026-08-21
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5903710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106269546 | Ongoing | 27000 | 5400 | 2026-04-01
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5904064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113885726 | Ongoing | 27000 | 0 | 2026-04-01
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5904080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113704131 | Ongoing | 27000 | 0 | 2026-04-01
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5904379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129638375 | Ongoing | 27000 | 0 | 2026-04-01
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5905226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118684341 | Completed | 27000 | 11700 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5905350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120925743 | Completed | 27000 | 12600 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5906446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120989041 | Ongoing | 27000 | 12600 | 2026-04-01
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5906823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149927557 | Physically Completed | 27000 | 0 | 2026-04-01 | 2026-09-27
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5907339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129530341 | Completed | 27000 | 5400 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5908740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129154633 | Physically Completed | 27000 | 26400 | 2026-08-21 | 2026-10-08
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5909384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115033840 | Completed | 27000 | 19200 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5909546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106261395 | Completed | 23490 | 0 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5909951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129578288 | Physically Completed | 27000 | 14400 | 2026-04-07 | 2026-09-25
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5909985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132336455 | Physically Completed | 27000 | 12000 | 2026-04-01 | 2026-09-25
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5910555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129530720 | Completed | 27000 | 12000 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5911273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150130974 | Completed | 27000 | 12000 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5911842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113967291 | Completed | 27000 | 12000 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5912347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126794419 | Completed | 27000 | 12000 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5912769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129531486 | Completed | 27000 | 12000 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5912798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129530055 | Physically Completed | 27000 | 22800 | 2026-08-21 | 2026-10-04
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5914407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125910336 | Approved | 27000 | 0 | 2026-01-14
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5914457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113885793 | Ongoing | 27000 | 13200 | 2026-04-01
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5915470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113967255 | Completed | 27000 | 4200 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5916277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113967207 | Completed | 27000 | 12000 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5917815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114952578 | Ongoing | 27000 | 18900 | 2026-04-01
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5918138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106891264 | Completed | 27000 | 12600 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5918448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129983813 | Completed | 27000 | 12300 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5919424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113967379 | Completed | 27000 | 12000 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5919939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140019878 | Physically Completed | 27000 | 27000 | 2026-08-21 | 2026-10-06
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5920651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129638212 | Physically Completed | 27000 | 0 | 2026-04-01 | 2026-09-27
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5920930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120925582 | Ongoing | 27000 | 0 | 2026-04-01
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5921390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129638715 | Completed | 27000 | 12000 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5921860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120988646 | Completed | 27000 | 12600 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5923025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145814900 | Ongoing | 27000 | 3600 | 2026-04-01
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5924295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120926220 | Completed | 27000 | 12000 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5924511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130986342 | Completed | 27000 | 12300 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5924622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120988904 | Completed | 27000 | 12000 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5925704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130048347 | Completed | 23490 | 0 | 2026-04-01 | 2026-08-06
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5926762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129578127 | Completed | 27000 | 2100 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5926904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120989516 | Completed | 23490 | 0 | 2026-04-01 | 2026-08-06
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5927076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106090836 | Completed | 27000 | 0 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5927240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129530980 | Completed | 27000 | 0 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5927376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120925418 | Completed | 23490 | 0 | 2026-04-01 | 2026-08-06
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5927394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114925662 | Completed | 27000 | 3600 | 2026-04-01 | 2026-09-22
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5927458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137470885 | Completed | 23490 | 0 | 2026-03-19 | 2026-09-22
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5927470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106557576 | Completed | 23490 | 0 | 2026-03-19 | 2026-08-06
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5927960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106891186 | Approved | 27000 | 0 | 2026-01-14
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/5929773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130048297 | Completed | 23490 | 0 | 2026-04-01 | 2026-08-06
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6126401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120925649 | Ongoing | 27000 | 18600 | 2026-07-04
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6130922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129638574 | Completed | 27000 | 26400 | 2026-07-04 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6132567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118684389 | Ongoing | 27000 | 24600 | 2026-07-21
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6132568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118684417 | Completed | 27000 | 26400 | 2026-07-04 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6137277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106261305 | Ongoing | 27000 | 18600 | 2026-07-04
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6144223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126771630 | Physically Completed | 27000 | 27000 | 2026-07-04 | 2026-10-09
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6144683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118345876 | Completed | 27000 | 26100 | 2026-07-04 | 2026-09-25
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6144815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130697465 | Ongoing | 27000 | 18600 | 2026-07-04
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6148063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113703969 | Completed | 27000 | 27000 | 2026-07-04 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6149753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140002566 | Completed | 27000 | 26400 | 2026-07-04 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6149754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140002618 | Completed | 27000 | 27000 | 2026-07-04 | 2026-09-25
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6149807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151163044 | Completed | 27000 | 27000 | 2026-07-04 | 2026-09-25
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6149855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129111612 | Physically Completed | 27000 | 15000 | 2026-07-04 | 2026-09-19
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6153196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125878433 | Physically Completed | 27000 | 25200 | 2026-07-04 | 2026-09-19
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6158215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149929886 | Physically Completed | 27000 | 20400 | 2026-07-04 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6159989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130048370 | Completed | 27000 | 27000 | 2026-07-03 | 2026-09-25
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6159990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130048441 | Ongoing | 27000 | 18300 | 2026-07-03
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6165710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106891057 | Ongoing | 27000 | 21600 | 2026-07-03
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6170506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129590716 | Completed | 27000 | 26700 | 2026-07-03 | 2026-09-22
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6170806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106235316 | Physically Completed | 27000 | 26100 | 2026-07-03 | 2026-10-06
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6297119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130990702 | Approved | 27000 | 0 | 2026-03-25
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005035/IF/IAY/6402275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120989313 | Approved | 27000 | 0 | 2026-01-14
KHANDWA / KHANDWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1725005035/WC/22012035245266 — Storm water drain nirman kary Surendra ke khet ke pas se fataka factory tak mundwada | Approved | 0 | 0 | 2024-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1725005035/WC/22012035301114 — gebiyan nirman kary khalil ke khet ke pas | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1725005035/WC/22012035301118 — gebiyan nirman kary kallu rashid khet ke pas | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1725005035/WC/22012035301121 — gebiyan nirman kary rahim karim ke khet ke pas | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1725005035/WC/22012035301123 — gebiyan nirman kary sartaj ismail ke khet ke pas | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1725005035/WC/22012035301126 — gebiyan nirman kary kalim rahim ke khet ke pas | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1725005035/WC/22012035301127 — gebiyan nirman kary rahman sultan ke khet ke pas | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1725005035/WC/22012035301128 — gebiyan nirman kary imran jahir ke khet ke pas | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1725005035/WC/22012035301129 — gebiyan nirman kary shohrab mehrab ke khet ke pas | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1725005035/WC/22012035301131 — gebiyan nirman kary anvar kalu ke khet ke pas | Approved | 0 | 0 | 2025-04-01