## Work List
Exported on: 2026-10-12 11:16:39
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SURGAON BANJARI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHANDWA / KHANDWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1725005056/IF/22012034776062 — पशु शेड निर्माण कार्य सुमन बाई अमान ग्राम सुरगांव बंजारी | Physically Completed | 102033.26 | 0 | 2022-04-08 | 2026-09-22
KHANDWA / KHANDWA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1725005056/IF/22012035064844 — kapil dhara kup nirman kary gendalal puran ग्राम पंचायत सुरगाव बंजारी | Ongoing | 253863.45 | 0 | 2023-06-30
KHANDWA / KHANDWA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1725005056/IF/22012035144618 — kapil dhara kup nirman kary bhim singh nemi gram pancayat surgaon banjari | Ongoing | 282417.57 | 0 | 2024-01-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1725005056/IF/22012035280366 — कपिल धारा कूप निर्माण कार्य सुशीला बाई ग्राम पंचायत सुरगांव बंजारी | Ongoing | 322434.45 | 0 | 2026-02-28
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1725005056/IF/22012035282162 — कपिल धारा कूप निर्माण कार्य vijay singh ग्राम पंचायत सुरगांव बंजारी | Approved | 267533.11 | 0 | 2024-10-02
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1725005056/IF/22012035344180 — JGJSA 2025 DUG WELL RICHARGE CHAIN SINGH SOMA KE KOOP KE PASS | Approved | 25899.46 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1725005056/IF/22012035396182 — JGJSA 2025 DUG WELL RICHARGE AMAN MALLU KE KOOP KE PASS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1725005056/IF/22012035397033 — JGJSA 2025 DUG WELL RICHARGE NARENDRA DEVRAM KE KOOP KE PASS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1725005056/IF/22012035397291 — JGJSA 2025 DUG WELL RICHARGE ANTIM RAMESH KE KOOP KE PASS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1725005056/IF/22012035497274 — JGJSA 2025 Dug well Richarge Sugar Bai Aamriya ke koop ke pass | Approved | 25899.46 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1725005056/IF/22012035497289 — JGJSA 2025 Dug well Richarge Shailendra singh Rajendra singh ke koop ke pass | Approved | 25899.46 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1725005056/IF/22012035497348 — JGJSA 2025 Dug well Richarge Kaveri Bai Gobariya ke koop ke pass | Approved | 25899.46 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1725005056/IF/22012035497381 — JGJSA 2025 Dug well Richarge Tara Bai Jagdish ke koop ke pass | Approved | 25899.46 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005056/IF/22012035541027 — Khet talab nirman karya Shobharam Rameshwar ke khet me | Approved | 0 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005056/IF/22012035541043 — Khet talab nirman karya Shankar heeralal ke khet me | Approved | 0 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1725005056/IF/22012035554391 — kapil dhra kup nirman kary saheblal natthu gram pancayat surgaon banjari | Ongoing | 267533.11 | 0 | 2026-02-22
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1725005056/IF/22012035560889 — kapil dhra kup nirman kary surprakash singh mouray gram pancayat surgaon banjari | Approved | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005056/IF/22012035584455 — Ek Bagiya Ma ke nam SHYAM BAI NAGOLE | Ongoing | 244478.26 | 5400 | 2025-09-12
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005056/IF/22012035584493 — Ek Bagiya Ma ke nam lalita bai devda | Ongoing | 280503.33 | 9000 | 2025-08-21
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005056/IF/22012035586642 — Ek Bagiya Ma ke Nam SAU BAI | Ongoing | 280503.33 | 10800 | 2025-08-23
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1725005056/IF/22012035588058 — JGJSA 2025 DUG WELL RECHASRGE JITENDRA MALVIYA KE KOOP KE PASS | Approved | 0 | 0 | 2025-06-26
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005056/IF/22012035591986 — Ek Bagiya Ma ke Nam Sapana | Ongoing | 280503.33 | 7200 | 2025-08-22
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005056/IF/22012035596430 — निजी खेत में वृक्षारोपण कार्य अंतिम उपाध्याय ग्राम पंचायत सुरगांव बंजारी | Approved | 0 | 0 | 2025-08-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005056/IF/22012035596431 — निजी खेत में वृक्षारोपण कार्य रणजीत पवार ग्राम पंचायत सुरगांव बंजारी | Approved | 0 | 0 | 2025-08-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1725005056/IF/22012035596432 — निजी खेत में वृक्षारोपण कार्य आशीष चावड़ा ग्राम पंचायत सुरगांव बंजारी | Approved | 0 | 0 | 2025-08-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005056/IF/22012035627409 — EK BAGIYA MA KE NAAM Manju Bai MP-25-005-056-001/285 | Ongoing | 199400.56 | 3600 | 2025-10-10
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005056/IF/22012035627513 — EK BAGIYA MA KE NAAM SUKMA BAI MP-25-005-056-001/94 | Ongoing | 199713.14 | 3600 | 2025-10-10
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005056/IF/22012035636675 — Ek Bagiya Ma ke Nam BASKUVAR BAI MP-25-005-056-001/247 | Ongoing | 266578.64 | 5400 | 2025-12-06
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1725005056/IF/22012035641772 — Ek Bagiya Ma ke Naam RANU BAI MP-25-005-056-001/307 | Ongoing | 266578.64 | 7200 | 2025-12-06
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1725005056/IF/22012035658411 — Kapil Dhara koop Nirman kary Shushila Bai | New | 0 | 0 | 2025-08-14
KHANDWA / KHANDWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/100945 — Construction of IAY House -IAY REG. NO. MP-25-005-056-001/127 | Approved | 27000 | 0 | 2015-11-03
KHANDWA / KHANDWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/100946 — Construction of IAY House -IAY REG. NO. MP-25-005-056-001/128 | Approved | 27000 | 0 | 2015-11-03
KHANDWA / KHANDWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/100947 — Construction of IAY House -IAY REG. NO. MP-25-005-056-001/129 | Approved | 27000 | 0 | 2015-11-03
KHANDWA / KHANDWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/100948 — Construction of IAY House -IAY REG. NO. MP-25-005-056-001/159 | Approved | 27000 | 0 | 2015-11-03
KHANDWA / KHANDWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/100949 — Construction of IAY House -IAY REG. NO. MP-25-005-056-001/167 | Approved | 27000 | 0 | 2015-11-03
KHANDWA / KHANDWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/135030 — Construction of IAY House -IAY REG. NO. MP-25-005-056-001/0123 | Approved | 27000 | 0 | 2016-02-15
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/3710849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117853245 | Completed | 23490 | 0 | 2024-12-04 | 2026-09-07
KHANDWA / KHANDWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/3750365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119312534 | Approved | 27000 | 0 | 2022-05-02
KHANDWA / KHANDWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/3761882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116522728 | Approved | 27000 | 0 | 2022-05-02
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/4584058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119617119 | Ongoing | 27000 | 0 | 2025-02-04
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/4608187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124990698 | Approved | 27000 | 0 | 2024-09-11
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/4703078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121358912 | Ongoing | 27000 | 7200 | 2024-12-04
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/4708825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124269085 | Approved | 27000 | 0 | 2024-09-19
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/4755795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117850390 | Ongoing | 27000 | 7200 | 2024-12-06
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5505639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124268430 | Completed | 23490 | 16800 | 2025-10-12 | 2026-09-22
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5506363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116546441 | Completed | 23490 | 7500 | 2025-07-01 | 2026-09-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5506978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115912227 | Ongoing | 27000 | 11100 | 2025-10-12
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5508140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125557944 | Completed | 23490 | 0 | 2025-07-08 | 2026-09-08
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5510450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126286886 | Approved | 27000 | 0 | 2025-02-13
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5510780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124298405 | Ongoing | 27000 | 5700 | 2025-10-12
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5511564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125876730 | Ongoing | 27000 | 9000 | 2025-10-12
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5512375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114130862 | Ongoing | 27000 | 9000 | 2026-08-25
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5512736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121873016 | Completed | 23490 | 0 | 2025-10-12 | 2026-09-08
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5534921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125817759 | Ongoing | 27000 | 9000 | 2025-10-12
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5535082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115909089 | Completed | 23490 | 0 | 2025-08-04 | 2026-09-08
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5536961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121431471 | Completed | 23490 | 0 | 2025-07-08 | 2026-09-08
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5537082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116552805 | Completed | 27000 | 18900 | 2025-10-12 | 2026-09-15
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5576709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121355055 | Ongoing | 27000 | 7200 | 2025-10-12
KHANDWA / KHANDWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/5670728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116563303 | Completed | 23490 | 0 | 2025-10-12 | 2026-09-08
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/6059192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115929480 | Approved | 27000 | 0 | 2025-01-21
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/6060385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117848545 | Physically Completed | 23490 | 0 | 2024-09-22 | 2026-07-12
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/6071092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114126753 | Physically Completed | 23490 | 0 | 2025-02-13 | 2026-07-26
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/6071184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114159665 | Physically Completed | 27000 | 14400 | 2026-08-09 | 2026-10-04
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/6071194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114165090 | Approved | 27000 | 0 | 2025-02-13
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/6073568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115925949 | Approved | 27000 | 0 | 2025-02-13
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/6073576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115931576 | Ongoing | 27000 | 19800 | 2026-08-12
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/6079450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119666542 | Ongoing | 27000 | 18000 | 2026-08-12
KHANDWA / KHANDWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/6079452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119667198 | Physically Completed | 23490 | 0 | 2025-02-23 | 2026-07-12
KHANDWA / KHANDWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1725005056/IF/IAY/6080445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120686708 | Ongoing | 27000 | 3600 | 2026-08-25
KHANDWA / KHANDWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1725005056/RC/22012034827466 — Strom drain water Urmila bai ke khet se Krish kumar ke khet ki taraf | Approved | 0 | 0 | 2024-08-16
KHANDWA / KHANDWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1725005056/RC/22012034827467 — Strom drain water Krish kumar ke khet se Umen Darbar ke khet ki taraf | Approved | 0 | 0 | 2024-08-16
KHANDWA / KHANDWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1725005056/RC/22012034837741 — CC ROAD NIRMAN KARY PRAHLAD KE GHAR SE KASHINATH KE GHAR KI OUR | Approved | 41989 | 0 | 2025-01-26
KHANDWA / KHANDWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1725005056/RC/22012034841804 — सी सी रोड निर्माण कार्य मयाराम के घर से चैन सिंह के घर की ओर | New | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1725005056/RC/22012034842000 — CC Road Nirman karya Mayaram ke ghar se Chain singh kr ghar ki taraf | Approved | 0 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1725005056/RC/22012034842002 — CC Road Nirman karya Mayaram ke ghar se Chain sing | Approved | 0 | 0 | 2025-04-14
KHANDWA / KHANDWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1725005056/RC/22012034842003 — CC Road Nirman karya Mayaram ke ghar se Chain sing | Approved | 40222 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1725005056/RC/22012034842006 — CC Road Nirman karya Prahlad ke ghar se Kashiram Yadav ke ghar ki taraf | Approved | 41989 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1725005056/WC/22012035262529 — JGJSA 2025 DUG WELL RECHASRGE SITARAM KE KOOP KE PASS | Approved | 25899.46 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1725005056/WC/22012035262538 — JGJSA 2025 DUG WELL RECHASRGE SEETARAM SHOBHRAM KE KOOP KE PASS | Deleted | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1725005056/WC/22012035280746 — JGJSA 2025 DUG WELL RICHARGE SHYAMLAL RAGHUNATH KE KOOP KE PASS | Deleted | 0 | 0 | 2025-04-01
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1725005056/WC/22012035328489 — Parcolarion Tank Surgaonbanjari | New | 0 | 0 | 2026-01-24
KHANDWA / KHANDWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1725005056/WC/22012035328490 — Pokhar nirman karya Surgaonbanjari | Approved | 1398839.7 | 0 | 2026-01-24