## Work List
Exported on: 2026-09-07 23:32:48
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KHOKHEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RAJGARH / KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1726002058/IC/22012034892957 — Construction of irrigation open well kalaji Maharaj ke pass gram kalakundal gp Khokheda | New | 0 | 0 | 2025-11-08
RAJGARH / KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1726002058/IF/22012034765541 — HITESHI KAPILDHARA KUP NIRMAN KARYA_KALUSINGH S/O DEVSINGH GRAM KHOKHEDA | Ongoing | 247839.67 | 0 | 2023-05-16
RAJGARH / KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1726002058/IF/22012035058912 — hiteshi kapil dhara kup nirman karya unkarlal s/o nanda ji gram kalakundal | Ongoing | 271795.94 | 0 | 2023-04-18
RAJGARH / KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1726002058/IF/22012035072434 — hiteshi kapil dhara kup nirman biram singh s/o jagnnath gram khokheda | Ongoing | 271795.94 | 0 | 2023-04-25
RAJGARH / KHILCHIPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726002058/IF/22012035314508 — JGSA_Khet Talab_gopilal s/o ramlal _GP khokheda | Approved | 138854.17 | 0 | 2025-01-26
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1726002058/IF/22012035352803 — JGSA_khet talab ray Singh s/o bherulal GP_Khokheda | Approved | 147621.16 | 0 | 2025-04-01
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726002058/IF/22012035377138 — JGSA_Khet_Talab_Karan singh So Gopal_Gram Kalakundal GP Khokheda | New | 0 | 0 | 2025-04-14
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6176848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115663675 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6177253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106909347 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6177333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115636450 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6178531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117872271 | Ongoing | 27000 | 8400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6178911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106197019 | Ongoing | 27000 | 8400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6178967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118069338 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6180605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106959824 | Ongoing | 27000 | 0 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6181322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115646547 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6182558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118332869 | Approved | 27000 | 0 | 2026-03-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6183010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115174769 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6183423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115426673 | Ongoing | 27000 | 8400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6185006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100891123 | Ongoing | 27000 | 8400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6187445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115632499 | Ongoing | 27000 | 10800 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6189192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115874066 | Ongoing | 27000 | 0 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6189263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100538050 | Ongoing | 27000 | 14700 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6189909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113948234 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6191469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115380181 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6192400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122074716 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6192993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115620752 | Approved | 27000 | 0 | 2026-03-07
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6193686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115641157 | Approved | 27000 | 0 | 2026-03-07
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6193931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114715832 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6194581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113933364 | Approved | 27000 | 0 | 2026-03-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6195305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115797420 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6196793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100539994 | Approved | 27000 | 0 | 2026-03-10
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6198203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115407781 | Approved | 27000 | 0 | 2026-03-07
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6198537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115812867 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6199024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117922926 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6200036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115653739 | Ongoing | 27000 | 8400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6200318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113991360 | Ongoing | 27000 | 14700 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6200559 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115244264 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6201182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115813291 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6202911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147179134 | Ongoing | 27000 | 0 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6203206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100539392 | Ongoing | 27000 | 8400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6205560 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115803480 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6205978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115429212 | Ongoing | 27000 | 8400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6207518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127456025 | Ongoing | 27000 | 8400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6208243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106912644 | Ongoing | 27000 | 8400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6210486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115660835 | Ongoing | 27000 | 13500 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6210855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115405020 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6211472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115664245 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6211794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113899240 | Ongoing | 27000 | 4200 | 2026-07-10
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6212138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113954751 | Approved | 27000 | 0 | 2026-03-07
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6212484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115809796 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6213820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115181206 | Ongoing | 27000 | 0 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6215171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117874332 | Ongoing | 27000 | 14400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6215504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115654561 | Ongoing | 27000 | 14700 | 2026-07-10
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6215888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115798208 | Approved | 27000 | 0 | 2026-03-07
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6217415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106191267 | Ongoing | 27000 | 8400 | 2026-07-10
RAJGARH / KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002058/IF/IAY/6376565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113859074 | Approved | 27000 | 0 | 2026-08-07
RAJGARH / KHILCHIPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1726002058/RC/22012034627126 — SUDUR SADAK_2022-23_KHOKHEDA SE AMARIT SAROVAR TALAB TAK GRAM KHOKHEDA | Ongoing | 1498509.96 | 0 | 2023-02-28
RAJGARH / KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1726002058/WC/22012035273308 — JGSA_ Dug well recharge pit _Shamshan Ke Pass_Gram Kalakundal GP Khokheda | Approved | 0 | 0 | 2025-04-14
RAJGARH / KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1726002058/WC/22012035273321 — JGSA_ Dug well recharge pit _Gaav Ke Niche_Gram Gulkhedi GP Mokampura | Approved | 0 | 0 | 2025-04-14
RAJGARH / KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726002058/WC/22012035323833 — Construction of ardhan band parcoletion tank balda ki khoyari gram piplya gp khokheda | Ongoing | 1468073.37 | 0 | 2026-02-26