## Work List
Exported on: 2026-10-24 15:16:44
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KULIKHEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RAJGARH / KHILCHIPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1726002060/DP/22012034408092 — SARVAJANIK KUP TALAB KA PASS KULIKHEDA | Ongoing | 535000 | 0 | 2020-04-22
RAJGARH / KHILCHIPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coast Line Plantation of Forestry Trees for Comm / Along the coast Block Plantation of Sericulture Trees for Community | Plantation | 1726002060/DP/22012034533676 — PALANTATION BAJI MAHRAJ KE BALDI MOTIPURA GP KULIKHEDA | Ongoing | 394489.84 | 0 | 2021-09-21
RAJGARH / KHILCHIPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1726002060/DP/22012034592406 — Vashudha_Vandhana_2023-24_ Kulikheda | Ongoing | 55847.4 | 0 | 2023-10-13
RAJGARH / KHILCHIPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1726002060/FP/22012034640524 — JGSA_NALA DESILTING FEEDER CHANNEL GADGANGA NADI ME GHAT KE PASS 2024-25 GRAM KULIKHEDA_GP_KULIKHEDA | Approved | 0 | 0 | 2024-06-08
RAJGARH / KHILCHIPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fish Drying Yards for Community / Construction of Fish Drying Yard for Community | Construction of Fish Drying Infrastructure | 1726002060/FR/22012034322960 — Construction of Fish Dryingh Yards for Community gad ganga nadi ke paas kulikheda 2024 2025 | New | 0 | 0 | 2024-11-20
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of Water Courses and Field Channels for Community | Construction of Canal | 1726002060/IC/22012034885850 — Construction of irrigation open well for community Gadganga nadi ke pass_2024-25_Gram Kulikheda | Ongoing | 558651.97 | 300 | 2024-12-02
RAJGARH / KHILCHIPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1726002060/IF/22012034407039 — hithse kapildara balchand / bardichand kulikheda | Ongoing | 210000 | 0 | 2018-06-19
RAJGARH / KHILCHIPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1726002060/IF/22012034407041 — HIThsi KAPILDHARA JASWANT / BAGWANSINGH MOTIPURA | Ongoing | 210000 | 0 | 2018-06-19
RAJGARH / KHILCHIPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1726002060/IF/22012034414595 — HITHSE KAPILDHARA SIVECHARAN / RATANLAL KULIKHEDA | Ongoing | 210000 | 0 | 2018-06-19
RAJGARH / KHILCHIPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726002060/IF/22012034637578 — RFR GADGANGA KAT TALAB JAGDISH S/O BAWARLAL | Ongoing | 332962.02 | 0 | 2021-06-26
RAJGARH / KHILCHIPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726002060/IF/22012034637580 — RFR GADGANGA KAT TALAB RAISINGH S/O BAWARLAL | Ongoing | 332962.02 | 0 | 2021-06-30
RAJGARH / KHILCHIPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726002060/IF/22012034637590 — RFR GADGANGA KHAT TALAB SHIVNARAYAN S/O NANDLAL | Ongoing | 332962.02 | 0 | 2021-06-26
RAJGARH / KHILCHIPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1726002060/IF/22012034637600 — HITESHI KUP SANJAY S/O JAGDISH | Ongoing | 246126.86 | 0 | 2021-06-26
RAJGARH / KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1726002060/IF/22012035072533 — hiteshi kapil dhara kup nirman guruprasad pita madan lal | Ongoing | 272395.94 | 0 | 2023-05-03
RAJGARH / KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Agro Forestry Block Plantation for Individual | Plantation | 1726002060/IF/22012035142164 — NIJI KHET ME NANDAN FLODHYAN RAMESHWAR S/o RADHESHYAM GP KULIKHEDA GRAM MOTIPURA | Ongoing | 161200 | 0 | 2023-12-07
RAJGARH / KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Agro Forestry Block Plantation for Individual | Plantation | 1726002060/IF/22012035142168 — NIJI KHET ME NANDAN FLODHYAN CHAMPALAL S/o Narasng GP kulikheda | Ongoing | 161200 | 0 | 2023-10-05
RAJGARH / KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Agro Forestry Block Plantation for Individual | Plantation | 1726002060/IF/22012035142173 — NIJI KHET ME NANDAN FLODHYAN BABLU S/o MOTILAL GP kulikheda | Ongoing | 161200 | 0 | 2023-10-05
RAJGARH / KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Agro Forestry Block Plantation for Individual | Plantation | 1726002060/IF/22012035142175 — NIJI KHET ME NANDAN FLODHYAN BADRILAL S/o DEVSINGH GP kulikheda | Ongoing | 161200 | 0 | 2023-10-05
RAJGARH / KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Agro Forestry Block Plantation for Individual | Plantation | 1726002060/IF/22012035142178 — NIJI KHET ME NANDAN FLODHYAN HAJARILAL S/o RADHESHYAM GP kulikheda | Ongoing | 161200 | 0 | 2023-10-05
RAJGARH / KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Agro Forestry Block Plantation for Individual | Plantation | 1726002060/IF/22012035142179 — NIJI KHET ME NANDAN FLODHYAN BHAGIRATH S/o KASHIRAM GP kulikheda | Ongoing | 161200 | 0 | 2023-10-05
RAJGARH / KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Agro Forestry Block Plantation for Individual | Plantation | 1726002060/IF/22012035143398 — NIJI KHET ME NANDAN FLODHYAN SHIVNARAYAN S/o MANGILAL GP kulikheda | Ongoing | 161200 | 0 | 2023-12-15
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726002060/IF/22012035252463 — Perkolation tank nirman 2024-25 Rajpalsingh/Bhagwansingh gram panchayat kulikheda | Ongoing | 219983.91 | 0 | 2025-05-20
RAJGARH / KHILCHIPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1726002060/IF/22012035273101 — Hiteshi kapildhara kup nirman Rambabu /radheshyam Gram Kulikheda | Approved | 0 | 0 | 2024-11-20
RAJGARH / KHILCHIPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1726002060/IF/22012035273104 — Hiteshi kapildhara kup nirman Shivnarayan/ motilal Gram Kulikheda | Approved | 0 | 0 | 2024-11-20
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726002060/IF/22012035314644 — JGSA_khet talab nirman_Shivprasad_prabhulal_ Gram Kulikheda | Ongoing | 175411.12 | 0 | 2025-05-11
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726002060/IF/22012035314655 — JGSA_khet talab nirman_bablu_motilal_ Gram Kulikheda | Ongoing | 175411.12 | 0 | 2025-05-10
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726002060/IF/22012035314661 — JGSA_khet talab nirman_radheshyam_kanheyalal_ Gram Kulikheda | Ongoing | 175411.12 | 0 | 2025-05-11
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726002060/IF/22012035314668 — JGSA_khet talab nirman_shankarlal_madhulal_Gram Kulikheda | Ongoing | 175411.12 | 0 | 2025-05-10
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726002060/IF/22012035501136 — JGSA_Khet talab shivanrayan motilal gram kulikheda GP kulikheda | Approved | 185441.45 | 0 | 2025-05-10
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726002060/IF/22012035501148 — JGSA_Khet talab narayan bhawarji gram kulikheda GP kulikheda | Approved | 185441.45 | 0 | 2025-05-10
RAJGARH / KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726002060/IF/22012035501158 — JGSA_Khet talab Jagdish bhagirath gram kulikheda GP kulikheda | Approved | 185441.45 | 0 | 2025-05-10
RAJGARH / KHILCHIPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726002060/IF/IAY/3258283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3547211 | Ongoing | 27000 | 0 | 2024-10-14
RAJGARH / KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726002060/IF/IAY/4040955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118054029 | Ongoing | 27000 | 0 | 2023-11-09
RAJGARH / KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1726002060/LD/22012034947509 — Construction of stone peripheral bund for community- shantidham_parisar_kulikheda - GP kulikheda | Ongoing | 326188.52 | 0 | 2025-07-03
RAJGARH / KHILCHIPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1726002060/RC/22012034671939 — Puliya nirman kary _ Men Rode Se Kundhi Tak _2023-24 Gram Kulikheda-GP Kulikheda | Ongoing | 1482454.53 | 0 | 2024-01-18
RAJGARH / KHILCHIPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1726002060/RC/22012034838221 — Nali nirman kary Harijan Basti me men road Nale se Biram verma ke ghar tak kulikheda | Approved | 59000 | 0 | 2025-01-26
RAJGARH / KHILCHIPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1726002060/RC/22012034838527 — CC ROAD NIRMAN KARY men road se shivsingh ke makan ki or gram kulikheda | Approved | 49063 | 0 | 2025-01-26
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1726002060/WC/22012035226960 — Earthen bund percolation tank-baji Maharaj ke sthan ke pass_gram-Kulikheda_GP-KULIKHEDA | Approved | 0 | 0 | 2024-11-06
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1726002060/WC/22012035229714 — Construction of mini_perkolation_tank-Baji Maharaj ke sthan par_GP kulikheda | Ongoing | 469757.4 | 0 | 2025-01-06
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1726002060/WC/22012035229719 — Construction of continuous_contour_trench for community Motipura_ki_baldi_par GP kulikheda | Approved | 824178.44 | 0 | 2024-11-10
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1726002060/WC/22012035230381 — Naveen Talab nirman karya movdi wali khoyri Gram kulikheda GP kulikheda | New | 0 | 0 | 2024-11-20
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1726002060/WC/22012035230382 — Naveen Talab nirman karya movdi wali khoyri Gram kulikheda GP kulikheda | New | 0 | 0 | 2024-11-20
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1726002060/WC/22012035230383 — Naveen Talab nirman karya movdi wali khoyri Gram kulikheda GP kulikheda | New | 0 | 0 | 2024-11-20
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1726002060/WC/22012035230384 — Naveen Talab nirman karya movdi wali khoyri Gram kulikheda GP kulikheda | New | 0 | 0 | 2024-11-20
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1726002060/WC/22012035230385 — Naveen Talab nirman karya movdi wali khoyri Gram kulikheda GP kulikheda | Approved | 0 | 0 | 2024-11-20
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1726002060/WC/22012035248401 — Naveen talab nirman karya - Movdi ke pass kulikheda - GP_kulikheda | Approved | 0 | 0 | 2024-12-22
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1726002060/WC/22012035254701 — Construction of water harvesting pond_2024-25_Talab ke peeche ki or_Gram Kulikheda | Approved | 0 | 0 | 2025-03-15
RAJGARH / KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1726002060/WC/22012035309275 — Construction of dyke_work Odi ke pass Ki Khali_Gram kulikheda GP kulikheda | Ongoing | 254512.44 | 0 | 2025-07-03
RAJGARH / KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1726002060/WC/22012035316007 — Earthen Bund perkolation tank- Bade talab ke raste par - Gram Kulikheda GP Kulikheda | Approved | 0 | 0 | 2025-04-01
RAJGARH / KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1726002060/WC/22012035316008 — Earthen Bund perkolation tank-Mowdi ke_pass - Gram Kulikheda GP Kulikheda | Approved | 0 | 0 | 2025-06-01
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1726002060/WH/22012034939785 — NGA_Stopdam Renovation Gadganga Nadi Par Gram Kulikheda 2024_25 Gram Panchayat Kulikheda | Approved | 0 | 0 | 2024-06-06
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1726002060/WH/22012034939786 — NGA_Checkdam Renovation Bakhediya khal me Gram Kulikheda 2024_25 Gram Panchayat Kulikheda | Approved | 0 | 0 | 2024-06-05
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1726002060/WH/22012034939787 — NGA_Talab Renovation Work Purana Bada Talab Gram Kulikheda_2024-25 GP Kulikheda | Approved | 0 | 0 | 2024-06-06
RAJGARH / KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1726002060/WH/22012034939788 — NGA_Stop Dam Renovation Motipura ke Pas Nadi me Gram Kulikheda_2024-25 GP Kulikheda | Approved | 0 | 0 | 2024-06-06