## Work List
Exported on: 2026-09-08 19:14:26
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JALALPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RAJGARH / RAJGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1726003032/AV/22012034533804 — GOSHALA_2020-21_GP_JALALPURA | Ongoing | 3784582.21 | 0 | 2020-09-17
RAJGARH / RAJGARH | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1726003032/AV/22012034668413 — SHANTIDHAM NIRMAN KARYA_2025-26_GRAM KASTURIPURA_GP JALALPURA | Approved | 237790.04 | 0 | 2025-10-02
RAJGARH / RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1726003032/IC/22012034890811 — SARVJANIK PAYJAL KOOP NIRMAN_2025-26_SHASKIYA GOUSHALA ME_GRAM JALALPURA_GP JALALPURA | Approved | 605674.76 | 0 | 2025-04-14
RAJGARH / RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1726003032/IC/22012034892904 — SARVAJANIK PAYJAL KOOP NIRMAN KARYA_2025-26_DILIP KE GHAR KE PASS_GRAM JOGIDATA_GP JALALPURA | Ongoing | 605674.69 | 0 | 2026-02-14
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1726003032/IC/22012034892988 — SARVAJANIK KOOP NIRMAN KARYA_2025-26_GOSWAMI SHAMSAN KE PASS_GRAM JALALPURA_GP JALALPURA | Ongoing | 605674.69 | 0 | 2026-05-19
RAJGARH / RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1726003032/IC/22012034893056 — SARVAJANIK PAYJAL KOOP NIRMAN KARYA_2025-26_LEEMDI CHOURAHE PER_GRAM KESARPURA_GP JALALPURA | New | 0 | 0 | 2025-10-02
RAJGARH / RAJGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/4307856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126323052 | Ongoing | 27000 | 0 | 2022-08-04
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6123568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126001316 | Ongoing | 27000 | 3000 | 2026-07-22
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6123570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126001665 | Ongoing | 27000 | 12000 | 2026-04-21
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6124333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126450384 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6125685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126342160 | Ongoing | 27000 | 0 | 2026-07-10
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6125938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126676304 | Physically Completed | 27000 | 7800 | 2026-04-21 | 2026-09-06
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6125939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126682108 | Ongoing | 27000 | 6000 | 2026-04-21
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6129231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121565211 | Ongoing | 27000 | 9000 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6131190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123885505 | Ongoing | 27000 | 0 | 2026-04-26
RAJGARH / RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6135408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125889906 | Approved | 27000 | 0 | 2026-02-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6135478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126220213 | Physically Completed | 27000 | 0 | 2026-04-21 | 2026-09-06
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6136953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123410193 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6138759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123866462 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6138763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123869881 | Ongoing | 27000 | 3000 | 2026-04-21
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6139060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125681314 | Ongoing | 27000 | 0 | 2026-04-21
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6139613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138738046 | Ongoing | 27000 | 6000 | 2026-08-03
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6139814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126047896 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6139820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126054883 | Physically Completed | 27000 | 7800 | 2026-04-28 | 2026-09-06
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6140185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149767523 | Ongoing | 27000 | 9000 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6140538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123861057 | Ongoing | 27000 | 9000 | 2026-06-03
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6143343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125894115 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6146729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149767121 | Ongoing | 27000 | 9000 | 2026-04-21
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6146730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149768194 | Ongoing | 27000 | 6000 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6146731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149768258 | Ongoing | 27000 | 3000 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6148537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125354807 | Ongoing | 27000 | 3000 | 2026-07-22
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6148716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123890096 | Ongoing | 27000 | 0 | 2026-06-03
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6148995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123880364 | Physically Completed | 23490 | 0 | 2026-04-28 | 2026-08-02
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6149161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126217965 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6149255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151657562 | Ongoing | 27000 | 3000 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6149261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151697324 | Ongoing | 27000 | 3000 | 2026-06-03
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6149262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151697401 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6149263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151697622 | Ongoing | 27000 | 3000 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6149264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151709396 | Physically Completed | 27000 | 5100 | 2026-04-28 | 2026-09-06
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6149794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150058793 | Physically Completed | 23490 | 5100 | 2026-04-28 | 2026-08-09
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6149795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150059209 | Ongoing | 27000 | 0 | 2026-06-03
RAJGARH / RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6150799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126294362 | Approved | 27000 | 0 | 2026-02-19
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6151465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126338087 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6151477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125679306 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6152366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125412277 | Physically Completed | 23490 | 5100 | 2026-04-28 | 2026-08-09
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6155076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125684598 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6155746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126014538 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6157100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126453646 | Ongoing | 27000 | 6000 | 2026-06-03
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6157769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125676797 | Ongoing | 27000 | 0 | 2026-06-03
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6159632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125622299 | Ongoing | 27000 | 0 | 2026-09-08
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6159642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125632853 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6160300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151711157 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6162950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126209206 | Physically Completed | 27000 | 0 | 2026-04-28 | 2026-09-06
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6163292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125664447 | Ongoing | 27000 | 3000 | 2026-07-22
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6163556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133078001 | Ongoing | 27000 | 6000 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6163980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126219408 | Physically Completed | 27000 | 7200 | 2026-04-28 | 2026-09-06
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6164977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126315205 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6164983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126320820 | Physically Completed | 23490 | 7800 | 2026-04-28 | 2026-08-16
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6165224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126323339 | Ongoing | 27000 | 6000 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6170631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123883071 | Ongoing | 27000 | 9000 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6173385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126336231 | Ongoing | 27000 | 0 | 2026-04-28
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6177712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119796231 | Ongoing | 27000 | 0 | 2026-07-10
RAJGARH / RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/6191145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149767307 | Ongoing | 27000 | 12000 | 2026-07-10
RAJGARH / RAJGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003032/IF/IAY/932107 — Construction of IAY House -IAY REG. NO. MP2654668 | Approved | 27000 | 0 | 2020-07-01
RAJGARH / RAJGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1726003032/RC/22012034553110 — APPROCH ROAD_2020-21_JALALPURA_JOGIDATA GRAM SE SHAMSAN TAK | Ongoing | 676404.48 | 0 | 2021-02-02
RAJGARH / RAJGARH | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1726003032/RC/22012034842344 — CC ROAD NIRMAN KARYA_2025-26_GOUSHALA PARISAR_GRAM JALALPURA_GP JALALPURA | Approved | 68909 | 0 | 2025-04-14
RAJGARH / RAJGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1726003032/WC/22012035210973 — JGSA Mini Percoletion Tank Gow Shala ke Pass 2024-25 Gram Jalalpura GP Jalalpura | Approved | 198563.25 | 0 | 2024-06-10
RAJGARH / RAJGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726003032/WC/22012035324612 — WATER HARVESTING POND_2025-26_KHEMRAJ KE KHET KE PASS_GRAM KASTURIPURA_GP JALALPURA | Approved | 0 | 0 | 2025-10-02
RAJGARH / RAJGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726003032/WC/22012035324613 — WATER HARVESTING POND_2025-26_MOHANSINGH KE KHET KE PASS_GRAM KASTURIPURA_GP JALALPURA | Ongoing | 947414.56 | 0 | 2026-02-04
RAJGARH / RAJGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726003032/WC/22012035326118 — WATER HARVESTING POND_2025-26_BAJESINGH KE KHET KE PASS_GRAM KASTURIPURA_GP JALALPURA | Ongoing | 934916.85 | 0 | 2026-02-04
RAJGARH / RAJGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726003032/WC/22012035326120 — NAVIN TALAB NIRMAN KARYA_2025-26_KHUSHALSINGH KE KHET KE PASS_GRAM KASTURIPURA_GP JALALPURA | Approved | 0 | 0 | 2025-10-02
RAJGARH / RAJGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1726003032/WC/VB/22012035331966 — Boulder Check Dam_2026-27_Mandir ke pass wale nale par Gram Jogidata_GP_Jalalpura | Approved | 70698.95 | 0 | 2026-07-28
RAJGARH / RAJGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1726003032/WH/22012034449079 — CTR_TALAB JIRNODDHAR_2021-22_JALALPURA_GRAM KUNDIBEH | Ongoing | 875270.72 | 0 | 2021-11-10
RAJGARH / RAJGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1726/RC/22012034560175 — Aproch Road_Kundibe School to Kankad Tak Gram Jalalpura Panchayat Jalalpura (RES) | Ongoing | 2723000 | 0 | 2021-03-05
RAJGARH / RAJGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1726/RC/22012034615368 — Regraveling work at A.B. Road to Kasturipura (RES) | Ongoing | 285000 | 0 | 2022-12-01