## Work List
Exported on: 2026-09-08 08:49:10
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KOTRA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RAJGARH / NARSINGHGARH | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1726006069/AV/22012034604746 — Sbm_segregation shed_ bus stand k paas_2021-22_gp_kotra | Physically Completed | 597999.66 | 0 | 2021-11-09 | 2026-08-16
RAJGARH / NARSINGHGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1726006069/DP/22012034566541 — Vraksha Ropan Karya Panchayat bhawan parisar Kotra | Ongoing | 409718.19 | 0 | 2022-11-30
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1726006069/IC/22012034892999 — Construction Of Irrigation Open Well For Community Shantidham Parisar_2025-26_GP_Kotra | Approved | 605674.69 | 0 | 2025-08-15
RAJGARH / NARSINGHGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1726006069/IF/22012035045395 — Parcolation Tank Nirman Karya Ram Prasad / Gor Lal | Ongoing | 293997.57 | 0 | 2023-10-07
RAJGARH / NARSINGHGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1726006069/IF/22012035098019 — hiteshi kup nirman karya Sarjan singh /maan singh | Ongoing | 280883.3 | 0 | 2023-10-07
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/203409 — Construction of IAY House -IAY REG. NO. MP-26-006-069-002/07 | Ongoing | 27000 | 0 | 2026-01-20
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/203410 — Construction of IAY House -IAY REG. NO. MP-26-006-069-002/11A | Ongoing | 27000 | 0 | 2026-02-17
RAJGARH / NARSINGHGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/3325788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3299156 | Ongoing | 27000 | 0 | 2026-06-11
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/4967389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127027392 | Ongoing | 27000 | 0 | 2025-05-25
RAJGARH / NARSINGHGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/5153323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127407006 | Approved | 27000 | 0 | 2025-02-24
RAJGARH / NARSINGHGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/5188487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128363691 | Approved | 27000 | 0 | 2025-02-25
RAJGARH / NARSINGHGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/5231640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127407404 | Approved | 27000 | 0 | 2025-02-25
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6176132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127408998 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6176368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127405776 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6179695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149864970 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6182096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125408599 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6183301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127713667 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6183874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126952931 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6184641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126963085 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6185391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127017641 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6187331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127017127 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6189877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127006683 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6191740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130338841 | Ongoing | 27000 | 0 | 2026-09-01
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6192319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126352526 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6192328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144409733 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6193309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132084773 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6193736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124554644 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6193857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125416374 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6196967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132084792 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6198685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149864975 | Ongoing | 27000 | 4200 | 2026-08-17
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6198994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127031235 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6199067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125413295 | Ongoing | 27000 | 9000 | 2026-07-06
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6199703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126405755 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6199798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126975899 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6200364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126957136 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6203319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127443746 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6205246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127408523 | Ongoing | 27000 | 0 | 2026-09-01
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6206821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125420279 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6207423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126397035 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6210634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126351720 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6211875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127407807 | Ongoing | 27000 | 9000 | 2026-07-30
RAJGARH / NARSINGHGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6212030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125417969 | Ongoing | 27000 | 4200 | 2026-07-06
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6212734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132084729 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6213731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126346991 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6213812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128040348 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6214418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127030819 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726006069/IF/IAY/6215144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126969654 | Approved | 27000 | 0 | 2026-02-27
RAJGARH / NARSINGHGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1726006069/WC/22012035245169 — Parcolation Tank Nirman Karya Shanti Dham k Pass Kotra | Approved | 199173.86 | 0 | 2024-10-02
RAJGARH / NARSINGHGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726006069/WC/22012035249298 — Construction Water Harvesting Pond Shantidham Ke Pass Gram Kotra_Gp_Kotra_2024-25 | Approved | 989186.43 | 0 | 2025-01-25