## Work List
Exported on: 2026-10-26 12:52:33
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Moondarasagar
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
VIDISHA / LATERI | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1727001038/AV/VB/YD/22012034669943 — Construction of Crematorium for 1 moodrasagar | New | 0 | 0 | 2026-10-02
VIDISHA / LATERI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1727001038/DP/22012034595088 — Amrit vatika kariya School ke paas Mohabbatpur Gp Mundra sagar | Ongoing | 55847.4 | 0 | 2023-09-20
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1727001038/IF/22012035640260 — एक बगिया माँ के नाम तुलसा SHG हितग्राही शोभाबाई/हीरालाल ग्राम मदनखेड़ी ग्राम पंचायत मूडरासागर | Ongoing | 264661.6 | 0 | 2026-04-29
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1727001038/IF/22012035662819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100679609 | Ongoing | 23490 | 0 | 2026-05-30
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1727001038/IF/22012035662824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125061768 | Ongoing | 23490 | 0 | 2026-06-01
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1727001038/IF/22012035662825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100023195 | Ongoing | 23490 | 0 | 2026-06-05
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1727001038/IF/22012035662826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124213875 | Ongoing | 23490 | 0 | 2026-06-01
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1727001038/IF/22012035662827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124244307 | Ongoing | 23490 | 0 | 2026-06-01
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1727001038/IF/22012035662828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125619092 | Ongoing | 23490 | 0 | 2026-06-05
VIDISHA / LATERI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/4608825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125095866 | Completed | 27000 | 4200 | 2024-09-23 | 2026-10-13
VIDISHA / LATERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/4958364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123196054 | Ongoing | 27000 | 6600 | 2025-04-23
VIDISHA / LATERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/4958365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123196315 | Ongoing | 27000 | 6600 | 2025-04-07
VIDISHA / LATERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/4958378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123204558 | Ongoing | 27000 | 6600 | 2025-04-07
VIDISHA / LATERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/4962237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125818848 | Ongoing | 27000 | 6600 | 2025-04-07
VIDISHA / LATERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/4962690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126451654 | Ongoing | 27000 | 6600 | 2025-04-07
VIDISHA / LATERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5642365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121446537 | Ongoing | 27000 | 4200 | 2025-07-30
VIDISHA / LATERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5769329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132660450 | Ongoing | 27000 | 6600 | 2025-09-08
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5903306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125357353 | Physically Completed | 27000 | 22500 | 2026-07-27 | 2026-10-18
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5904242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125812035 | Physically Completed | 27000 | 9000 | 2026-05-07 | 2026-10-25
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5904300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124200073 | Physically Completed | 27000 | 8400 | 2026-04-22 | 2026-10-23
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5904466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125782692 | Ongoing | 27000 | 9000 | 2026-06-01
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5904505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124212626 | Ongoing | 27000 | 9000 | 2026-07-27
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5904721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126448982 | Physically Completed | 27000 | 12600 | 2026-04-22 | 2026-10-18
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5905472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124214505 | Ongoing | 27000 | 9000 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5905813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125512691 | Ongoing | 27000 | 9300 | 2026-06-17
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5905850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125059504 | Ongoing | 27000 | 13500 | 2026-06-01
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5905886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125819363 | Physically Completed | 27000 | 15300 | 2026-04-22 | 2026-10-18
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5906097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125091128 | Ongoing | 27000 | 4200 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5906681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125058728 | Ongoing | 27000 | 4200 | 2026-05-07
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5906752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125092106 | Ongoing | 27000 | 13500 | 2026-05-12
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5907079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125074292 | Ongoing | 27000 | 12000 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5907627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125370464 | Completed | 27000 | 9900 | 2026-04-15 | 2026-10-13
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5907794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125072224 | Ongoing | 27000 | 12600 | 2026-06-01
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5909253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122862304 | Ongoing | 27000 | 8700 | 2026-06-01
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5910776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144075019 | Physically Completed | 27000 | 11700 | 2026-04-22 | 2026-10-23
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5910926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125660549 | Ongoing | 27000 | 12000 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5911102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125111873 | Ongoing | 27000 | 8700 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5911726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124972576 | Ongoing | 27000 | 9300 | 2026-05-02
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5912418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123326651 | Physically Completed | 27000 | 11400 | 2026-04-22 | 2026-10-23
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5912957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124209308 | Ongoing | 27000 | 13800 | 2026-06-01
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5914852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125100235 | Ongoing | 27000 | 9300 | 2026-05-07
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5917255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125569713 | Ongoing | 27000 | 4500 | 2026-04-15
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5918211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125354661 | Ongoing | 27000 | 9000 | 2026-04-15
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5921626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123193201 | Ongoing | 27000 | 9000 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5922337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123326551 | Physically Completed | 27000 | 11700 | 2026-04-22 | 2026-10-23
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5922422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125098235 | Ongoing | 27000 | 17100 | 2026-07-31
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5922947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124208751 | Ongoing | 27000 | 12300 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5923657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123191051 | Physically Completed | 27000 | 8100 | 2026-04-22 | 2026-10-18
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5924360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124215576 | Ongoing | 27000 | 11700 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5924570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125815924 | Ongoing | 27000 | 4200 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5924596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124209914 | Ongoing | 27000 | 9300 | 2026-06-01
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5924779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124212014 | Physically Completed | 27000 | 11700 | 2026-04-22 | 2026-10-23
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5925136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125717915 | Ongoing | 27000 | 4200 | 2026-05-30
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5925270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125101185 | Ongoing | 27000 | 9000 | 2026-05-07
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5926066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124213256 | Physically Completed | 27000 | 11700 | 2026-04-22 | 2026-10-23
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5926750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124218251 | Ongoing | 27000 | 12000 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5928217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125839226 | Ongoing | 27000 | 4200 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5928728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123326395 | Ongoing | 27000 | 8700 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5929448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147801457 | Ongoing | 27000 | 4200 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5929519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125073098 | Physically Completed | 27000 | 10800 | 2026-04-22 | 2026-10-14
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5929871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125102706 | Ongoing | 27000 | 13500 | 2026-05-30
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5930691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125087939 | Ongoing | 27000 | 9300 | 2026-06-17
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5931498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124242684 | Ongoing | 27000 | 8100 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5998488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125623548 | Ongoing | 27000 | 9300 | 2026-06-17
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5999180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123327372 | Ongoing | 27000 | 4200 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5999181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123329673 | Ongoing | 27000 | 9000 | 2026-05-12
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5999245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125082494 | Ongoing | 27000 | 7800 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/5999331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125088959 | Physically Completed | 27000 | 12600 | 2026-04-22 | 2026-10-18
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6000091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125590653 | Ongoing | 27000 | 13500 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6000278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125068240 | Physically Completed | 27000 | 11400 | 2026-04-22 | 2026-10-18
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6000280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125098811 | Ongoing | 27000 | 13500 | 2026-05-30
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6000543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125099673 | Physically Completed | 27000 | 16200 | 2026-04-22 | 2026-10-18
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6000701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122862861 | Physically Completed | 27000 | 13200 | 2026-04-22 | 2026-10-18
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6000736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126002856 | Physically Completed | 27000 | 11700 | 2026-04-22 | 2026-10-18
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6001033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120856598 | Completed | 27000 | 15600 | 2026-04-22 | 2026-10-13
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6001145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125568413 | Ongoing | 27000 | 4200 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6001479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123192919 | Ongoing | 27000 | 4200 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6001636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122493022 | Physically Completed | 27000 | 11700 | 2026-04-22 | 2026-10-23
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6001924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123326893 | Physically Completed | 27000 | 18300 | 2026-05-07 | 2026-10-11
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6001978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124227837 | Ongoing | 27000 | 9300 | 2026-05-07
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6002291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124201777 | Ongoing | 27000 | 9000 | 2026-08-06
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6002426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122490957 | Ongoing | 27000 | 14100 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6002479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123203534 | Physically Completed | 27000 | 11100 | 2026-04-22 | 2026-10-18
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6003023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125781570 | Ongoing | 27000 | 4200 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6003323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122860638 | Physically Completed | 27000 | 8100 | 2026-06-01 | 2026-10-23
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6003370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125358441 | Ongoing | 27000 | 13500 | 2026-05-12
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6003576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123328987 | Ongoing | 27000 | 9000 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6004239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124202376 | Ongoing | 27000 | 2400 | 2026-05-07
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6006183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120889398 | Ongoing | 27000 | 4200 | 2026-04-15
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6006271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125061001 | Physically Completed | 27000 | 11100 | 2026-04-22 | 2026-10-18
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6008057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124880774 | Physically Completed | 27000 | 12300 | 2026-04-22 | 2026-10-18
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6008178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125081801 | Physically Completed | 27000 | 15600 | 2026-05-07 | 2026-10-23
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6008195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125563293 | Ongoing | 27000 | 4500 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6008776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123329085 | Ongoing | 27000 | 9000 | 2026-05-07
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6009531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125799200 | Ongoing | 27000 | 13500 | 2026-05-30
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6122087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122492698 | Ongoing | 27000 | 13500 | 2026-05-07
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6124336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126451131 | Ongoing | 27000 | 8700 | 2026-05-07
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6132047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122488188 | Ongoing | 27000 | 13800 | 2026-06-17
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6132817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125069757 | Physically Completed | 27000 | 15600 | 2026-05-02 | 2026-10-14
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6135512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123326730 | Physically Completed | 27000 | 11700 | 2026-04-22 | 2026-10-11
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6138951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124200616 | Ongoing | 27000 | 4200 | 2026-05-02
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6153096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123328918 | Ongoing | 27000 | 4200 | 2026-06-01
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6159004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123214426 | Physically Completed | 27000 | 15900 | 2026-04-22 | 2026-10-11
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6168009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125817696 | Completed | 27000 | 12900 | 2026-04-22 | 2026-10-13
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6171586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124246344 | Ongoing | 27000 | 4200 | 2026-04-22
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6172644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125837254 | Ongoing | 27000 | 18000 | 2026-06-01
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6264152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125818362 | Ongoing | 27000 | 3000 | 2026-10-11
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6264877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126318121 | Ongoing | 27000 | 0 | 2026-10-16
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6286237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125065928 | Ongoing | 27000 | 3000 | 2026-10-11
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6297977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122492041 | Ongoing | 27000 | 2400 | 2026-10-13
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6304764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123329202 | Ongoing | 27000 | 3000 | 2026-10-11
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6321183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132886069 | Ongoing | 27000 | 13200 | 2026-07-28
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6325252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121447586 | Ongoing | 27000 | 13200 | 2026-07-28
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6335524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125577750 | Ongoing | 27000 | 2400 | 2026-10-13
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6342619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144075182 | Ongoing | 27000 | 3000 | 2026-10-11
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6368015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124243171 | Ongoing | 27000 | 3000 | 2026-10-11
VIDISHA / LATERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727001038/IF/IAY/6383420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125075766 | Ongoing | 27000 | 0 | 2026-10-16
VIDISHA / LATERI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1727001038/WC/22012035207787 — गैबियन स्ट्रक्चर निर्माण कार्य हीरालाल के खेत के पास ग्राम मदन खेड़ी ग्राम पंचायत मुंडरा सागर | Approved | 112742.77 | 0 | 2024-06-10
VIDISHA / LATERI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1727001038/WC/22012035207800 — rr33 | Approved | 0 | 0 | 2024-06-10
VIDISHA / LATERI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1727001038/WC/22012035207808 — गैबियन स्ट्रक्चर निर्माण कार्य दीमान सिंह के खेत के पास ग्राम मदन खेड़ी ग्राम पंचायत मुंडरा सागर | Approved | 123084.81 | 0 | 2024-06-10
VIDISHA / LATERI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1727001038/WC/22012035207814 — गैबियन स्ट्रक्चर निर्माण कार्य ग्यारसी लाल के खेत के पास ग्राम मदन खेड़ी ग्राम पंचायत मुंडरा सागर | Approved | 117913.8 | 0 | 2024-06-10
VIDISHA / LATERI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1727001038/WC/22012035207825 — गैबियन स्ट्रक्चर निर्माण कार्य रामचंद अहिरवार के खेत के पास ग्राम मदन खेड़ी ग्राम पंचायत मुंडरा सागर | Approved | 123084.81 | 0 | 2024-06-10
VIDISHA / LATERI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1727001038/WC/22012035207835 — rrr22 | Approved | 0 | 0 | 2024-06-10
VIDISHA / LATERI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1727001038/WC/22012035207845 — गैबियन स्ट्रक्चर निर्माण कार्य सरदार सिंह के खेत के पास ग्राम मदन खेड़ी ग्राम पंचायत मुंडरा सागर | Approved | 123084.81 | 0 | 2024-06-10