## Work List
Exported on: 2026-09-13 18:06:10
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JHUKARHOJ
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
VIDISHA / SIRONJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1727002017/AV/22012034630885 — RANIGHAT MODEL GAUSHALA NIRMAN GRAM JALALPUR | Physically Completed | 12711000 | 0 | 2023-03-21 | 2026-07-08
VIDISHA / SIRONJ | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1727002017/IF/22012034411188 — कपिलधारा कूप घूमनसिंह (मनसिंह) / मोतीसिंह जलालपुर | Ongoing | 230000 | 0 | 2018-06-19
VIDISHA / SIRONJ | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1727002017/IF/22012034469909 — कपिलधारा कूप निर्माण बालाराम / शोभाराम ग्राम पाटन | Ongoing | 230000 | 0 | 2019-10-22
VIDISHA / SIRONJ | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1727002017/IF/22012034469919 — कपिलधारा कूप निर्माण कंचनसिंह / नारायणसिंह ग्राम पाटन | Ongoing | 230000 | 0 | 2019-10-30
VIDISHA / SIRONJ | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1727002017/IF/22012034469926 — कपिलधारा कूप निर्माण सुल्‍तान सिंह / मोती सिंह ग्राम पाटन | Ongoing | 230000 | 0 | 2019-03-10
VIDISHA / SIRONJ | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1727002017/IF/22012034498536 — कूप निर्माण खुमान सिंह जाटव ग्राम पाटन | Ongoing | 234458.62 | 0 | 2019-10-22
VIDISHA / SIRONJ | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1727002017/IF/22012034499937 — कूप निर्माण राधे श्याम s/o प्यारेलाल ग्राम पाटन | Ongoing | 234458.62 | 0 | 2020-01-07
VIDISHA / SIRONJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727002017/IF/22012034997138 — खेत तालाब निर्माण सव्‍वा बाई / अमरसिंह ग्राम सुमेरपुर | Ongoing | 356340.1 | 0 | 2022-05-27
VIDISHA / SIRONJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727002017/IF/22012034997226 — खेत तालाब निर्माण मलखान / मिश्रीलाल ग्राम सुमेरपुर | Ongoing | 356340.1 | 0 | 2022-05-27
VIDISHA / SIRONJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727002017/IF/22012034997255 — खेत तालाब निर्माण देवी सिंह / छुटटीलाल ग्राम सुमेरपुर | Ongoing | 356340.1 | 0 | 2022-05-27
VIDISHA / SIRONJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727002017/IF/22012034997268 — खेत तालाब निर्माण गुलाबसिंह / कमल सिंह ग्राम पाटन | Ongoing | 356340.1 | 0 | 2022-05-27
VIDISHA / SIRONJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727002017/IF/GIS/29949 — खेत तालाब निर्माण सुमेरसिंह /हनमंत सिंह ग्राम सुमेरपुर | Ongoing | 359861.92 | 0 | 2023-01-25
VIDISHA / SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727002017/IF/GIS/37076 — खेत तालाब निर्माण गोविंद सिंह / लाखन सिंह ग्राम जलालपुर | Ongoing | 231755.07 | 0 | 2025-05-02
VIDISHA / SIRONJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/3786269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120834425 | Approved | 27000 | 0 | 2022-04-29
VIDISHA / SIRONJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/4772050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122454529 | Ongoing | 27000 | 0 | 2024-11-20
VIDISHA / SIRONJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/4772055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122456766 | Ongoing | 27000 | 0 | 2024-11-20
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5949509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122024111 | Ongoing | 27000 | 3600 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5949513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122042849 | Ongoing | 27000 | 0 | 2026-09-07
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5949514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122043449 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5949516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122045376 | Ongoing | 27000 | 7200 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5949867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122042404 | Ongoing | 27000 | 3600 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5949868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122047948 | Ongoing | 27000 | 3600 | 2026-07-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5950359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127538238 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5950836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120949340 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5950847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120968192 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5950848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120968419 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5950966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124180049 | Ongoing | 27000 | 0 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5950968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124185997 | Ongoing | 27000 | 0 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5950970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124188607 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5950973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124194359 | Ongoing | 27000 | 7200 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5951110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124181380 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5951205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121610772 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5951208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121612758 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5951209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121613145 | Ongoing | 27000 | 7200 | 2026-08-01
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5951216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124108298 | Ongoing | 27000 | 0 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5951435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127542720 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5952742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122379739 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5952829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123195385 | Ongoing | 27000 | 3600 | 2026-07-15
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5952890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126740631 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5952961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120968741 | Ongoing | 27000 | 10800 | 2026-07-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5952971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121613509 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5953138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124189882 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5953473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126946950 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5953475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126947974 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5953482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126957101 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5953507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126737316 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5953564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122029985 | Ongoing | 27000 | 0 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5953618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127252162 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5954147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126956092 | Ongoing | 27000 | 3600 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5954154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126011277 | Ongoing | 27000 | 3600 | 2026-07-15
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5954291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121611142 | Ongoing | 27000 | 7200 | 2026-08-01
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5954298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126962086 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5954517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121608714 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5954559 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126732216 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5955385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124180748 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5955700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127605647 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5955745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122774047 | Ongoing | 27000 | 7200 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5957177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123191727 | Ongoing | 27000 | 0 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5957430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122823872 | Ongoing | 27000 | 3600 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5957436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121608287 | Ongoing | 27000 | 7200 | 2026-08-01
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5957843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126928766 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5957907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121687476 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5959291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126919536 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5959295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126928068 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5959608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126741483 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5960602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126932024 | Ongoing | 27000 | 0 | 2026-09-07
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5960614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126903303 | Ongoing | 27000 | 0 | 2026-04-11
VIDISHA / SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5960628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126943534 | Approved | 27000 | 0 | 2026-02-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5960631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126950050 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5960635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126960041 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5962098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121607597 | Ongoing | 27000 | 0 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5962099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121607939 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5962168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126732953 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5962172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126749359 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5962250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125845098 | Ongoing | 27000 | 0 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5962259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121614648 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5962316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126538187 | Ongoing | 27000 | 0 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5962507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120968047 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5962509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124191095 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5962651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120947847 | Ongoing | 27000 | 7200 | 2026-04-11
VIDISHA / SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5962655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124182137 | Approved | 27000 | 0 | 2026-02-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5962656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124191722 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5963272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126961012 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5963505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122373739 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5963822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126743161 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5964015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123416938 | Ongoing | 27000 | 7200 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5964021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124189303 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5964023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124179205 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5964027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120952228 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5964148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126654684 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5964216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123418347 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5964370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126944563 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5964503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126959133 | Ongoing | 27000 | 7200 | 2026-08-01
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5964725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121685606 | Ongoing | 27000 | 7200 | 2026-08-01
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5964872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125858143 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5965982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126736219 | Ongoing | 27000 | 3600 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5965983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126736652 | Ongoing | 27000 | 3600 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5966419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126745978 | Ongoing | 27000 | 3600 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5966529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120948983 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5986558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120968300 | Ongoing | 27000 | 10800 | 2026-05-12
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5986709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124240750 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5987143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121612148 | Ongoing | 27000 | 3600 | 2026-07-15
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5987242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122456180 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5987462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126736444 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5987849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126963172 | Ongoing | 27000 | 10800 | 2026-07-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5987916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121610008 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5987926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125561205 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5988038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122023686 | Ongoing | 27000 | 7200 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5988040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127163389 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5988115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127125876 | Ongoing | 27000 | 3600 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5988179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126740911 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5988218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126732684 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5988354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121611536 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5988362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126733387 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5988363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120951165 | Ongoing | 27000 | 3600 | 2026-05-12
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5988491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126736008 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5988843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126014910 | Ongoing | 27000 | 10800 | 2026-05-12
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5988903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126740194 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5988985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128648104 | Ongoing | 27000 | 3600 | 2026-05-12
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/5989023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124183361 | Ongoing | 27000 | 3600 | 2026-04-11
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6081315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121609568 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6081318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121610386 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6081445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121673425 | Ongoing | 27000 | 0 | 2026-07-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6081786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122029440 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6082361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122522870 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6082378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122529782 | Ongoing | 27000 | 3600 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6083299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123223607 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6083569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123469245 | Ongoing | 27000 | 10800 | 2026-07-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6084619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124187736 | Ongoing | 27000 | 3600 | 2026-07-15
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6087522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126266007 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6088753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126732449 | Ongoing | 27000 | 3600 | 2026-07-15
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6088759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126733147 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6088761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126733523 | Approved | 27000 | 0 | 2026-03-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6088775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126736877 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6088781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126739167 | Ongoing | 27000 | 7200 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6088782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126739421 | Ongoing | 27000 | 7200 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6088797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126742515 | Ongoing | 27000 | 10800 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6088801 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126745048 | Ongoing | 27000 | 3600 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6088803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126745507 | Ongoing | 27000 | 7200 | 2026-07-04
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6088908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126784086 | Ongoing | 27000 | 7200 | 2026-07-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6089166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126917267 | Ongoing | 27000 | 7200 | 2026-08-07
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6089187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126925373 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6089215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126939218 | Ongoing | 27000 | 0 | 2026-09-07
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6089265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126968776 | Ongoing | 27000 | 7200 | 2026-08-06
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6089769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127247724 | Ongoing | 27000 | 10800 | 2026-06-03
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6090197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127531111 | Ongoing | 27000 | 7200 | 2026-08-01
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6125877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126920159 | Ongoing | 27000 | 3600 | 2026-05-12
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6349082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127131317 | Approved | 27000 | 0 | 2026-07-14
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6355771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126740368 | Approved | 27000 | 0 | 2026-07-14
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6366493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122517813 | Approved | 27000 | 0 | 2026-07-14
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6366520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126936895 | Approved | 27000 | 0 | 2026-07-14
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6366550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126927101 | Approved | 27000 | 0 | 2026-07-14
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6366557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126929830 | Approved | 27000 | 0 | 2026-07-14
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6366561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127124967 | Approved | 27000 | 0 | 2026-07-14
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6366567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126926172 | Approved | 27000 | 0 | 2026-07-14
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6383926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126741200 | Approved | 27000 | 0 | 2026-07-14
VIDISHA / SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002017/IF/IAY/6384998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126738160 | Approved | 27000 | 0 | 2026-07-14
VIDISHA / SIRONJ | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1727002017/RC/GIS/37077 — ग्रेवल रोड निर्माण श्री सांवरिया सेठ मंदिर से मुख्य मार्ग तक ग्राम पाटन | Ongoing | 1199999.55 | 0 | 2024-03-16
VIDISHA / SIRONJ | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1727002017/WC/22012035004330 — निर्मल नीर कूप निर्माण पाटन टपरों के पास ग्राम पाटन | Ongoing | 453451.55 | 0 | 2022-12-06
VIDISHA / SIRONJ | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1727002017/WC/GIS/29384 — सामुदायिक खेत तालाब निर्माण कंचनसिंह के खेत के पास ग्राम पाटन | Ongoing | 355840.1 | 0 | 2022-12-27
VIDISHA / SIRONJ | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1727002017/WC/GIS/29389 — बोल्‍डर चैक डेम निर्माण नाले पर वीर सिंह के खेत के पास ग्राम पाटन | Ongoing | 54553.93 | 0 | 2022-12-29
VIDISHA / SIRONJ | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1727002017/WC/GIS/29391 — बोल्‍डर चैक डेम निर्माण नाले पर कमर सिंह के खेत के पास ग्राम पाटन | Ongoing | 54553.93 | 0 | 2023-02-28