## Work List
Exported on: 2026-10-25 12:29:39
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KAKARAWADA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
VIDISHA / BASODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1727004062/IF/22012035357968 — Dugweel Racharge Rajan/budhha ke kup ke pass gp Kakarawada | Approved | 23995.18 | 0 | 2025-04-14
VIDISHA / BASODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1727004062/IF/22012035358059 — Dugweel Racharge Shibbu/kallu ke kup ke pass gp Kakarawada | Approved | 23995.18 | 0 | 2025-04-14
VIDISHA / BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1727004062/IF/22012035375023 — Khet talab vijay Singh /parasram kakrawada | Approved | 199203.54 | 0 | 2025-04-14
VIDISHA / BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1727004062/IF/22012035636314 — Ek Bagiya Maa ke naam Gaytri Devi Raghuwanshi/Karan raghuwanshi | Approved | 0 | 0 | 2025-10-02
VIDISHA / BASODA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/101746 — Construction of IAY House -IAY REG. NO. MP-27-004-062-001/12018 | Approved | 27000 | 0 | 2015-09-22
VIDISHA / BASODA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/101747 — Construction of IAY House -IAY REG. NO. MP-27-004-062-001/12076 | Approved | 27000 | 0 | 2015-09-22
VIDISHA / BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/1540532 — Construction of IAY House -IAY REG. NO. MP3941125 | Approved | 27000 | 0 | 2018-03-10
VIDISHA / BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/1543352 — Construction of IAY House -IAY REG. NO. MP3978729 | Approved | 27000 | 0 | 2018-03-10
VIDISHA / BASODA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/3832021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117672846 | Approved | 27000 | 0 | 2022-04-25
VIDISHA / BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4458814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936392 | Physically Completed | 27000 | 0 | 2024-03-01 | 2026-09-03
VIDISHA / BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4458819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936541 | Physically Completed | 27000 | 0 | 2024-03-01 | 2026-09-03
VIDISHA / BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4461049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151930795 | Ongoing | 27000 | 0 | 2024-03-01
VIDISHA / BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4461114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013691 | Physically Completed | 27000 | 0 | 2024-03-01 | 2026-09-03
VIDISHA / BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4468893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012537 | Physically Completed | 27000 | 0 | 2024-05-29 | 2026-09-03
VIDISHA / BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4468894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012585 | Physically Completed | 27000 | 0 | 2024-03-01 | 2026-09-03
VIDISHA / BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4468902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013681 | Physically Completed | 27000 | 0 | 2024-03-01 | 2026-09-03
VIDISHA / BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4468904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013689 | Physically Completed | 27000 | 0 | 2024-04-03 | 2026-09-03
VIDISHA / BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4468961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152019755 | Physically Completed | 27000 | 0 | 2024-04-03 | 2026-09-03
VIDISHA / BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4469135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151930672 | Ongoing | 27000 | 0 | 2024-03-01
VIDISHA / BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4469136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151930729 | Physically Completed | 27000 | 0 | 2024-03-01 | 2026-09-03
VIDISHA / BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4469311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936451 | Physically Completed | 27000 | 0 | 2024-03-01 | 2026-09-03
VIDISHA / BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4470282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936485 | Physically Completed | 27000 | 0 | 2024-04-03 | 2026-09-03
VIDISHA / BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4471858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936352 | Ongoing | 27000 | 0 | 2024-04-03
VIDISHA / BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4485418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936589 | Physically Completed | 27000 | 0 | 2024-04-03 | 2026-09-03
VIDISHA / BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4693907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116434330 | Ongoing | 27000 | 0 | 2025-02-05
VIDISHA / BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4815355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152066002 | Ongoing | 27000 | 0 | 2025-02-20
VIDISHA / BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4815420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152066447 | Ongoing | 27000 | 0 | 2025-02-06
VIDISHA / BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4815493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152067438 | Ongoing | 27000 | 0 | 2025-02-20
VIDISHA / BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4947353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116434294 | Approved | 27000 | 0 | 2025-02-07
VIDISHA / BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4948325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115969317 | Ongoing | 27000 | 2400 | 2025-07-09
VIDISHA / BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4954047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120696783 | Physically Completed | 23490 | 0 | 2025-08-01 | 2026-08-02
VIDISHA / BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/4958863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123633568 | Physically Completed | 23490 | 1500 | 2025-06-03 | 2026-08-02
VIDISHA / BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/5439431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120696483 | Approved | 27000 | 0 | 2025-02-08
VIDISHA / BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004062/IF/IAY/6272222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131230972 | Approved | 27000 | 0 | 2026-04-13
VIDISHA / BASODA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034614788 — cc road nirman karya veer singh sen ke ghar se guddu ke ghar tak kakravda | Ongoing | 30700 | 0 | 2022-05-24
VIDISHA / BASODA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034833083 — CC ROAD NIRMAN HANUMAN MANDIR SE NAVAL PANDA KE GHAR KI OR | Ongoing | 21000 | 0 | 2026-08-20
VIDISHA / BASODA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1727004062/RS/22012034658366 — nali ke upar farsikaran karya main road kakrawada | Ongoing | 26154 | 0 | 2022-05-27
VIDISHA / BASODA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair & Maintenance of Water Harvesting Pond for Community | Repair & maint of Pond/ Tank | 1727004062/WC/22012034942626 — Wast Weir Nirman Gram Kakrawda | Ongoing | 315991.58 | 0 | 2022-04-12