## Work List
Exported on: 2026-10-26 09:53:39
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: AMARPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
VIDISHA / NATERAN | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1727005041/AV/22012034389924 — Anganwadi bhawan bherobag | Ongoing | 180000 | 0 | 2018-09-28
VIDISHA / NATERAN | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1727005041/AV/22012034389926 — Anganwadi bhawan goriyakheda | Ongoing | 180000 | 0 | 2018-09-28
VIDISHA / NATERAN | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen Shed for Government School for Community | Constr of Kitchen Shed | 1727005041/AV/22012034598305 — NMS GORIYA KHEDA ME DAINING HALL NIRMAN GRAM GORIYA KHEDA GP AMARPUR | Ongoing | 16093.2 | 0 | 2021-10-21
VIDISHA / NATERAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1727005041/DP/22012034593400 — vasudha vandhan- amrit vatika- praimary school bheronbag parisar | Ongoing | 55847.4 | 0 | 2023-10-08
VIDISHA / NATERAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1727005041/DP/22012034625672 — VARSHAROPAN SAMUDAYIK KARYA SHATIDHAM PARISAR GRAM BHEROGAAG AMARPURA | Ongoing | 453563.17 | 0 | 2024-08-23
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1727005041/IF/22012035364261 — JGSA khet talab ramswarup sharma /premnrayan sharma | Approved | 369740.21 | 0 | 2025-04-01
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1727005041/IF/22012035365664 — JGSA khet talab kamal singh yadav/halkuram goriyaheda amarpura | Physically Completed | 369740.21 | 0 | 2025-04-24 | 2026-07-06
VIDISHA / NATERAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1727005041/IF/22012035379722 — JGSA recharge structure naresh yadav /kailash yadav gram bherobag gp amarpura | Approved | 25899.46 | 0 | 2025-04-14
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1727005041/IF/22012035526741 — JGSA khet talab ramcharan narayan singh bheron bhag amarpura | Approved | 0 | 0 | 2025-04-01
VIDISHA / NATERAN | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/2586340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4064227 | Approved | 27000 | 0 | 2020-05-21
VIDISHA / NATERAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/3435313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5436550 | Ongoing | 27000 | 0 | 2022-09-04
VIDISHA / NATERAN | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/4471735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151932448 | Approved | 27000 | 0 | 2024-03-01
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/4506849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151882900 | Approved | 27000 | 0 | 2024-06-11
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/4702951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118721182 | Physically Completed | 27000 | 19500 | 2026-06-22 | 2026-10-04
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/4703360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120244722 | Ongoing | 27000 | 0 | 2026-02-12
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/4803044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151932552 | Approved | 27000 | 0 | 2024-09-10
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5153447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125865097 | Completed | 23490 | 0 | 2026-02-12 | 2026-07-30
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5156037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118721317 | Approved | 27000 | 0 | 2025-02-12
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5226151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121723773 | Approved | 27000 | 0 | 2025-02-12
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5370503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119689606 | Physically Completed | 23490 | 0 | 2026-01-01 | 2026-08-02
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5709258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121724543 | Physically Completed | 23490 | 4200 | 2026-02-12 | 2026-08-16
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5902762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118721341 | Physically Completed | 27000 | 13800 | 2026-04-10 | 2026-10-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5903087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117396035 | Ongoing | 27000 | 4200 | 2026-10-06
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5903509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120277786 | Ongoing | 27000 | 12600 | 2026-08-14
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5904125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121724971 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5904760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123566930 | Ongoing | 27000 | 16800 | 2026-08-14
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5905674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123564214 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5905930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123576309 | Physically Completed | 27000 | 22500 | 2026-06-01 | 2026-10-11
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5906028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119568617 | Physically Completed | 27000 | 22500 | 2026-06-01 | 2026-10-11
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5906479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121723386 | Ongoing | 27000 | 24300 | 2026-06-22
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5907077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121727109 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5908472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121721482 | Ongoing | 27000 | 4200 | 2026-09-29
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5909047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121725802 | Ongoing | 27000 | 0 | 2026-10-17
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5912278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119568678 | Physically Completed | 27000 | 22500 | 2026-06-01 | 2026-10-11
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5912345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123597156 | Ongoing | 27000 | 21000 | 2026-06-01
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5912490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116947111 | Ongoing | 27000 | 0 | 2026-09-29
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5914325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119690830 | Ongoing | 27000 | 16800 | 2026-08-14
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5914333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119690514 | Physically Completed | 27000 | 23100 | 2026-07-03 | 2026-10-04
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5914352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123573195 | Physically Completed | 27000 | 22500 | 2026-06-01 | 2026-10-11
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5915760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120235766 | Ongoing | 27000 | 16800 | 2026-08-14
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5916750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121719289 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5917453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116729926 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5917671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117396307 | Physically Completed | 27000 | 26700 | 2026-07-16 | 2026-10-04
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5918316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123198633 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5918651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120279831 | Ongoing | 27000 | 0 | 2026-04-10
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5918697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118721538 | Ongoing | 27000 | 8400 | 2026-08-14
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5918898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123566510 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5919024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119568752 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5919528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123537936 | Physically Completed | 27000 | 26700 | 2026-08-14 | 2026-10-11
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5919628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123538722 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5919757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120278698 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5919945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119568961 | Physically Completed | 27000 | 9900 | 2026-05-16 | 2026-10-04
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5920190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123580360 | Physically Completed | 27000 | 26700 | 2026-08-14 | 2026-10-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5921440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121729096 | Physically Completed | 27000 | 7500 | 2026-04-29 | 2026-09-20
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5922215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123597930 | Ongoing | 27000 | 16800 | 2026-08-14
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5923894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120245047 | Ongoing | 27000 | 16800 | 2026-08-14
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5924858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123794702 | Ongoing | 27000 | 0 | 2026-10-13
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5926258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116947580 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5927465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120279609 | Ongoing | 27000 | 16800 | 2026-08-14
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5927750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118721292 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5928335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118721276 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5928839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120280259 | Ongoing | 27000 | 0 | 2026-09-29
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5929203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123596354 | Physically Completed | 27000 | 26700 | 2026-07-17 | 2026-10-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5929273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118721215 | Physically Completed | 27000 | 12300 | 2026-04-10 | 2026-10-04
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5929290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120278489 | Ongoing | 27000 | 16800 | 2026-08-14
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5930212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126122724 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5930798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118721421 | Ongoing | 27000 | 0 | 2026-06-01
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5931092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118721477 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5931488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118721500 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5999025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123587034 | Ongoing | 27000 | 16800 | 2026-08-14
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5999068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123199018 | Ongoing | 27000 | 4200 | 2026-10-06
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5999340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123555183 | Physically Completed | 27000 | 8400 | 2026-04-29 | 2026-10-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5999658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123769794 | Ongoing | 27000 | 16500 | 2026-08-14
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/5999860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120280047 | Ongoing | 27000 | 16800 | 2026-08-14
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6000205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116947873 | Physically Completed | 27000 | 26700 | 2026-07-16 | 2026-10-04
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6000206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121726228 | Ongoing | 27000 | 0 | 2026-10-17
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6000688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123566072 | Ongoing | 27000 | 8400 | 2026-09-29
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6000803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117395939 | Physically Completed | 23490 | 8400 | 2026-05-16 | 2026-08-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6000873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123581278 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6001032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118721370 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6001110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123192282 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6001503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119689755 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6001504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119689957 | Physically Completed | 27000 | 26700 | 2026-07-03 | 2026-10-04
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6001507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126179787 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6001763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126177808 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6001911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119690971 | Ongoing | 27000 | 0 | 2026-10-17
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6002126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121723022 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6002545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123563737 | Ongoing | 27000 | 0 | 2026-09-29
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6002657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123541142 | Physically Completed | 27000 | 26700 | 2026-07-17 | 2026-10-06
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6002658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119568998 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6002661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123572053 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6002665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123577365 | Physically Completed | 27000 | 16200 | 2026-06-01 | 2026-09-20
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6002666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123579888 | Physically Completed | 27000 | 26700 | 2026-07-03 | 2026-10-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6002667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123581687 | Ongoing | 27000 | 16800 | 2026-08-14
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6002668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123582621 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6002670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123585261 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6002671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123585716 | Physically Completed | 27000 | 26700 | 2026-07-03 | 2026-10-18
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6003190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123569861 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6003253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121725383 | Ongoing | 27000 | 21000 | 2026-06-01
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6003768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123592370 | Approved | 27000 | 0 | 2026-02-18
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6003803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123586584 | Ongoing | 27000 | 8400 | 2026-10-06
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6255882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118721397 | Approved | 27000 | 0 | 2026-05-19
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6258981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121722190 | Ongoing | 27000 | 0 | 2026-10-17
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6260866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123193798 | Approved | 27000 | 0 | 2026-05-23
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6261121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123584374 | Ongoing | 27000 | 8400 | 2026-10-06
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6298337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120278272 | Approved | 27000 | 0 | 2026-05-19
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6299248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123594883 | Approved | 27000 | 0 | 2026-05-23
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6300620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123538347 | Approved | 27000 | 0 | 2026-05-19
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6303578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121684433 | Approved | 27000 | 0 | 2026-05-19
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6330341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116947511 | Approved | 27000 | 0 | 2026-07-14
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6349818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120237994 | Approved | 27000 | 0 | 2026-07-07
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6379743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121722626 | Approved | 27000 | 0 | 2026-07-07
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/6380122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121720325 | Approved | 27000 | 0 | 2026-08-03
VIDISHA / NATERAN | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1727005041/IF/IAY/744861 — Construction of IAY House -IAY REG. NO. MP2368638 | Approved | 27000 | 0 | 2017-03-20
VIDISHA / NATERAN | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1727005041/RC/22012034819220 — सीसी सडक निर्माण विशन सिंह के मकान से हनुमान मंदिर की ओर ग्राम बेरखेडीघाट ग्राम पंचायत अमरपुरा | Approved | 104019 | 0 | 2024-04-24
VIDISHA / NATERAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1727005041/WC/22012035237210 — WATER HARVESTINGH POND NIRMAN GRAM PANCHAYAT BHAWAN KE PASS AMARPURA | Approved | 0 | 0 | 2024-10-30
VIDISHA / NATERAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1727005041/WC/22012035237212 — WATER HARVESTING POND NIRMAN KARYA BAGICHE KE NICHE GRAM BHEROBAG AMARPURA | New | 0 | 0 | 2024-10-30
VIDISHA / NATERAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1727005041/WC/22012035275901 — JGSA pas recharge structure panchayat bhavan ke gram amarpura gp amarpura | Approved | 25899.46 | 0 | 2025-04-14