## Work List
Exported on: 2026-10-24 10:58:26
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JOGIKIRRODA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
VIDISHA / NATERAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1727005065/DP/22012034593230 — vasudha vandhan- amrit vatika- sarvjanik parisar nadi ghat par gp jogikirooda | Ongoing | 55847.4 | 0 | 2023-09-30
VIDISHA / NATERAN | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1727005065/IF/22012034383160 — Plantation khet ki med pr bhoori bai/ bhero singh | Ongoing | 189200 | 0 | 2019-01-11
VIDISHA / NATERAN | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Bio-drainage Plantation for Individual | Plantation | 1727005065/IF/22012034519019 — Khet talab nirman leelakisan sen | Ongoing | 101997.1 | 0 | 2020-06-08
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1727005065/IF/22012035377567 — JGSA khet talab bahadur singh kanshiram jogikirroda | Ongoing | 145971.43 | 0 | 2025-04-23
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1727005065/IF/22012035377584 — JGSA khet talab sher singh kanshiram jogikirroda | Ongoing | 147621.16 | 0 | 2025-04-23
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1727005065/IF/22012035612419 — EK BAGIYA MAA KE NAAM RAJNEETA AHIRWAR RAMKRISHN 304159586 GRAM PAYRI JOGIKIRRODA | Ongoing | 266577.25 | 0 | 2025-10-16
VIDISHA / NATERAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/3799542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103948195 | Approved | 27000 | 0 | 2022-05-03
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/4129675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102213760 | Physically Completed | 23490 | 0 | 2024-09-25 | 2026-07-30
VIDISHA / NATERAN | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/4395098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102927332 | Physically Completed | 23490 | 0 | 2023-11-24 | 2026-07-30
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/4734444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100990939 | Approved | 27000 | 0 | 2024-09-18
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/4734493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102110814 | Approved | 27000 | 0 | 2024-10-10
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/4734994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102300213 | Ongoing | 27000 | 0 | 2025-04-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/4735003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102307451 | Physically Completed | 23490 | 0 | 2025-03-10 | 2026-07-30
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/4735271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100725679 | Physically Completed | 23490 | 0 | 2025-03-10 | 2026-07-30
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/4737545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102085329 | Physically Completed | 23490 | 0 | 2025-03-10 | 2026-07-30
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/4739283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105460534 | Physically Completed | 27000 | 0 | 2025-03-10 | 2026-10-11
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5151027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100862533 | Ongoing | 27000 | 0 | 2025-04-17
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5154156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104899201 | Ongoing | 27000 | 0 | 2025-04-17
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5154823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101003713 | Physically Completed | 27000 | 10200 | 2025-04-17 | 2026-10-18
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5154992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113859768 | Ongoing | 27000 | 0 | 2026-02-02
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5157959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102447486 | Approved | 27000 | 0 | 2025-03-07
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5162607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104027570 | Completed | 23490 | 0 | 2025-10-30 | 2026-07-30
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5162783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104922228 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5165165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102233434 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5167799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102325692 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5168926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105720535 | Physically Completed | 27000 | 12300 | 2026-06-06 | 2026-10-11
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5169795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102332310 | Ongoing | 27000 | 16200 | 2026-09-03
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5170875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102638502 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5173467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102193460 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5176302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100871625 | Physically Completed | 23490 | 0 | 2026-01-19 | 2026-07-12
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5180030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113951428 | Ongoing | 27000 | 22200 | 2026-08-19
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5182045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102640771 | Ongoing | 27000 | 0 | 2026-07-28
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5182898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100985658 | Approved | 27000 | 0 | 2025-03-07
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5185047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101017190 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5185094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100874971 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5185952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104919410 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5187727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104034772 | Approved | 27000 | 0 | 2025-03-07
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5188223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104919213 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5188296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100993078 | Ongoing | 27000 | 0 | 2026-05-22
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5190853 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103097801 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5191231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113861794 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5191958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102275347 | Ongoing | 27000 | 15600 | 2026-07-30
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5194263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103599957 | Approved | 27000 | 0 | 2025-03-07
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5194969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100796224 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5195564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102088548 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5195716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106082055 | Approved | 27000 | 0 | 2025-03-07
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5196447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102302816 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5196787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147203260 | Ongoing | 27000 | 0 | 2025-04-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5197501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105442170 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5198190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102238281 | Ongoing | 27000 | 0 | 2025-10-28
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5199336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102651137 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5201758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104922926 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5202131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106077595 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5202658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100711083 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5203633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102642039 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5203805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102658422 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5204520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100801175 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5206012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104927698 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5206318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103972076 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5207499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101000514 | Physically Completed | 23490 | 0 | 2025-02-17 | 2026-08-02
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5207788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105587734 | Ongoing | 27000 | 0 | 2026-10-13
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5208338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102210352 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5209281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104028920 | Completed | 23490 | 0 | 2025-10-30 | 2026-07-30
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5209322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100985012 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5209460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100868510 | Ongoing | 27000 | 16800 | 2026-08-19
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5211464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102097788 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5214659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100850377 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5217991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102319326 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5218087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103532239 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5220931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102191551 | Physically Completed | 27000 | 0 | 2026-08-18 | 2026-10-11
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5221188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102356574 | Ongoing | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5221882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100818406 | Ongoing | 27000 | 25200 | 2026-08-19
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5224822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102305094 | Ongoing | 27000 | 0 | 2025-09-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5225325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102215493 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5226120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102449370 | Physically Completed | 27000 | 26400 | 2026-07-07 | 2026-10-06
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5228006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102254438 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5229331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102641816 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5230592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106587686 | Ongoing | 27000 | 0 | 2025-10-28
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5230768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100865261 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5232870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113922572 | Approved | 27000 | 0 | 2025-03-07
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5237108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100879490 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5239382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102430485 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5239668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100881483 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5241739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106080996 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5243699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104030810 | Ongoing | 27000 | 3000 | 2025-10-28
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5322160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105713704 | Approved | 27000 | 0 | 2025-03-21
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5434278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105709361 | Approved | 27000 | 0 | 2025-04-01
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5434339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102273180 | Approved | 27000 | 0 | 2025-04-01
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5436084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105466946 | Physically Completed | 27000 | 4200 | 2026-07-07 | 2026-10-18
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5438695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105490369 | Approved | 27000 | 0 | 2025-04-01
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5439621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100846594 | Approved | 27000 | 0 | 2025-04-01
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5635542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103579647 | Approved | 27000 | 0 | 2025-05-12
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5697895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105490305 | Ongoing | 27000 | 0 | 2026-07-28
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5871836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105489691 | Approved | 27000 | 0 | 2025-07-05
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5871837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102235830 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5948676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100824559 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5948885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113924566 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5948889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105560674 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5948972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101020138 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5948992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102920060 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5948994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102933790 | Ongoing | 27000 | 0 | 2026-09-03
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5949136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100829049 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5949148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100885470 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5949331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102210438 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5949477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105845840 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5949479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105860726 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5949597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105866647 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5949688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105474396 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5950583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100986689 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5950625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102287885 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5950892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147223354 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5951781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104918734 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5952866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105563122 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5953916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106005721 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5953917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106005733 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5955002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105858602 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5957617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113855649 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5957644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102131663 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5958141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102459096 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5958390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104919602 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5958392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104921947 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5958441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113857356 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5958859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105436373 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5959562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105857198 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5960720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102199853 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5963238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102452402 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5963240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102454995 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5963865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100820805 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5965256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102229452 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5965262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100963596 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5965267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102198312 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5965584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102291013 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5966026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105567002 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5966566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100727256 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5966567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105869001 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5966862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931900 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5966888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103095055 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5966889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113896497 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/5966891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100815741 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6118182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104046346 | Approved | 27000 | 0 | 2026-03-04
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6118183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104913715 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6118560 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105478184 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6118834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104919817 | Approved | 27000 | 0 | 2026-02-21
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6118835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104920613 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6119213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105525043 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6119507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103097243 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6119536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104921409 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6119961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105851984 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6120342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106587708 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6120404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105839255 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6120704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105863234 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6121033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106085023 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6121715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105850502 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6122211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102641447 | Approved | 27000 | 0 | 2026-03-04
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6122471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113914532 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6125464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100877292 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6126897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102441005 | Approved | 27000 | 0 | 2026-03-04
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6138525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102440069 | Approved | 27000 | 0 | 2026-03-04
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6138721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102269842 | Approved | 27000 | 0 | 2026-03-04
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6138723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102288103 | Approved | 27000 | 0 | 2026-03-04
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6138726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102310132 | Approved | 27000 | 0 | 2026-03-04
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6141259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102462667 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6155041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102266979 | Approved | 27000 | 0 | 2026-03-06
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6159419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102434353 | Approved | 27000 | 0 | 2026-03-04
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6159423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102286634 | Approved | 27000 | 0 | 2026-02-16
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6172453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113906056 | Approved | 27000 | 0 | 2026-03-06
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6172456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100977995 | Approved | 27000 | 0 | 2026-03-06
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6172458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102996793 | Approved | 27000 | 0 | 2026-03-06
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6175625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102128504 | Approved | 27000 | 0 | 2026-03-04
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6243054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105550223 | Approved | 27000 | 0 | 2025-03-07
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6243403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102081292 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6243494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102348608 | Ongoing | 27000 | 15900 | 2026-07-28
VIDISHA / NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6244949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103097462 | Approved | 27000 | 0 | 2025-02-17
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6246249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102909343 | Approved | 27000 | 0 | 2026-05-14
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6246675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102457375 | Approved | 27000 | 0 | 2026-05-14
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6246988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104927238 | Approved | 27000 | 0 | 2026-06-01
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6298334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113857961 | Approved | 27000 | 0 | 2026-05-14
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6304440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104927475 | Approved | 27000 | 0 | 2026-06-01
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6329602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106486827 | Approved | 27000 | 0 | 2026-06-25
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6330173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105534572 | Approved | 27000 | 0 | 2026-06-25
VIDISHA / NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6330537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103964590 | Approved | 27000 | 0 | 2026-06-25
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6378311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113966411 | Approved | 27000 | 0 | 2026-03-04
VIDISHA / NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727005065/IF/IAY/6379471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113911558 | Approved | 27000 | 0 | 2026-02-23
VIDISHA / NATERAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1727005065/WC/22012035059329 — Nirmal neer shantidham parisar jogikirroda | Ongoing | 492450.4 | 0 | 2023-10-05
VIDISHA / NATERAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1727005065/WC/22012035261481 — JGSA recharge structure gaon bala kuaa jogikirroda | Approved | 25899.46 | 0 | 2025-04-01
VIDISHA / NATERAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1727005065/WC/22012035261483 — JGSA recharge structure samandar ke khet ke pass nebli | Approved | 25899.46 | 0 | 2025-04-01