## Work List
Exported on: 2026-10-02 12:00:18
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: LALARIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1728001049/IC/VB/22012034893381 — samudayak koop nirman gp lalaria | New | 0 | 0 | 2026-07-10
BHOPAL / BERASIA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1728001049/IF/22012034939818 — Koop nirman jaheer khan | Ongoing | 296834.23 | 0 | 2022-03-01
BHOPAL / BERASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1728001049/IF/22012035250945 — Cattle shed nirman khaleel khan / saeed khan | Approved | 0 | 0 | 2024-06-09
BHOPAL / BERASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1728001049/IF/22012035250946 — Cattle shed nirman Abid Khan / Abdul Badood Khan | Approved | 0 | 0 | 2024-06-09
BHOPAL / BERASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1728001049/IF/22012035254475 — Cattle shed nirman Asif Khan / mumtaj Khan | Approved | 0 | 0 | 2024-06-09
BHOPAL / BERASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1728001049/IF/22012035260126 — Cattle shed nirman uzma bee / akeel khan | Approved | 0 | 0 | 2024-08-16
BHOPAL / BERASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1728001049/IF/22012035260128 — Cattle shed nirman seema jahan /Abid Khan | Approved | 0 | 0 | 2024-08-16
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1728001049/IF/22012035321991 — Koop Nirman Abdul Saleem Khan / Rasheed Khan | Approved | 333734.73 | 0 | 2025-04-01
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1728001049/IF/22012035322043 — Koop Nirman Kamlesh / devchand | Approved | 333249.11 | 0 | 2025-04-01
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1728001049/IF/22012035352541 — Koop Nirman Ajay Kumar Malviya / Kamlesh Malviya | Ongoing | 339410.7 | 0 | 2025-04-27
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1728001049/IF/22012035456595 — Koop Nirman Recharge pit peer khan | New | 0 | 0 | 2025-04-14
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1728001049/IF/22012035457434 — Koop Nirman Recharge pit Raja Khan | New | 0 | 0 | 2025-04-14
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1728001049/IF/22012035460198 — Khet talab Rakeeb khan / Rafeek Khan | New | 0 | 0 | 2025-04-14
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1728001049/IF/22012035460235 — Khet talab Rakeeb khan / Rafeek Khan | Physically Completed | 185441.45 | 0 | 2025-05-06 | 2026-08-17
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1728001049/IF/22012035460591 — Khet talab peer khan / jafar Khan | Approved | 0 | 0 | 2025-04-14
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1728001049/IF/22012035460943 — Khet talab arjun singh / jagannath | Ongoing | 185441.45 | 0 | 2025-05-06
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1728001049/IF/22012035465827 — Khet talab Rashid khan / Salam Khan | Approved | 0 | 0 | 2025-04-14
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1728001049/IF/22012035542818 — Koop Nirman Karya Yasir Khan / Shafi Ullah Khan | Ongoing | 267533.14 | 0 | 2025-06-04
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1728001049/IF/22012035563540 — Khet Talab Nazra Sultan / Abdul Hakeem Khan | New | 0 | 0 | 2025-04-14
BHOPAL / BERASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1728001049/IF/22012035587064 — एक बगिया माँ के नाम (हितग्राही अरबिया हकीम खान / अब्दुल हकीम खान) | Approved | 0 | 0 | 2025-04-14
BHOPAL / BERASIA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/2130775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4782733 | Ongoing | 27000 | 0 | 2019-07-16
BHOPAL / BERASIA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/2945319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1268388 | Approved | 27000 | 0 | 2021-01-05
BHOPAL / BERASIA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/2953512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4197173 | Ongoing | 27000 | 0 | 2021-09-14
BHOPAL / BERASIA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/3231761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3800319 | Ongoing | 27000 | 0 | 2021-08-31
BHOPAL / BERASIA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/3232027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2473373 | Ongoing | 27000 | 0 | 2021-08-31
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/3241417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4308593 | Ongoing | 27000 | 16800 | 2026-08-25
BHOPAL / BERASIA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/3662964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114030545 | Ongoing | 27000 | 0 | 2022-05-18
BHOPAL / BERASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/4664042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149776001 | Ongoing | 27000 | 0 | 2025-01-25
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/4744737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031725 | Ongoing | 27000 | 0 | 2025-04-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/4749058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115916871 | Ongoing | 27000 | 0 | 2026-05-23
BHOPAL / BERASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5589475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031470 | Ongoing | 27000 | 0 | 2025-09-13
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5590354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115679984 | Ongoing | 27000 | 0 | 2026-05-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5986776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031255 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5986777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031654 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5986778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031660 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5986779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031670 | Physically Completed | 27000 | 12000 | 2026-04-08 | 2026-09-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5986781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031719 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5986830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150866075 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5986864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149775962 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5986865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149776039 | Ongoing | 27000 | 7200 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5986866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149776304 | Ongoing | 27000 | 12300 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5986953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106644084 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115916099 | Ongoing | 27000 | 0 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376248 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376271 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376377 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376393 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376406 | Physically Completed | 27000 | 12000 | 2026-04-08 | 2026-09-13
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115680573 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987288 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115680710 | Ongoing | 27000 | 7800 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115912841 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115375831 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115916852 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065112 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065180 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115915762 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115679024 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065228 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065245 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5987978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065294 | Physically Completed | 27000 | 12000 | 2026-04-08 | 2026-09-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115917837 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115917935 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125633872 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106643659 | Physically Completed | 27000 | 12000 | 2026-04-08 | 2026-09-13
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106643835 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106643848 | Ongoing | 27000 | 3900 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376501 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106657629 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106657711 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106365961 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106366017 | Physically Completed | 27000 | 12000 | 2026-04-08 | 2026-09-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106366060 | Physically Completed | 27000 | 12000 | 2026-04-08 | 2026-09-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115680066 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115680185 | Ongoing | 27000 | 12000 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115680222 | Ongoing | 27000 | 4200 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115680967 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106979334 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5988927 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376103 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031685 | Ongoing | 27000 | 3900 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150865865 | Ongoing | 27000 | 12300 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114769776 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114771543 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115916507 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115679505 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115680933 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115681028 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115375755 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125631840 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065255 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065284 | Physically Completed | 27000 | 11700 | 2026-04-08 | 2026-09-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065301 | Ongoing | 27000 | 3600 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065361 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376674 | Physically Completed | 27000 | 11700 | 2026-04-23 | 2026-09-13
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115916132 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115916170 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376872 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376881 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106657451 | Physically Completed | 27000 | 11700 | 2026-04-08 | 2026-09-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106657490 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115591411 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115681231 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149776082 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149776135 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149776274 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115916071 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115911708 | Ongoing | 27000 | 5400 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115917202 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106978649 | Ongoing | 27000 | 4200 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106978720 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106978852 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116895936 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989539 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376654 | Physically Completed | 27000 | 7800 | 2026-04-08 | 2026-09-13
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376666 | Physically Completed | 27000 | 11700 | 2026-04-08 | 2026-09-13
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106366101 | Physically Completed | 27000 | 11700 | 2026-04-08 | 2026-09-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149776827 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031451 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031576 | Ongoing | 27000 | 4200 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106978875 | Ongoing | 27000 | 3600 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106978939 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106979067 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106979086 | Physically Completed | 27000 | 11700 | 2026-04-08 | 2026-09-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106979109 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106644020 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065516 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147147881 | Physically Completed | 27000 | 10800 | 2026-04-08 | 2026-09-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115680179 | Ongoing | 27000 | 7800 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115680227 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115680913 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115680919 | Ongoing | 27000 | 3600 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115680926 | Ongoing | 27000 | 3600 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149776107 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150866570 | Ongoing | 27000 | 12000 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115375994 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376034 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376485 | Physically Completed | 27000 | 11700 | 2026-04-08 | 2026-09-13
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031366 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5989959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031677 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115918524 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376515 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106365851 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115911600 | Ongoing | 27000 | 4200 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031171 | Ongoing | 27000 | 3600 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031181 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031210 | Ongoing | 27000 | 4200 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065085 | Ongoing | 27000 | 7500 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065161 | Ongoing | 27000 | 7500 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115915711 | Ongoing | 27000 | 7500 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115915731 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115917899 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106644063 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106657578 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106978914 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106978991 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065216 | Ongoing | 27000 | 8100 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065273 | Ongoing | 27000 | 3600 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106978665 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106978686 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115916582 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147166899 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106643879 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031438 | Ongoing | 27000 | 7500 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106643689 | Ongoing | 27000 | 0 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106643702 | Ongoing | 27000 | 3600 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/5990530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106643746 | Ongoing | 27000 | 11700 | 2026-04-08
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6068639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065315 | Ongoing | 27000 | 3600 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6068968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106365921 | Physically Completed | 27000 | 11700 | 2026-04-23 | 2026-09-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6068969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106366262 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6069302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106643810 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6069303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106644166 | Physically Completed | 27000 | 11700 | 2026-04-23 | 2026-09-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6069333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106656982 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6069334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106657039 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6069771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106978834 | Ongoing | 27000 | 3600 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6070919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114030897 | Ongoing | 27000 | 7800 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6070921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031638 | Physically Completed | 27000 | 11700 | 2026-04-23 | 2026-09-27
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6071608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114831482 | Ongoing | 27000 | 0 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6072712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376112 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6072713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376258 | Ongoing | 27000 | 7800 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6072714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376286 | Physically Completed | 27000 | 11700 | 2026-04-23 | 2026-09-13
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6072985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115679514 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6072995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115681232 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6073543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115912730 | Ongoing | 27000 | 7500 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6073548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115915553 | Ongoing | 27000 | 0 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6073549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115915576 | Ongoing | 27000 | 7500 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6073553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115918765 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6100198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149775684 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6100199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149775800 | Ongoing | 27000 | 6600 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6100200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149775877 | Ongoing | 27000 | 7500 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6100745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150865614 | Ongoing | 27000 | 4200 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6140254 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031645 | Ongoing | 27000 | 7800 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6145604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106978769 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6146734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149776248 | Ongoing | 27000 | 12000 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6152278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149776861 | Ongoing | 27000 | 12000 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6153273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115376795 | Ongoing | 27000 | 0 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6155633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106364631 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6165725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106979233 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6166928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106366168 | Ongoing | 27000 | 11700 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6173615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150866194 | Ongoing | 27000 | 0 | 2026-04-23
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6388772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114030876 | Approved | 27000 | 0 | 2026-08-20
BHOPAL / BERASIA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728001049/IF/IAY/6389164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115917297 | Approved | 27000 | 0 | 2026-09-01
BHOPAL / BERASIA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1728001049/RC/22012034850412 — CC ROAD CHANDANKHEDI TIRAHA SE | Ongoing | 120000 | 116700 | 2025-11-07
BHOPAL / BERASIA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1728001049/RS/22012035138980 — RCC NALI NIRMAN ABDUL SALAM KE GHAR KI AUR | Ongoing | 90000 | 48300 | 2026-04-22
BHOPAL / BERASIA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1728001049/RS/22012035138981 — Grey water treatment | Approved | 67000 | 0 | 2025-04-16
BHOPAL / BERASIA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1728001049/RS/VB/22012035139588 — grey water treatment plan | Deleted | 67000 | 0 | 2026-07-10
BHOPAL / BERASIA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1728001049/WC/22012035232553 — pokhar nirman gp lalaria | Approved | 0 | 0 | 2024-10-02
BHOPAL / BERASIA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1728001049/WC/22012035253774 — CHECK DAM NIRMAN GP LALARIA | Approved | 0 | 0 | 2025-01-24
BHOPAL / BERASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1728001049/WC/22012035316638 — Pond Nirman Gram Panchayat Lalaria | Approved | 0 | 0 | 2025-04-14
BHOPAL / BERASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1728001049/WC/22012035322075 — Percolation tank nirman lalaria | New | 0 | 0 | 2025-10-02