## Work List
Exported on: 2026-09-26 11:06:26
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PURA CHHINDWARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHOPAL / PHANDA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1728002009/AV/22012034540283 — पुलिया निर्माण कार्य मनरेगा अभिसरण +15 वां वित्‍त नासिर के खेत के पास, पुराछिंदवाडा | Ongoing | 27000 | 0 | 2020-10-19
BHOPAL / PHANDA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1728002009/AV/22012034586625 — मॉं की बगिया निर्माण कार्य मा.शाला शेखपुरा पुराछिंदवाडा | Ongoing | 23848.35 | 0 | 2021-09-13
BHOPAL / PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1728002009/AV/22012034653359 — पुलिया निर्माण कार्य 3 रो, मनरेगा +15 वां वित्त, ग्राम पंचायत पुराछिंदवाडा | Ongoing | 150000 | 0 | 2024-02-19
BHOPAL / PHANDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002009/IF/22012034671499 — कपिलधारा कूप निर्माण सह खेत तालाब कामूबाइ/खुशीलाल पुराछिन्‍दवाडा | Ongoing | 291397.77 | 0 | 2021-05-10
BHOPAL / PHANDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002009/IF/22012034716007 — कपिलधारा कूप सह खेत तालाब निर्माण कार्य गोपीलाल / बलीराम, पुराछिंदवाडा | Ongoing | 294161.33 | 0 | 2021-05-24
BHOPAL / PHANDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002009/IF/22012034716010 — कपिलधारा कूप सह खेत तालाब निर्माण कार्य हजारी लाल / नर्बदा, पुराछिंदवाडा | Ongoing | 294161.33 | 0 | 2021-05-24
BHOPAL / PHANDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002009/IF/22012034898210 — कपिलधारा कूप निर्माण कार्य सहखेततालाब विश्राम / प्रेमनारायण, पुराछिंदवाडा | Ongoing | 296834.23 | 0 | 2021-11-29
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002009/IF/22012035435117 — खेत तालाब निर्माण कार्य राहुल / उमाशंकर, पुराछिंदवाडा | Ongoing | 147621.16 | 0 | 2025-05-07
BHOPAL / PHANDA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/2178920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3215623 | Ongoing | 27000 | 0 | 2019-08-05
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/3652634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115857097 | Approved | 27000 | 0 | 2022-04-21
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/3653388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119908136 | Ongoing | 27000 | 7200 | 2022-07-14
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4227561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119919038 | Ongoing | 27000 | 0 | 2026-06-08
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4573860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117572794 | Ongoing | 27000 | 0 | 2025-04-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4573861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117572816 | Ongoing | 27000 | 0 | 2025-04-14
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4573862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117572843 | Approved | 27000 | 0 | 2024-09-14
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4573866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117572958 | Approved | 27000 | 0 | 2024-09-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4573869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573435 | Ongoing | 27000 | 0 | 2025-07-21
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4588366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119920288 | Physically Completed | 27000 | 5400 | 2025-07-21 | 2026-09-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4641683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130911942 | Ongoing | 27000 | 0 | 2025-07-21
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4693192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115857412 | Approved | 27000 | 0 | 2024-09-16
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4698536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119302042 | Ongoing | 27000 | 3600 | 2025-12-29
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4702876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119918562 | Approved | 27000 | 0 | 2024-09-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4717790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131046440 | Ongoing | 27000 | 0 | 2025-06-02
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4761023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119912408 | Ongoing | 27000 | 3600 | 2026-08-17
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/4883614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113518207 | Ongoing | 27000 | 0 | 2025-04-07
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5490046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115857050 | Ongoing | 27000 | 1800 | 2025-08-18
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5490276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115243632 | Approved | 27000 | 0 | 2025-02-13
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5490277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115244605 | Approved | 27000 | 0 | 2025-02-13
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5492694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131050011 | Approved | 27000 | 0 | 2025-02-13
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5492721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113517221 | Ongoing | 27000 | 14400 | 2026-08-17
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5492724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113517894 | Approved | 27000 | 0 | 2025-02-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5492843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129719073 | Approved | 27000 | 0 | 2025-04-02
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5493425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP139936608 | Ongoing | 27000 | 1800 | 2026-09-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5493691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573381 | Physically Completed | 27000 | 12000 | 2025-08-18 | 2026-09-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5607654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127580091 | Ongoing | 27000 | 3600 | 2026-02-16
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5608759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP139917640 | Ongoing | 27000 | 0 | 2025-07-21
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5723253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131046856 | Approved | 27000 | 0 | 2025-05-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5743580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130912043 | Approved | 27000 | 0 | 2025-04-16
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5747040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130929643 | Ongoing | 27000 | 1800 | 2026-08-17
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5747279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117572677 | Approved | 27000 | 0 | 2025-02-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5748221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127324670 | Approved | 27000 | 0 | 2025-04-02
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5762414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573128 | Ongoing | 27000 | 0 | 2026-01-12
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5762866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP139940195 | Approved | 27000 | 0 | 2025-02-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5763665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127584914 | Approved | 27000 | 0 | 2025-04-02
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5764077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140563819 | Approved | 27000 | 0 | 2025-02-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5821290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126886201 | Ongoing | 27000 | 1800 | 2026-02-05
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5824892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP139923713 | Ongoing | 27000 | 0 | 2025-11-03
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5826834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127157811 | Ongoing | 27000 | 7200 | 2026-08-17
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5828567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115856632 | Approved | 27000 | 0 | 2025-05-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5903297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130924020 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5905162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115243573 | Ongoing | 27000 | 9000 | 2026-06-22
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5905907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119916201 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5906972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127156952 | Approved | 27000 | 0 | 2026-01-29
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5907390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130930595 | Ongoing | 27000 | 3600 | 2026-09-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5909184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130930558 | Approved | 27000 | 0 | 2026-01-29
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5910650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119918494 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5910783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119914962 | Approved | 27000 | 0 | 2026-01-29
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5912993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130923972 | Approved | 27000 | 0 | 2026-01-29
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5913142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117572635 | Ongoing | 27000 | 9000 | 2026-08-03
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5913514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130911840 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5913883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130929943 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5915406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131048327 | Approved | 27000 | 0 | 2026-01-29
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5917365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113518457 | Ongoing | 27000 | 5400 | 2026-08-17
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5917658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130930057 | Approved | 27000 | 0 | 2026-01-29
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5917832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131046747 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5918000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117572750 | Ongoing | 27000 | 1800 | 2026-09-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5919727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127584214 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5922955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115243528 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5925138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130911740 | Ongoing | 27000 | 1800 | 2026-06-08
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5930366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115244656 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5930847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117574021 | Approved | 27000 | 0 | 2026-01-29
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5931630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573742 | Ongoing | 27000 | 3600 | 2026-09-14
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5935988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127586432 | Ongoing | 27000 | 1800 | 2026-09-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5936095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115244557 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/5941731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117572771 | Ongoing | 27000 | 18000 | 2026-08-17
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6122702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119920347 | Approved | 27000 | 0 | 2026-01-29
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6122704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119920453 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6123113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119918437 | Approved | 27000 | 0 | 2026-03-05
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6124685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115244699 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6125753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119909866 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6125760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119913349 | Ongoing | 27000 | 3600 | 2026-08-03
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6125761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119914542 | Approved | 27000 | 0 | 2026-03-05
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6125763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119915377 | Approved | 27000 | 0 | 2026-01-29
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6125766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119916934 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6125768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119916992 | Approved | 27000 | 0 | 2026-03-05
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6130521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127151983 | Approved | 27000 | 0 | 2026-01-29
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6131815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130929981 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6131818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130930195 | Ongoing | 27000 | 7200 | 2026-06-22
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6132182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130911728 | Ongoing | 27000 | 3600 | 2026-09-14
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6132184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130911780 | Ongoing | 27000 | 0 | 2026-05-18
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6132185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130911797 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6132189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130911931 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6133491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127582928 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6136914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107068139 | Ongoing | 27000 | 9000 | 2026-08-03
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6139865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140386324 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6143961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130923988 | Approved | 27000 | 0 | 2026-01-29
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6144160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119915069 | Ongoing | 27000 | 1800 | 2026-09-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6147669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115245142 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6147670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119915791 | Approved | 27000 | 0 | 2026-03-05
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6147672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119915837 | Approved | 27000 | 0 | 2026-03-05
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6147673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119915883 | Ongoing | 27000 | 3600 | 2026-09-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6148193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113517453 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6148194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113518127 | Ongoing | 27000 | 10800 | 2026-06-22
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6152666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131050050 | Ongoing | 27000 | 1800 | 2026-09-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6154374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140498319 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6156796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131046819 | Ongoing | 27000 | 3600 | 2026-09-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6158391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130929742 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6158393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131048090 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6158677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131048140 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6162923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119914638 | Approved | 27000 | 0 | 2026-03-05
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6163781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127163275 | Ongoing | 27000 | 1800 | 2026-09-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6166475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573899 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6166550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127120397 | Approved | 27000 | 0 | 2026-03-05
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6168417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573707 | Ongoing | 27000 | 3600 | 2026-06-22
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6172381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131048435 | Approved | 27000 | 0 | 2026-03-05
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6173366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117574344 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6175041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130930406 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6175042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130930532 | Approved | 27000 | 0 | 2026-02-23
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6175044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130930738 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/6245285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127587676 | Approved | 27000 | 0 | 2026-01-20
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002009/IF/IAY/84995 — Construction of IAY House -IAY REG. NO. MP-28-002-009-001/018 | Approved | 27000 | 0 | 2016-01-11
BHOPAL / PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002009/RC/22012034655267 — खेत सडक निर्माण कार्य मनरेगा+जनभागीदारी, सुनीता बाई से इमरत के खेत तक, पुराछिंदवाडा | Ongoing | 2734000 | 0 | 2023-10-06
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002009/RC/22012034679926 — सी सी रोड निर्माण ग्राम पंचायत पुराछिंदवाडा | New | 0 | 0 | 2024-04-14
BHOPAL / PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002009/RC/22012034849407 — सी सी रोड निर्माण मनरेगा +15 वां वित्त स्‍कूल गेट से शाला भवन तक, पुराछिंदवाडा | Approved | 60000 | 0 | 2025-04-14
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002009/RS/22012035130230 — पाईप नाली निर्माण कार्य मनरेगा +15 वां वित्त उधम से जमना प्रसाद के घर तक, पुराछिंदवाडा | Approved | 42572 | 0 | 2024-06-08
BHOPAL / PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002009/RS/22012035138641 — पाईप नाली निर्माण कार्य मनरेगा +15 वां वित्त सुरेश से सुखी बाई के घर तक, पुराछिंदवाडा | Approved | 37500 | 0 | 2025-04-14
BHOPAL / PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002009/RS/22012035138642 — पाईप नाली निर्माण कार्य मनरेगा +15 वां वित्त रमेश से भैयालाल के घर की ओर, पुराछिंदवाडा | Approved | 25900 | 0 | 2025-04-14
BHOPAL / PHANDA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002009/WC/22012034429618 — MWC चेक डेम निर्माण राम मोहन के खेत के पास पुराछिंदवाडा | Ongoing | 785000 | 0 | 2019-01-28
BHOPAL / PHANDA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1728002009/WC/VB/22012035332479 — रेन वाटर हार्वेस्टिंग कार्य सामुदायिक भवन, ग्राम पंचायत पुराछिंदवाडा | Approved | 0 | 0 | 2026-07-10