## Work List
Exported on: 2026-09-11 02:11:11
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MUGALIYA HAT
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHOPAL / PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002012/DP/22012034583469 — व़क्षारोपण कार्य पंचायत भवन परिसर, मुगालियाहाट | Ongoing | 134212.69 | 0 | 2023-08-15
BHOPAL / PHANDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002012/DP/22012034622608 — सामुदायिक वृक्षारोपण कार्य पंचायत भवन व शांतिधाम परिसर, ग्राम पंचायत मुगालियाहाट | Approved | 0 | 0 | 2024-06-08
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002012/IF/22012034916324 — कपिलधारा कूप निर्माण सह खेततालाब कार्य जगदीश / रामफूल प्रजापति, मुगालियाहाट | Ongoing | 296834.23 | 0 | 2022-05-25
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002012/IF/22012034976094 — कपिलधारा कूप निर्माण कार्य सह खेत तालाब धापू बाई / रमेश प्रसाद, मुगालियाहाट | Ongoing | 306971.28 | 0 | 2022-05-10
BHOPAL / PHANDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1728002012/IF/22012035556727 — डगवेल रिर्चाज निर्माण राहुल / कैलाश के कूप के पास, ग्राम पंचायत मुगालियाहाट | Approved | 25899.46 | 0 | 2025-04-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1728002012/IF/22012035584655 — एक बगिया मॉं के नाम ममता बाई / रमेश, MP28002012001/57, मुगालियाहाट | Ongoing | 281858.62 | 0 | 2025-08-26
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/130110 — Construction of IAY House -IAY REG. NO. MP-28-002-012-001/34 | Approved | 27000 | 0 | 2016-02-08
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/3671950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114130157 | Ongoing | 27000 | 0 | 2022-07-16
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/4555409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114133209 | Ongoing | 27000 | 0 | 2025-03-04
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/4555412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114133304 | Ongoing | 27000 | 0 | 2024-12-31
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/4578204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118117381 | Ongoing | 27000 | 0 | 2024-11-26
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/4578650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118062914 | Ongoing | 27000 | 0 | 2024-11-26
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/4578665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118064448 | Ongoing | 27000 | 0 | 2024-10-08
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/4636232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130463840 | Ongoing | 27000 | 0 | 2024-12-03
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/4697989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118118547 | Ongoing | 27000 | 0 | 2025-02-04
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5115451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130463740 | Approved | 27000 | 0 | 2025-02-10
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5117548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140390563 | Ongoing | 27000 | 5400 | 2026-06-23
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5118235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118120067 | Ongoing | 27000 | 1200 | 2026-09-03
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5125130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120390252 | Approved | 27000 | 0 | 2025-03-03
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5127595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130462747 | Approved | 27000 | 0 | 2025-02-17
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5247186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114971355 | Approved | 27000 | 0 | 2025-02-10
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5264169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117412665 | Ongoing | 27000 | 0 | 2026-05-26
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5268886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122101543 | Ongoing | 27000 | 1800 | 2026-05-19
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5280597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120313087 | Ongoing | 27000 | 0 | 2025-07-08
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5288730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120253204 | Ongoing | 27000 | 0 | 2026-06-16
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5442352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122105568 | Physically Completed | 27000 | 5400 | 2026-06-23 | 2026-09-06
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5445945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117317616 | Approved | 27000 | 0 | 2025-03-03
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5448136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114133169 | Physically Completed | 23490 | 0 | 2026-05-05 | 2026-07-12
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5449979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115209005 | Approved | 27000 | 0 | 2025-03-03
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5450138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124804844 | Approved | 27000 | 0 | 2025-03-03
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5451070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114129987 | Approved | 27000 | 0 | 2025-02-17
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5451071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114130224 | Approved | 27000 | 0 | 2025-02-10
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/54787 — Construction of IAY House -IAY REG. NO. MP-28-002-012-001/96 | Approved | 27000 | 0 | 2015-12-15
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/54795 — Construction of IAY House -IAY REG. NO. MP-28-002-012-001/130 | Approved | 27000 | 0 | 2015-12-15
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5519862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117412594 | Ongoing | 27000 | 0 | 2025-09-30
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5522204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117321021 | Approved | 27000 | 0 | 2025-03-03
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5590172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117320740 | Approved | 27000 | 0 | 2025-02-10
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5590478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120889764 | Approved | 27000 | 0 | 2025-02-17
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5590843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120390968 | Physically Completed | 27000 | 7200 | 2026-06-16 | 2026-09-06
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5694722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122854803 | Approved | 27000 | 0 | 2025-02-10
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5721181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118115882 | Approved | 27000 | 0 | 2025-03-03
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5721958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114971193 | Approved | 27000 | 0 | 2025-02-17
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5730453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124801972 | Approved | 27000 | 0 | 2025-03-03
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5798552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118063003 | Physically Completed | 23490 | 0 | 2026-02-17 | 2026-07-19
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5903477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117322174 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5903744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120391906 | Ongoing | 27000 | 1200 | 2026-09-03
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5908568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122852060 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5909385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117313711 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5909965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122095488 | Ongoing | 27000 | 7200 | 2026-06-02
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5911430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120388579 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5911504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118118000 | Ongoing | 27000 | 1200 | 2026-09-03
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5912186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122023720 | Ongoing | 27000 | 10800 | 2026-06-16
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5912306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117321392 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5912688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130462679 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5914100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118115606 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5914294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120244944 | Ongoing | 27000 | 0 | 2026-05-19
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5914840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118064715 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5915677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115209588 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5916471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122102591 | Ongoing | 27000 | 0 | 2026-04-21
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5920021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124799110 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5924296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118118162 | Ongoing | 27000 | 1200 | 2026-09-03
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5924959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114971269 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5925737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130463913 | Approved | 27000 | 0 | 2026-01-21
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5926022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114971594 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5926087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120392022 | Ongoing | 27000 | 3600 | 2026-06-16
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5926534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122108289 | Approved | 27000 | 0 | 2026-01-13
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5928774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115209797 | Ongoing | 27000 | 6600 | 2026-06-16
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5929168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124801429 | Ongoing | 27000 | 9000 | 2026-06-16
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/5929542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120393519 | Ongoing | 27000 | 1200 | 2026-09-03
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/6071810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114971800 | Ongoing | 27000 | 3600 | 2026-09-01
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/6077389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118118814 | Ongoing | 27000 | 10800 | 2026-07-15
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/6080196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120393259 | Approved | 27000 | 0 | 2026-03-09
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/6092927 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130462579 | Ongoing | 27000 | 0 | 2026-09-03
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/6243525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118118651 | Approved | 27000 | 0 | 2026-03-24
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/6244736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115208920 | Ongoing | 27000 | 0 | 2026-09-08
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/6245274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124805408 | Ongoing | 27000 | 1200 | 2026-09-03
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/67385 — Construction of IAY House -IAY REG. NO. MP-28-002-012-001/74 | Approved | 27000 | 0 | 2015-12-30
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/85021 — Construction of IAY House -IAY REG. NO. MP-28-002-012-001/26 | Approved | 27000 | 0 | 2016-01-11
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/85024 — Construction of IAY House -IAY REG. NO. MP-28-002-012-001/28 | Approved | 27000 | 0 | 2016-01-11
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002012/IF/IAY/85026 — Construction of IAY House -IAY REG. NO. MP-28-002-012-001/80 | Approved | 27000 | 0 | 2016-01-11
BHOPAL / PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002012/RC/22012034636782 — सुदूर सडक निर्माण मनरेगा+जनभागीदारी जितेंद्र मेहर के घर से हाईवे झिरनिया मेड तक, मुगालियाहाट | Ongoing | 3359000 | 0 | 2023-05-23
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002012/RC/22012034679837 — सुदूर निर्माण कार्य बाबा साहब से रातीबढ कांकड की ओर मुगालियाहाट | New | 0 | 0 | 2024-04-14
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1728002012/RS/22012035137070 — सामुदायिक स्‍वच्‍छता परिसर निर्माण मनरेगा + 15 वां वित्त +एसबीएम, हनुमान मंदिर के पास, मुगालियाहाट | Approved | 44000 | 0 | 2024-06-08
BHOPAL / PHANDA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002012/WC/22012034527764 — पोण्‍ड निर्माण कार्य ग्राम पंचायत मुगालियाहाट | Ongoing | 101997.1 | 0 | 2020-03-17
BHOPAL / PHANDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1728002012/WC/22012035229342 — पोण्ड निर्माण कार्य ग्राम पंचायत मुगालियाहाट | Approved | 0 | 0 | 2024-06-08
BHOPAL / PHANDA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1728002012/WC/VB/22012035332481 — रेन वाटर हार्वेस्टिंग कार्य सामुदायिक शेड, ग्राम पंचायत मुगालियाहाट | Approved | 0 | 0 | 2026-07-10