## Work List
Exported on: 2026-09-26 00:18:57
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: SEMRI BAZYAFT
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHOPAL / PHANDA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1728002069/AV/22012034582056 — डायनिंग हॉल में बेंच निर्माण कार्य प्रा.शाला, सेमरीबाजयाफत | Closed | 26881.94 | 0 | 2021-04-14
BHOPAL / PHANDA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1728002069/AV/22012034586481 — माँ की बगिया निर्माण कार्य मा.शाला सेमरीबाजयाफ्त | Closed | 37953.5 | 0 | 2021-04-14
BHOPAL / PHANDA | 2022-2023 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1728002069/AV/22012034621337 — सेग्रीगेशन शेड निर्माण कार्य मनरेगा +15 वां वित्‍त, सेमरीवाजयाफ़त | Completed | 20000 | 19992 | 2022-09-13 | 2022-11-09
BHOPAL / PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1728002069/AV/22012034653101 — आगनवाड़ी भवन निर्माण बाउण्ड्रीवॉल साहित,मनरेगा +महिला बाल विकास,खारपा, सेमरीबाजयाफ्त | Completed | 500000 | 410821.05 | 2024-03-15 | 2026-04-01
BHOPAL / PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002069/DP/22012034581121 — व़क्षारोपण कार्य पंचायत भवन परिसर, सेमरीबाजयाफत | Ongoing | 427106.07 | 6630 | 2023-08-08
BHOPAL / PHANDA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1728002069/DP/468 — व़क्षारोपण कार्य, शाला परिसर एवं शमशान के पास, सेमरीबाज्‍यफ | Completed | 55000 | 29125 | 2010-08-09 | 2016-08-18
BHOPAL / PHANDA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1728002069/DP/9926695142 — निर्मल वाटिका निर्माण कार्य 66 हितग्राही ग्राम पंच | Completed | 350000 | 71136 | 2012-05-29 | 2013-03-31
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/22012034302648 — मनरेगा+इंदिरा आवास अभिसरण हीरा बाई / अमर सिंह, सेमरीबाजयाफत | Completed | 16000 | 15030 | 2016-11-15 | 2016-12-16
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002069/IF/22012035422042 — खेत तालाब निर्माण कार्य शैतान सिंह / हरि प्रसाद, सेमरीवाजयाफ्त | Approved | 570989.21 | 0 | 2025-04-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002069/IF/22012035451807 — खेत तालाब निर्माण्‍ा कार्य अमित / गंगाराम, खारपा, सेमरीबाजयाफ्त | Ongoing | 347409.68 | 1566 | 2025-05-06
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002069/IF/22012035452640 — खेत तालाब निर्माण्‍ा कार्य अमित / गंगाराम, खारपा, सेमरीबाजयाफ्त | New | 0 | 0 | 2025-04-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002069/IF/22012035469850 — खेत तालाब निर्माण कार्य राजेन्द्र / राम चरण, सेमरीवाजयाफ्त | Physically Completed | 347409.68 | 294834.38 | 2025-05-06 | 2026-05-05
BHOPAL / PHANDA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002069/IF/67 — कूप निर्माण प्रीतमसिंह/हरप्रसाद सेमरीवाज्‍याफत | Completed | 279000 | 277271 | 2009-05-22 | 2012-03-15
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002069/IF/9993668708 — पशु शेड निर्माण संतोष /छीतर सिंह सेमरीबाजयाफत | Completed | 57876 | 53383 | 2015-07-07 | 2015-08-17
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002069/IF/9993668710 — पशु शेड निर्माण अजय/मोहनसिंह सेमरीबाजयाफत | Deleted | 57876 | 0 | 2015-07-01
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/9993747305 — मनरेगा+इंदिरा आवास अभिरसरण इम्तियाज बी / नबाब खॉं, सेमरीबाजयाफ्त | Completed | 16000 | 12024 | 2016-06-28 | 2016-07-19
BHOPAL / PHANDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/9993747719 — मनरेगा+इंदिरा आवास अभिसरण छोटी बाई / रामफूल सेमरीबाजयाफ्त | Completed | 16000 | 12556 | 2017-06-13 | 2017-08-02
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/3681303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113722935 | Completed | 18360 | 17952 | 2022-07-15 | 2023-07-12
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/3683202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113729717 | Completed | 18360 | 16932 | 2022-07-15 | 2024-03-26
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/4146046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121394692 | Completed | 18360 | 17952 | 2022-07-15 | 2023-07-12
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/4703080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121361054 | Approved | 27000 | 0 | 2024-09-23
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/4705570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122788101 | Ongoing | 27000 | 18954 | 2024-12-03
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/4707272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122484247 | Ongoing | 27000 | 10638 | 2025-03-11
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/4763489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121676754 | Physically Completed | 23490 | 20412 | 2024-11-12 | 2026-06-15
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/4773546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122527459 | Approved | 27000 | 0 | 2024-09-23
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/535900 — Construction of IAY House -IAY REG. NO. MP2952472 | Completed | 15030 | 5010 | 2017-02-14 | 2021-11-11
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/54829 — Construction of IAY House -IAY REG. NO. MP-28-002-069-002/28 | Approved | 27000 | 0 | 2015-12-15
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/54830 — Construction of IAY House -IAY REG. NO. MP-28-002-069-002/52 | Approved | 27000 | 0 | 2015-12-15
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5521050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121755811 | Approved | 27000 | 0 | 2025-02-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5522170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116134324 | Completed | 23490 | 21924 | 2025-05-20 | 2026-01-07
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5522763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116106441 | Physically Completed | 23490 | 22968 | 2026-05-07 | 2026-06-12
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5523484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121350342 | Completed | 23490 | 22185 | 2025-07-22 | 2026-01-07
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5524017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121707087 | Completed | 23490 | 21924 | 2025-06-17 | 2025-11-28
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5524333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122814310 | Completed | 23490 | 21924 | 2025-07-22 | 2026-01-07
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5524562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122452661 | Completed | 23490 | 21924 | 2025-06-17 | 2026-01-07
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5525406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125546442 | Completed | 23490 | 21924 | 2025-07-22 | 2026-01-07
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5526092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113709316 | Approved | 27000 | 0 | 2025-02-13
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5526101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121720552 | Completed | 23490 | 22446 | 2025-07-22 | 2026-01-07
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5526198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116130377 | Physically Completed | 23490 | 0 | 2025-02-13 | 2025-12-25
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5527528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113740603 | Approved | 27000 | 0 | 2025-04-02
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5527687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113763611 | Physically Completed | 23490 | 15660 | 2025-05-20 | 2026-06-14
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5528012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121393896 | Completed | 23490 | 21402 | 2025-05-20 | 2026-01-07
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5528082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116145842 | Completed | 23490 | 22446 | 2025-07-15 | 2026-01-07
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5529321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113756816 | Completed | 23490 | 21924 | 2025-05-20 | 2026-01-07
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5529358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125812218 | Completed | 23490 | 22185 | 2025-07-15 | 2025-11-28
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5529712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114208484 | Physically Completed | 23490 | 20358 | 2025-05-20 | 2026-06-15
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5529763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116111116 | Completed | 23490 | 22446 | 2025-10-07 | 2026-01-07
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5530567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116108539 | Physically Completed | 23490 | 0 | 2025-02-13 | 2026-04-19
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5531684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126490639 | Completed | 23490 | 22707 | 2025-06-17 | 2026-01-07
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5532395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116116023 | Completed | 23490 | 21924 | 2025-06-17 | 2025-11-28
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5570204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115421633 | Completed | 23490 | 23229 | 2025-06-17 | 2025-11-28
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5571092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122457691 | Approved | 27000 | 0 | 2025-04-21
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5571990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122531462 | Approved | 27000 | 0 | 2025-04-21
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/567745 — Construction of IAY House -IAY REG. NO. MP3963098 | Deleted | 15030 | 0 | 2017-02-14
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5907493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114843378 | Ongoing | 27000 | 18792 | 2026-05-26
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5907499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116120299 | Ongoing | 27000 | 15000 | 2026-01-28
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5914315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114199847 | Approved | 27000 | 0 | 2026-01-28
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5922428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125612262 | Ongoing | 27000 | 5100 | 2026-01-28
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5924314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122805287 | Ongoing | 27000 | 23490 | 2026-05-19
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5926041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113745447 | Ongoing | 27000 | 15660 | 2026-05-26
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5926593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125549759 | Ongoing | 27000 | 9000 | 2026-01-28
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5927180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114195257 | Ongoing | 27000 | 21924 | 2026-05-26
BHOPAL / PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5929119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114214863 | Ongoing | 27000 | 6264 | 2026-06-02
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5931059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116125034 | Approved | 27000 | 0 | 2026-01-28
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/5936280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125855046 | Approved | 27000 | 0 | 2025-07-01
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002069/IF/IAY/6245248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121671323 | Approved | 27000 | 0 | 2026-03-13
BHOPAL / PHANDA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1728002069/LD/22012034300515 — शांति धाम निर्माण ग्राम पंचायत सेमरी वज्याफ्त | Completed | 245300 | 172423.92 | 2017-01-31 | 2017-09-19
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034154495 — सी सी रोड निर्माण पंचपरमेश्‍वर ग्राम पंचायत सेमरी | Completed | 466000 | 160026 | 2012-06-14 | 2012-07-30
BHOPAL / PHANDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034171223 — सी सी सड्क पंचपरमेश्‍वर निर्माण कार्य पुलिया से गो | Completed | 173000 | 161908 | 2013-06-13 | 2013-12-25
BHOPAL / PHANDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034188602 — सी सी रोड पंचपरमेश्‍वर निमार्ण कार्य जगदीश के मकान | Completed | 178388 | 161722 | 2013-10-04 | 2014-12-04
BHOPAL / PHANDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034291521 — सी सी रोड पंचपमेश्‍वर ज्ञानवती के घर से हनुमान मंदिर की ओर सेमरीबाजयाफ्त | Completed | 499900 | 109962 | 2015-12-15 | 2016-05-25
BHOPAL / PHANDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034306551 — सी सी रोड पंचपरमेश्‍वर हेमराज से पप्‍पू के घर तक सेमरीबाजयाफत | Deleted | 0 | 0 | 2015-10-02
BHOPAL / PHANDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034306552 — सी सी रोड पंचपरमेश्‍वर गोपचंद्र बाबा के चबूतरे से हनुमान मंदिर तक सेमरीबाजयाफत | Deleted | 0 | 0 | 2015-10-02
BHOPAL / PHANDA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034313534 — सी सी रोड परफार्मेंस ग्रांट रमेश से ज्ञानवती के घर की ओर, सेमरीबाजयाफत | Completed | 22900 | 19038 | 2016-08-02 | 2016-08-11
BHOPAL / PHANDA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034316538 — सी सी रोड पंचपरमेश्‍वर शांति धाम पहुंच मार्ग, सेमरीबाजयाफत | Completed | 110500 | 107882 | 2016-11-29 | 2017-04-18
BHOPAL / PHANDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034323364 — c.c.road semri bajyafat | Deleted | 0 | 0 | 2017-04-14
BHOPAL / PHANDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034330776 — सी.सी.रोड पंचपरमेश्‍वर अजब के घर से डीपी की ओर सेमरी वजयाफात | Completed | 36993 | 35088 | 2017-04-04 | 2017-06-13
BHOPAL / PHANDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034337325 — सी सी रोड पंचपरमेश्वर प्रीतम से मानसिंह के घर तक सेमरीबाज्यफ्त | Completed | 39939 | 37496 | 2017-05-16 | 2017-08-17
BHOPAL / PHANDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034352907 — सी सी रोड पंचपरमेश्वर हेमराज के घर से शेषराम,हनुमान मंदिर के सामने,राम मंदिर के सामने सेमरीबाज्याफ्त | Completed | 60000 | 59856 | 2017-09-19 | 2018-03-13
BHOPAL / PHANDA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034370650 — सी सी रोड पंचपरमेश्‍वर मनरेगा जयराम से जगदीश के घर की ओर, सेमरीबजायाफत | Completed | 53475 | 52380 | 2018-12-26 | 2019-07-26
BHOPAL / PHANDA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034388716 — सी सी रोड पंचपरमेश्‍वर स्‍कूल परिसर से कालूराम के घर की ओर सेमरीबाजयाफत | Completed | 32302 | 32190 | 2018-05-29 | 2018-10-18
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034437504 — C C ROAD NIRMAN KARYA GYANWATI BAI KE GHAR SE SANTOSH KE GHAR | Closed | 0 | 0 | 2019-04-14
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034437702 — CC ROAD PANCHPERMESHWAR | Closed | 0 | 0 | 2019-04-14
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034437705 — CC ROAD PANCHPERMESHWAR | Closed | 0 | 0 | 2019-04-14
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034437707 — CC ROAD PANCHPERMESHWAR | Closed | 0 | 0 | 2019-04-14
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002069/RC/22012034439083 — ग्रेबल रोड रूपसिंह के घर से शांतिधाम की ओर | Closed | 1422905.11 | 0 | 2019-04-14
BHOPAL / PHANDA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034463166 — सी सी रोड पंचपरमेश्‍वर रूपसिंह के मकान से शांतिधाम की ओर, खारपा ग्राम पंचायत सेमरीबाजयाफत | Completed | 74000 | 72264 | 2019-03-12 | 2020-10-29
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034468343 — सी सी रोड पंचपरमेश्‍वर दशरथ से अजब सिंह के घर की ओर सेमरीबाजयाफत | Completed | 55200 | 54204 | 2019-06-25 | 2020-08-24
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034468348 — सी सी रोड पंचपरमेश्‍वर लीलाकिशन से राधेश्‍याम के घर की ओर सेमरीबाजयाफत | Completed | 74000 | 72336 | 2019-06-25 | 2020-03-05
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034511742 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त दशरथ से श्‍याम लाल के घर की ओर, सेमरीबाजयाफत | Completed | 46500 | 44566 | 2020-01-28 | 2020-12-11
BHOPAL / PHANDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002069/RC/22012034537611 — सुदूर ग्राम संपर्क सडक तालाब से झागरिया रोड की ओर, सेमरीबाजयाफत | Completed | 1422808.36 | 1406065.41 | 2021-03-16 | 2024-07-05
BHOPAL / PHANDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002069/RC/22012034537612 — खेत सडक निर्माण कार्य हनुमान मंदिर जगदीश के खेत की ओर, सेमरीबाजयाफत | Completed | 1422808.36 | 1372819.04 | 2020-09-29 | 2024-07-08
BHOPAL / PHANDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034543885 — सी सी रोड निर्माण कार्य अभिसरण मनरेगा+15वॉं वित्‍त पप्‍पु से केशरसिंह के घर की ओर, सेमरीबाजायाफत | Completed | 69285 | 41040 | 2020-10-20 | 2022-10-01
BHOPAL / PHANDA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034619453 — सी सी रोड सहनाली निर्माण मनरेगा+15वां वित्त मेनरोड से फूलसिंह के मकान की ओर, खारपा, सेमरीबाजयाफत | Completed | 69750 | 60180 | 2022-11-15 | 2023-03-25
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034652811 — सी सी निर्माण कार्य मनरेगा+15 वां वित्‍त, पुलिया से रमेश के घर तक, खारपा, सेमरीबाजयाफत | Completed | 76000 | 27459 | 2024-07-02 | 2026-05-13
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034652818 — सी सी निर्माण कार्य मनरेगा+15 वां वित्‍त, जमना प्रसाद से ओमप्रकश के घर की ओर, सेमरीबाजयाफत | Completed | 40500 | 38394 | 2024-08-20 | 2025-01-07
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034680942 — सी सी रोड निर्माण जमना प्रसाद से ओमप्रकाश के घर की ओर सेमरीबाजयाफ्त | New | 0 | 0 | 2024-04-14
BHOPAL / PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034839841 — सी सी रोड निर्माण मनरेगा +5 वां वित्त मेन रोड खारपा से शमशान की ओर, खारपा, सेमरीबाजयाफत | Completed | 65850 | 49590 | 2025-05-26 | 2026-04-01
BHOPAL / PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002069/RC/22012034839850 — सी सी रोड निर्माण मनरेगा +5 वां वित्त मेन रोड से आंगनबाडी की ओर, खारपा, सेमरीबाजयाफत | Completed | 24000 | 23229 | 2025-05-06 | 2026-04-01
BHOPAL / PHANDA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002069/RS/22012034384168 — नाडेप निर्माण कार्य सेमरीबाजयाफत | Closed | 0 | 0 | 2018-04-14
BHOPAL / PHANDA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002069/RS/22012034384911 — NADEP NIRMAN KARYA SEMRIBAZAFAT | Closed | 0 | 0 | 2018-04-14
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1728002069/RS/22012034436848 — nadep nirman | Closed | 0 | 0 | 2019-04-14
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1728002069/RS/22012034436850 — nadep nirman | Closed | 0 | 0 | 2019-04-14
BHOPAL / PHANDA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002069/RS/22012034621985 — नाडेप निर्माण कार्य मनरेगा +15 वां वित्त (संख्या 05) सेमरीबाजयाफ्त | Completed | 9490 | 1836 | 2022-04-19 | 2022-06-15
BHOPAL / PHANDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002069/RS/22012034629602 — लीच पिट निर्माण मनरेगा +15 वां वित्त (संख्या 10), सेमरीबाजयाफ्त | Completed | 11383 | 11001 | 2022-01-25 | 2022-05-12
BHOPAL / PHANDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002069/RS/22012034643297 — लीच पिट निर्माण कार्य मनरेगा +15 वां वित्त, (संख्या 10), खारपा ग्राम पंचायत सेमरीबाजयाफ्त | Completed | 11383 | 10206 | 2022-03-01 | 2022-12-25
BHOPAL / PHANDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002069/RS/22012034643325 — नाडेप निर्माण कार्य मनरेगा +15 वां वित्त (संख्या 5), खारपा, सेमरीबाजयाफ्त | Closed | 0 | 0 | 2021-10-02
BHOPAL / PHANDA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002069/RS/22012034643326 — नाडेप निर्माण कार्य मनरेगा +15 वां वित्त (संख्या 5), खारपा, सेमरीबाजयाफ्त | Completed | 9490 | 3672 | 2022-09-06 | 2024-09-04
BHOPAL / PHANDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002069/RS/22012034651862 — लीच पीट निर्माण कार्य संख्‍या 10 ग्राम पंचायत सेमरीबाजायफत | Closed | 0 | 0 | 2022-03-08
BHOPAL / PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002069/RS/22012034700384 — नाली निर्माण कार्य खारपा मंदिर के पास, सेमरीबाजयाफत | Ongoing | 1002785.06 | 884 | 2023-10-06
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002069/RS/22012035132489 — नाली निर्माण कार्य मनरेगा + 15 वां वित्त खारपा, ग्राम पंचायत सेमरीबाजयाफत | Approved | 46000 | 0 | 2024-06-08
BHOPAL / PHANDA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002069/WC/13 — निर्मलनीर/सोखता गडडा, सेमरी बाज्‍याफत | Completed | 55412119 | 12596.5 | 2009-04-09 | 2009-04-09
BHOPAL / PHANDA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002069/WC/22012034571745 — सोख्‍ता गढढा निर्माण कार्य स्‍कूल के पास, सेमरीबाजयाफत | Closed | 14283.77 | 0 | 2020-01-26
BHOPAL / PHANDA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002069/WC/22012034571746 — सोख्‍ता गढढा निर्माण कार्य हरिजन मोहल्‍ला, सेमरीबाजयाफत | Closed | 14283.77 | 0 | 2020-01-26
BHOPAL / PHANDA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002069/WC/22012034571748 — सोख्‍ता गढढा निर्माण कार्य लखन के घर केे पास, सेमरीबाजयाफत | Closed | 14283.77 | 0 | 2020-01-26
BHOPAL / PHANDA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002069/WC/22012034571749 — सोख्‍ता गढढा निर्माण कार्य श्‍यामलाल के मकान केे पास, सेमरीबाजयाफत | Closed | 14283.77 | 0 | 2020-01-26
BHOPAL / PHANDA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002069/WC/22012034571750 — सोख्‍ता गढढा निर्माण कार्य शासकीय कूप केे पास, सेमरीबाजयाफत | Closed | 14283.77 | 0 | 2020-01-26
BHOPAL / PHANDA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1728002069/WC/22012034631642 — तालाब क्षमता ब़द्धिकरण कार्य खारपा, सेमरीबाजयाफत | Closed | 0 | 0 | 2021-03-08
BHOPAL / PHANDA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1728002069/WC/22012034663168 — जल भराव क्षमता में ब़द्धिकरण कार्य, सेमरीबाजयाफत | Closed | 0 | 0 | 2021-04-14
BHOPAL / PHANDA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002069/WC/22012034692955 — गली प्‍लग / बोल्‍डर चेक निर्माण्‍ा कार्य, कंछेदी साहू के खेत वाला नाला, (संख्‍या 27), सेमरीबाजयाफत | Closed | 0 | 0 | 2021-04-14
BHOPAL / PHANDA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002069/WC/22012034692967 — गली प्‍लग / बोल्‍डर चेक निर्माण्‍ा कार्य, शमशान तालाब से जयराम की ओर वाला नाला, (36), सेमरीबाजयाफत | Closed | 0 | 0 | 2021-04-14
BHOPAL / PHANDA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002069/WC/22012034692972 — गली प्‍लग / बोल्‍डर चेक निर्माण्‍ा कार्य, स्‍टाप डेम से पुलिया वाला नाला, (संख्‍या 27), सेमरीबाजयाफत | Closed | 0 | 0 | 2021-04-14
BHOPAL / PHANDA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002069/WC/22012034692976 — गली प्‍लग / बोल्‍डर चेक निर्माण्‍ा कार्य, ज्‍वाल सिंह के खेत से पुलिया वाला नाला, (25), सेमरीबाजयाफत | Closed | 0 | 0 | 2021-04-14
BHOPAL / PHANDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002069/WC/22012034942637 — गली प्लग / बोल्डर चेक डेम निर्माण कार्य (संख्या 10), सेमरीबाजयाफ्त | Ongoing | 124715.53 | 5304 | 2022-04-12
BHOPAL / PHANDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Masonry/CC Anicut for Community / Repair and Maintenance of Masonry/CC Check Dam for Community | Repair & maint of Water Harvesting Structures | 1728002069/WC/22012034950639 — चेक डेम मरम्‍मत कार्य खुबीलाल के खेत के पास ग्राम पंचायत सेमरीबाज्‍याफत | Completed | 101227.75 | 99410.38 | 2022-05-03 | 2022-07-30
BHOPAL / PHANDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Masonry/CC Anicut for Community / Repair and Maintenance of Masonry/CC Check Dam for Community | Repair & maint of Water Harvesting Structures | 1728002069/WC/22012034950656 — चेक डेम मरम्‍मत कार्य हरिप्रसाद के खेत के पास ग्राम पंचायत सेमरीबाज्‍याफत | Completed | 152010.46 | 116920.8 | 2022-05-03 | 2022-09-25
BHOPAL / PHANDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Masonry/CC Anicut for Community / Repair and Maintenance of Masonry/CC Check Dam for Community | Repair & maint of Water Harvesting Structures | 1728002069/WC/22012034950664 — चेक डेम मरम्‍मत कार्य पप्‍पु मारन के खेत के पास ग्राम पंचायत सेमरीबाज्‍याफत | Completed | 126600.35 | 111068.05 | 2022-05-03 | 2022-08-25
BHOPAL / PHANDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Masonry/CC Anicut for Community / Repair and Maintenance of Masonry/CC Check Dam for Community | Repair & maint of Water Harvesting Structures | 1728002069/WC/22012034950687 — चेक डेम मरम्‍मत कार्य रामस्‍वरूप के खेत के पास ग्राम पंचायत सेमरीबाज्‍याफत | Completed | 151897.94 | 141465.54 | 2022-05-03 | 2022-10-10
BHOPAL / PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002069/WC/22012035125829 — सामुदायिक पोण्‍ड निर्माण कार्य खारपा, सेमरीबाजयाफत | Closed | 859450.44 | 0 | 2023-08-17
BHOPAL / PHANDA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002069/WC/76 — निर्मल नीर राम मंदिर सेमरीबाज्‍याफ्त | Completed | 12300 | 11940.4 | 2009-06-04 | 2009-05-01
BHOPAL / PHANDA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1728002069/WC/VB/22012035332107 — रेन वाटर हार्वेस्टिंग कार्य सामुदायिक शेड, सेमरीबाजयाफ्त | Approved | 0 | 0 | 2026-07-10