## Work List
Exported on: 2026-10-23 02:16:29
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: PHANDAKALAN
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHOPAL / PHANDA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1728002075/AV/22012034369215 — शांतिधाम कार्य बाग स्‍थल फंदा कला | Completed | 180000 | 171912.93 | 2017-10-28 | 2018-03-21
BHOPAL / PHANDA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1728002075/AV/22012034576106 — डायनिंग हॉल में बेंच निर्माण कार्य मा.शाला, फंदाकला | Completed | 26881.94 | 25514.01 | 2021-08-28 | 2022-06-06
BHOPAL / PHANDA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1728002075/DP/22012034490148 — मंदिर कुंज योजना व़क्षारोपण कार्य हरिहर मंदिर परिसर में, फंदाकला | Completed | 161671.42 | 68097 | 2020-08-22 | 2024-09-11
BHOPAL / PHANDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1728002075/DP/36 — व़क्षारोपण रेशम केन्‍द्र फन्‍दाकलां | Completed | 411000 | 140982 | 2008-07-22 | 2016-08-17
BHOPAL / PHANDA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1728002075/DP/9926690063 — Nirmal Vatika 100 gram panchayat Phandakala | Completed | 440000 | 206612 | 2011-03-17 | 2012-06-16
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1728002075/IF/22012034318905 — इंदिराआवास निर्माण कार्य कंचनबाई /बद्रीप्रसाद ग्राम पंचायत फंदा कला | Completed | 16000 | 15468 | 2017-03-18 | 2019-04-02
BHOPAL / PHANDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002075/IF/22012034340475 — वृक्षारोपण कार्य पंचायत भवन परिसर में फन्दाकला | Completed | 335000 | 67646 | 2017-05-20 | 2020-08-28
BHOPAL / PHANDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002075/IF/22012034340481 — वृक्षारोपण कार्य आंगनबाड़ी के पास फन्दाखुर्द, फन्दाकला | Completed | 335000 | 61553 | 2017-05-20 | 2020-08-28
BHOPAL / PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002075/IF/9993667209 — पशु शेड निर्माण प्रहलाद सिंह /वंशीलाल फंदाकला | Completed | 57875 | 53918.04 | 2015-06-27 | 2015-07-10
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/9993747488 — मनरेगा +इंद्रा आवास अभिसरण गंगा बाई / शेषराम ग्राम पंचायत फंदाकला | Completed | 16000 | 15758 | 2016-09-17 | 2017-04-28
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/9993747489 — मनरेगा +इंद्रा आवास अभिसरण राजल बाई / हेमराज ग्राम पंचायत फंदाकला | Completed | 16000 | 12024 | 2016-07-23 | 2017-08-28
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/9993749049 — मनरेगा +अभिशरण इन्द्रावास निर्माण कार्य तारा बाई /बाबूलाल ग्र.प. फन्दा कलां | Completed | 16000 | 15030 | 2016-07-23 | 2016-08-22
BHOPAL / PHANDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1017818 — Construction of IAY House -IAY REG. NO. MP1848306 | Completed | 15480 | 15354 | 2017-11-25 | 2018-06-30
BHOPAL / PHANDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1042416 — Construction of IAY House -IAY REG. NO. MP3146858 | Completed | 15480 | 15390 | 2017-12-16 | 2018-06-30
BHOPAL / PHANDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1177588 — Construction of IAY House -IAY REG. NO. MP1780064 | Completed | 15480 | 15342 | 2017-11-25 | 2018-06-30
BHOPAL / PHANDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1178701 — Construction of IAY House -IAY REG. NO. MP3088945 | Completed | 15480 | 15540 | 2017-11-25 | 2018-05-14
BHOPAL / PHANDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1178740 — Construction of IAY House -IAY REG. NO. MP3133702 | Completed | 15480 | 15426 | 2017-12-16 | 2018-07-07
BHOPAL / PHANDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1184837 — Construction of IAY House -IAY REG. NO. MP1784522 | Completed | 15480 | 15426 | 2017-11-25 | 2018-07-07
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1625662 — Construction of IAY House -IAY REG. NO. MP1850329 | Completed | 15660 | 15486 | 2018-08-04 | 2019-03-27
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1820911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2658493 | Completed | 15660 | 15486 | 2018-07-14 | 2019-03-07
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1828395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3638391 | Completed | 15660 | 15660 | 2018-07-14 | 2018-11-30
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5107160 | Completed | 15660 | 15138 | 2018-09-08 | 2018-12-18
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899288 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4580159 | Completed | 15660 | 15660 | 2018-09-01 | 2018-12-18
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5157792 | Completed | 15660 | 15312 | 2018-09-01 | 2019-01-21
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5235766 | Completed | 15660 | 15486 | 2018-09-08 | 2019-01-15
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4873940 | Completed | 15660 | 14616 | 2019-03-02 | 2019-03-27
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5307703 | Completed | 15660 | 15660 | 2018-09-01 | 2018-12-26
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4653600 | Completed | 15660 | 15312 | 2018-09-01 | 2018-12-18
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5144525 | Completed | 15660 | 15660 | 2018-09-01 | 2018-12-05
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5233385 | Completed | 15660 | 15660 | 2018-09-01 | 2018-12-26
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5257280 | Completed | 15660 | 14964 | 2018-09-08 | 2019-02-12
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5257410 | Completed | 15660 | 15486 | 2018-09-01 | 2019-02-12
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5300008 | Completed | 15660 | 15486 | 2018-09-08 | 2019-01-15
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5309213 | Completed | 15660 | 15660 | 2018-09-01 | 2018-12-18
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5355565 | Completed | 15660 | 15660 | 2018-09-08 | 2018-12-26
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5366444 | Completed | 15660 | 15138 | 2018-09-01 | 2019-02-12
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5402412 | Completed | 15660 | 15138 | 2018-09-08 | 2019-03-07
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5107287 | Completed | 15660 | 15312 | 2018-09-01 | 2019-01-21
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5107514 | Completed | 15660 | 15486 | 2018-09-08 | 2019-01-15
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1899976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5108048 | Completed | 15660 | 15312 | 2018-09-01 | 2019-03-07
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1900026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5499597 | Completed | 15660 | 15312 | 2018-09-01 | 2018-12-18
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1900030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5514669 | Completed | 15660 | 15486 | 2018-09-01 | 2019-03-27
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1900045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5571219 | Completed | 15660 | 14616 | 2018-09-01 | 2019-02-12
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1900047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5572307 | Completed | 15660 | 15312 | 2018-09-01 | 2019-03-27
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1900048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5572325 | Completed | 15660 | 15660 | 2018-09-08 | 2018-12-26
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1905072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5200894 | Completed | 15660 | 14616 | 2018-09-01 | 2019-03-27
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1925049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5331592 | Completed | 15660 | 15312 | 2018-09-08 | 2019-01-21
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1930845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1784554 | Completed | 15660 | 15660 | 2018-10-06 | 2019-02-15
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1930847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1934307 | Completed | 15660 | 15660 | 2018-10-20 | 2018-12-26
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1930849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1946091 | Completed | 15660 | 15660 | 2018-10-20 | 2018-12-26
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1930861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2644113 | Completed | 15660 | 15138 | 2018-10-06 | 2019-03-07
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1930877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3514499 | Completed | 15660 | 15660 | 2018-10-06 | 2018-12-26
BHOPAL / PHANDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1930883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3612731 | Completed | 15660 | 15312 | 2018-10-06 | 2019-01-21
BHOPAL / PHANDA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/1966334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2026062 | Completed | 15840 | 15840 | 2019-07-06 | 2020-01-28
BHOPAL / PHANDA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2053824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3546194 | Completed | 15840 | 15488 | 2019-07-06 | 2020-03-13
BHOPAL / PHANDA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2110847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4356825 | Completed | 17100 | 15818 | 2019-07-06 | 2020-12-30
BHOPAL / PHANDA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2149015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5242709 | Completed | 15840 | 15488 | 2019-07-06 | 2019-12-04
BHOPAL / PHANDA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2154981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5381508 | Completed | 15840 | 15488 | 2019-07-06 | 2019-11-19
BHOPAL / PHANDA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2155666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5396796 | Completed | 17100 | 15934 | 2019-07-06 | 2021-07-16
BHOPAL / PHANDA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2162102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5571249 | Completed | 15840 | 15488 | 2019-11-09 | 2020-03-13
BHOPAL / PHANDA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2184614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2602003 | Completed | 15840 | 15312 | 2019-10-12 | 2020-03-13
BHOPAL / PHANDA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2341181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4337004 | Completed | 15840 | 15312 | 2020-01-18 | 2020-03-26
BHOPAL / PHANDA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2353412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3533120 | Completed | 17100 | 15770 | 2020-05-02 | 2020-12-30
BHOPAL / PHANDA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2353462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5184444 | Completed | 17100 | 15770 | 2020-05-02 | 2020-12-30
BHOPAL / PHANDA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2353463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5224745 | Completed | 17100 | 15580 | 2020-05-02 | 2020-08-24
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/287990 — Construction of IAY House -IAY REG. NO. MP1365790 | Completed | 15030 | 15011 | 2017-03-04 | 2017-12-15
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/290941 — Construction of IAY House -IAY REG. NO. MP1370729 | Completed | 15030 | 14986 | 2017-02-18 | 2018-01-06
BHOPAL / PHANDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/291571 — Construction of IAY House -IAY REG. NO. MP1828479 | Completed | 15030 | 15308 | 2017-05-06 | 2017-12-15
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/291632 — Construction of IAY House -IAY REG. NO. MP1908229 | Completed | 15030 | 14939 | 2017-02-04 | 2018-01-06
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/291747 — Construction of IAY House -IAY REG. NO. MP2028952 | Completed | 15030 | 14891 | 2017-02-04 | 2018-02-09
BHOPAL / PHANDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/291763 — Construction of IAY House -IAY REG. NO. MP2042475 | Completed | 15030 | 14964 | 2017-11-18 | 2018-01-06
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/292007 — Construction of IAY House -IAY REG. NO. MP2090428 | Completed | 15030 | 14891 | 2017-02-18 | 2018-02-09
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/292392 — Construction of IAY House -IAY REG. NO. MP2671044 | Completed | 15030 | 14817 | 2017-02-04 | 2018-05-14
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/292667 — Construction of IAY House -IAY REG. NO. MP3240286 | Completed | 15030 | 15515 | 2017-02-18 | 2018-05-14
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/292776 — Construction of IAY House -IAY REG. NO. MP3536265 | Completed | 15030 | 14874 | 2017-02-04 | 2018-02-09
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/292795 — Construction of IAY House -IAY REG. NO. MP3588425 | Completed | 15030 | 15300 | 2017-02-18 | 2017-10-16
BHOPAL / PHANDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2944670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1829535 | Completed | 17100 | 15054 | 2021-06-12 | 2021-08-30
BHOPAL / PHANDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2944671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1938887 | Completed | 17100 | 16791 | 2021-06-05 | 2021-11-11
BHOPAL / PHANDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2944673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2025400 | Completed | 17100 | 16984 | 2021-06-05 | 2021-11-24
BHOPAL / PHANDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2952003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2719964 | Completed | 17100 | 16984 | 2021-06-05 | 2021-11-18
BHOPAL / PHANDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2955912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3186638 | Completed | 17100 | 16984 | 2021-06-05 | 2021-11-18
BHOPAL / PHANDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2963993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3898021 | Completed | 17100 | 16984 | 2021-06-12 | 2021-11-18
BHOPAL / PHANDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/2964580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4173561 | Completed | 17100 | 12738 | 2021-06-05 | 2021-12-07
BHOPAL / PHANDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/3223972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3531632 | Completed | 17370 | 16984 | 2021-08-21 | 2022-01-25
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/3661484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125826868 | Completed | 18360 | 17952 | 2022-05-21 | 2022-10-25
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/3662088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116096700 | Completed | 18360 | 17952 | 2022-05-21 | 2022-10-25
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/3662091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116096916 | Completed | 18360 | 17952 | 2022-05-21 | 2022-08-05
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/3662292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116427140 | Completed | 18360 | 18156 | 2022-06-04 | 2022-12-22
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/3812846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116510919 | Completed | 18360 | 18156 | 2022-05-28 | 2022-11-08
BHOPAL / PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/4175198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106747551 | Completed | 18360 | 17952 | 2022-06-25 | 2022-12-15
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/420922 — Construction of IAY House -IAY REG. NO. MP1333339 | Completed | 15030 | 334 | 2017-02-18 | 2021-11-11
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/4692921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116096414 | Completed | 23490 | 21599.28 | 2024-10-12 | 2026-03-09
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/4706365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123870166 | Completed | 21870 | 21613.19 | 2024-10-12 | 2025-03-12
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/4710951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125830136 | Completed | 23490 | 21395.76 | 2024-10-12 | 2026-03-09
BHOPAL / PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/4870291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116096631 | Completed | 23490 | 22180.89 | 2025-03-01 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5248300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116459905 | Completed | 23490 | 23415.84 | 2025-04-26 | 2025-07-18
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5251876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115667009 | Completed | 23490 | 21832.8 | 2025-05-03 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5267153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123865264 | Completed | 23490 | 23407.8 | 2025-04-26 | 2025-07-18
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5269028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113453311 | Completed | 23490 | 22380.88 | 2025-04-26 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5269501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125827423 | Completed | 23490 | 21832.8 | 2025-05-03 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5283239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115667461 | Completed | 23490 | 21860.88 | 2025-05-03 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5301065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116044100 | Completed | 23490 | 22616.82 | 2025-05-31 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5302408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116147636 | Completed | 23490 | 22381.12 | 2025-04-26 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5309947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123867706 | Completed | 23490 | 22371.88 | 2025-04-26 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5321806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106744611 | Completed | 23490 | 21838.8 | 2025-05-03 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5323615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115667355 | Completed | 23490 | 21866.88 | 2025-04-19 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5329821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115668388 | Completed | 23490 | 21866.88 | 2025-04-26 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5338015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106770768 | Completed | 23490 | 21838.08 | 2025-05-10 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5342817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125828500 | Completed | 23490 | 21838.8 | 2025-05-03 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5525161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106870718 | Completed | 23490 | 22365.81 | 2025-05-17 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5573113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127170849 | Completed | 23490 | 21816.78 | 2025-05-31 | 2026-03-09
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/5610117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127171443 | Completed | 23490 | 23226 | 2025-06-21 | 2026-03-09
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/576725 — Construction of IAY House -IAY REG. NO. MP1476296 | Completed | 15030 | 15220 | 2017-02-18 | 2018-06-15
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/578122 — Construction of IAY House -IAY REG. NO. MP1843477 | Completed | 15030 | 14208 | 2017-02-18 | 2018-02-19
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/578238 — Construction of IAY House -IAY REG. NO. MP1881279 | Completed | 15030 | 15325 | 2017-02-04 | 2017-10-30
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/578302 — Construction of IAY House -IAY REG. NO. MP1908010 | Completed | 15030 | 15235 | 2017-02-18 | 2017-12-15
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/578363 — Construction of IAY House -IAY REG. NO. MP1928698 | Completed | 15030 | 14936 | 2017-02-18 | 2018-02-19
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/578365 — Construction of IAY House -IAY REG. NO. MP1928771 | Completed | 15030 | 15162 | 2017-02-04 | 2018-05-14
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/578386 — Construction of IAY House -IAY REG. NO. MP1937394 | Completed | 15030 | 13272 | 2017-02-04 | 2018-06-22
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/578622 — Construction of IAY House -IAY REG. NO. MP2022940 | Completed | 15030 | 14637 | 2017-02-18 | 2017-12-15
BHOPAL / PHANDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/604123 — Construction of IAY House -IAY REG. NO. MP3155488 | Completed | 15030 | 14448 | 2017-05-06 | 2017-12-15
BHOPAL / PHANDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002075/IF/IAY/604418 — Construction of IAY House -IAY REG. NO. MP3941711 | Completed | 15030 | 15071 | 2017-03-11 | 2017-11-06
BHOPAL / PHANDA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002075/LD/3799380565 — खेल मैदान निर्माण कार्य शासकीय माध्‍यमिक शाला, फंदा | Completed | 490000 | 485822 | 2011-03-14 | 2011-05-23
BHOPAL / PHANDA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002075/LD/5801190 — खेल मैदान हाईस्‍कूल कैम्‍पस फंदा ग्राम पंचायत फंदा | Completed | 480000 | 470643 | 2010-12-15 | 2010-11-01
BHOPAL / PHANDA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1728002075/RC/22012034153201 — ग्रेवल रोउ माता बाई वाला मार्ग ग्राम पंचायत फंदाकल | Completed | 262000 | 228612 | 2011-11-07 | 2012-06-07
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034154163 — सी सी रोड अभिसरण, धन्‍ना के घर से ग्राम पंचायत फंद | Completed | 162200 | 158946 | 2012-05-10 | 2012-07-18
BHOPAL / PHANDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034170338 — सी सी रोड निर्माण्‍ा पंचपरमेश्‍वर ग्राम पंचायत फन् | Completed | 165300 | 155774 | 2013-06-02 | 2013-09-29
BHOPAL / PHANDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034171608 — सी सी रोड पंचपरमेश्‍वर शंकर के घर से चालर माता, फं | Completed | 165300 | 155774 | 2013-06-15 | 2013-09-29
BHOPAL / PHANDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034197317 — सी सी रोड पंचपरमेश्‍वर गुलाब से मोहन सिंह के घर तक | Completed | 169500 | 160024 | 2014-01-04 | 2014-03-07
BHOPAL / PHANDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034209650 — सी सी रोड पंचपरमेश्‍वर मिठठूलाल के घर से तेली की क | Completed | 169500 | 157418 | 2014-03-01 | 2014-07-29
BHOPAL / PHANDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034219621 — सी सी रोड पंचपरमेश्‍वर बाबूलाल के मकान से आंगनबाडी | Completed | 173500 | 163204 | 2014-06-07 | 2014-08-27
BHOPAL / PHANDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034219663 — सी सी रोड जयजयराम से क्रपाल के घर तक, फंदा कला | Completed | 173500 | 155040 | 2014-06-07 | 2014-09-15
BHOPAL / PHANDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034219979 — सी सी रोड पंचपरमेश्‍वर क्रपाल से बाबूलाल के मकान त | Completed | 173500 | 162262 | 2014-06-07 | 2014-07-26
BHOPAL / PHANDA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034317148 — सी सी रोड परफार्मेंसग्रांट छत्री मोहल्‍ला, ग्रामपंचायत फंदाकला | Completed | 28100 | 28056 | 2016-12-03 | 2017-02-08
BHOPAL / PHANDA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034320891 — सी सी रोड मनरेगा+पंच परमेश्वर अभिसरण कार्य तेली की कुण्डी से नारायण के घर तक फंदकला | Completed | 186620 | 211962 | 2017-02-04 | 2017-07-31
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034467925 — सी सी रोड पंचपरमेश्‍वर श्रीमति रूकमणी के घर से पिपलियामार्ग तक, फंदाकला | Completed | 18600 | 18480 | 2019-06-22 | 2019-07-27
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034467926 — सी सी रोड जसमत से कंवरी बाई के घर तक फंदा कला | Completed | 51150 | 56496 | 2019-07-13 | 2019-10-11
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034467928 — सी सी रोड मुरली बाई के मकान से आगे तक, फंदा कला | Completed | 55800 | 55616 | 2019-06-22 | 2019-09-12
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034473141 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त रवि राजपूत से पर्वत सिंह के मकान तक, फंदाकला | Completed | 65025 | 64944 | 2019-09-07 | 2019-12-07
BHOPAL / PHANDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034476704 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त गणेश चौक अर्जुन कालोनी फंदाकला | Completed | 19890 | 19888 | 2019-11-30 | 2020-02-10
BHOPAL / PHANDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002075/RC/22012034520814 — सुदूर ग्राम संपर्क सडक हरिहर मंदिर से शमशान तक, फंदाकला | Completed | 1369873.8 | 790344.88 | 2020-06-20 | 2023-03-31
BHOPAL / PHANDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034526538 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त अचल सिंह के घर से हाईवे मार्ग तक, फंदाकला | Completed | 73470 | 73384 | 2020-06-20 | 2021-06-30
BHOPAL / PHANDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034526982 — सीसी रोड निर्माण कार्य अभिसरण 14 वा वित्त शांति धाम परिसर, फंदाकला | Completed | 75225 | 75050 | 2020-07-04 | 2020-08-24
BHOPAL / PHANDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002075/RC/22012034537614 — खेत सडक निर्माण कार्य प्रीतम सिंह के घर से मोती सिंह के खेत तक, फंदाकला | Completed | 1422808.36 | 1182097.21 | 2020-09-26 | 2023-03-20
BHOPAL / PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002075/RC/22012034663672 — सुदूर सडक निर्माण कार्य मनरेगा+जनभागीदारी, सुरेश प्रजापति के भटटे से गोविंद सिंह के खेत तक, फंदाकला | Completed | 1149000 | 1128736.98 | 2023-10-06 | 2026-06-05
BHOPAL / PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034826795 — सी सी रोड निर्माण मनरेगा +15 वां वित्त श्रृद्धा हार्डवेयर से चालार माता के स्‍थान की ओर, फंदाकला | Completed | 66000 | 65450.82 | 2025-06-27 | 2026-05-05
BHOPAL / PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002075/RC/22012034826797 — सी सी रोड निर्माण मनरेगा +15 वां वित्त नारायण के घर से चालार माता के स्‍थान की ओर, फंदाकला | Completed | 66000 | 65957.45 | 2026-01-31 | 2026-05-05
BHOPAL / PHANDA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1728002075/RC/62 — सडक मुरमीकरण रामचरण के खेत से फंदा नाला तक | Completed | 333000 | 171642 | 2009-04-27 | 2009-04-27
BHOPAL / PHANDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1728002075/RS/22012034503217 — सामुदायिक स्वच्छता परिसर, अभिसरण मनरेगा, 15वाॅं वित्त,एसबीएम हरिहर मंदिर परिसर, फंदाकला | Completed | 44000 | 43950 | 2021-02-20 | 2021-11-03
BHOPAL / PHANDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002075/RS/22012034526748 — SLWM लीच पिट निर्माण कार्य (संख्‍या 23) ग्राम पंचायत फंदाकला | Completed | 318928.61 | 267700.04 | 2021-12-04 | 2022-04-25
BHOPAL / PHANDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002075/RS/22012034526756 — SLWM सामुदायिक नाडेप निर्माण कार्य, (संख्‍या 6) फंदाकला | Completed | 74868.5 | 63477.15 | 2021-09-18 | 2021-12-01
BHOPAL / PHANDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002075/RS/22012034594778 — नाडेप निर्माण कार्य (संख्या 4) ग्राम पंचायत फंदा कला | Completed | 54290.09 | 44553.13 | 2021-10-30 | 2021-12-10
BHOPAL / PHANDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002075/RS/22012034594781 — नाडेप निर्माण कार्य (संख्या 4) फंदाखुर्द, ग्राम पंचायत फंदाकला | Completed | 54290.09 | 44132.13 | 2021-10-30 | 2023-09-12
BHOPAL / PHANDA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002075/RS/22012034677462 — सामुदायिक लीच पिट निर्माण कार्य (संख्‍या 2), फंदाकला, ग्राम पंचायत फंदाकला | Completed | 21453.94 | 2448 | 2022-12-24 | 2025-05-08
BHOPAL / PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002075/RS/22012034702760 — सामुदायिक लीच पिट निर्माण मनरेगा+15 वां वित्‍त, संतोष से गप्‍पू महाराज क घर की ओर, फंदाकला | Completed | 105000 | 102102 | 2023-08-26 | 2024-07-15
BHOPAL / PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002075/RS/22012035113436 — नाली निर्माण कार्य मनरेगा +15 वां वित्‍त उस्‍ताद से होतम सिंह लाइनमेन के घर तक, फंदाकला | Completed | 60900 | 60655.64 | 2023-10-06 | 2024-09-04
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002075/RS/22012035129556 — नाली निर्माण कार्य मनरेगा + 15 वां वित्त तेली मोहल्ला से टीलाखेडी रोड की ओर, फंदाकला | Completed | 56800 | 56378.15 | 2024-11-08 | 2025-03-06
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002075/RS/22012035129621 — नाली निर्माण कार्य मनरेगा + 15 वां वित्त संतोष से प्रेम सिंह के मकान की ओर, फंदाकला | Completed | 56800 | 56366.21 | 2024-08-30 | 2024-11-21
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002075/RS/22012035131147 — नाली निर्माण कार्य मनरेगा + 15 वां वित्त ग्राम पंचायत फंदाकला | Completed | 46000 | 45190.68 | 2024-11-30 | 2025-03-18
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/740 — निर्मल भारत अभियान शौचालय निर्माण प्रवेश / रामगोपा | Completed | 4400 | 4400 | 2013-01-01 | 2013-01-07
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/741 — निर्मल भारत अभियान शौचालय निर्माण नरेश / बाबूलाल | Completed | 4400 | 4400 | 2013-01-01 | 2013-01-07
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/742 — निर्मल भारत अभियान शौचालय निर्माण केसरबाई / नन्‍नू | Completed | 4400 | 4400 | 2013-01-01 | 2013-01-07
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/743 — निर्मल भारत अभियान शौचालय निर्माण सिताबाई / केदार | Completed | 4400 | 4400 | 2013-01-01 | 2013-01-07
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/744 — निर्मल भारत अभियान शौचालय निर्माण रामकुंवरबाई / रा | Completed | 4400 | 4400 | 2013-01-01 | 2013-01-07
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/745 — निर्मल भारत अभियान शौचालय निर्माण राजमल / हजारीलाल | Completed | 4400 | 4400 | 2013-01-01 | 2013-01-07
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/746 — निर्मल भारत अभियान शौचालय निर्माण बरकतअली / इमामअल | Completed | 4400 | 4400 | 2013-01-01 | 2013-01-07
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/747 — निर्मल भारत अभियान शौचालय निर्माण भवरजी / हरिप्रसा | Completed | 4400 | 4400 | 2013-01-01 | 2013-01-07
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/748 — निर्मल भारत अभियान शौचालय निर्माण तुलाराम / भंवरजी | Completed | 4400 | 4400 | 2013-01-01 | 2013-01-07
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/749 — निर्मल भारत अभियान शौचालय निर्माण सन्‍तोष / बद्रीप | Completed | 4400 | 4400 | 2013-01-01 | 2013-01-07
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/750 — निर्मल भारत अभियान शौचालय निर्माण बाबूलाल / देवीला | Completed | 4400 | 4400 | 2013-01-01 | 2013-01-07
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/751 — निर्मल भारत अभियान शौचालय निर्माण कैलाश / केशरीबाई | Completed | 4400 | 4400 | 2013-01-21 | 2013-01-27
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/752 — निर्मल भारत अभियान शौचालय निर्माण शक्‍कर बाई / शिव | Completed | 4400 | 4400 | 2013-01-21 | 2013-01-27
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/753 — निर्मल भारत अभियान शौचालय निर्माण मोहनसिंह / भागीर | Completed | 4400 | 4400 | 2013-01-21 | 2013-01-27
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/754 — निर्मल भारत अभियान शौचालय निर्माण आजादसिंह / रामचर | Completed | 4400 | 4400 | 2013-01-21 | 2013-01-27
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/755 — निर्मल भारत अभियान शौचालय निर्माण मोहनलाल / रामचरण | Completed | 4400 | 4400 | 2013-01-21 | 2013-01-27
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/756 — निर्मल भारत अभियान शौचालय निर्माण भगवतसिंह / काशीर | Completed | 4400 | 4400 | 2013-01-21 | 2013-01-27
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/757 — निर्मल भारत अभियान शौचालय निर्माण धनसिंह / गुरूबक् | Completed | 4400 | 4400 | 2013-01-21 | 2013-01-27
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/758 — निर्मल भारत अभियान शौचालय निर्माण अनिल / वीरभान ग् | Completed | 4400 | 4400 | 2013-01-21 | 2013-01-27
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/759 — निर्मल भारत अभियान शौचालय निर्माण सुनीताबाई / जगदी | Completed | 4400 | 4400 | 2013-01-21 | 2013-01-27
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/760 — निर्मल भारत अभियान शौचालय निर्माण कमलाबाई / काशीरा | Completed | 4400 | 4400 | 2013-01-21 | 2013-01-27
BHOPAL / PHANDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002075/RS/761 — निर्मल भारत अभियान शौचालय निर्माण जगदीश दास / काशी | Completed | 4400 | 4400 | 2013-01-21 | 2013-01-27
BHOPAL / PHANDA | 2015-2016 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1728002075/SK/9993647627 — Bharat Nirman Rajeev Gandhi Sewa Kendra,PHANDAKALAN | Completed | 1285000 | 699037 | 2015-07-18 | 2016-10-18
BHOPAL / PHANDA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1728002075/WC/22012034619892 — फलड कंट्रोल एंड बंड स्‍टेबलाइजेशन कार्य, फंदाखुर्द, फंदाकला | Completed | 599261.67 | 542696.49 | 2021-03-13 | 2022-05-12
BHOPAL / PHANDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002075/WC/22012035017726 — सामुदायिक सोक पिट निर्माण कार्य (संख्‍या 5)फंदाखुर्द, ग्राम पंचायत फंदाकला | Completed | 95077.82 | 29022 | 2022-12-24 | 2025-05-08
BHOPAL / PHANDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002075/WC/22012035017761 — सामुदायिक सोख्‍ता गढढा निर्माण्‍ा कार्य (संख्‍या 2), फंदाकला,ग्राम पंचायत फंदाकला | Completed | 39831.12 | 23137 | 2022-12-24 | 2025-05-08
BHOPAL / PHANDA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002075/WC/45 — गेबियन संरचना स्‍वाखेडी | Completed | 70500 | 65110 | 2009-04-24 | 2009-05-01
BHOPAL / PHANDA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002075/WC/46 — गेवियन संरचना बस स्‍टेण्‍ड के पास फंदा कला | Completed | 52000 | 46365 | 2009-04-24 | 2009-05-08
BHOPAL / PHANDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002075/WC/5 — गेबियन संरचना, नदी की गाद निकालना, फन्‍दा खुर्द | Completed | 20000 | 29315.57 | 2009-01-28 | 2009-01-28