## Work List
Exported on: 2026-09-04 19:59:44
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: PIPALIYABAJ KHAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHOPAL / PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1728002091/AV/22012034648634 — Gram Panchayat Seva Kendra | Ongoing | 1100000 | 486354.68 | 2024-03-08
BHOPAL / PHANDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002091/DP/22012034624706 — सामुदायिक वृक्षारोपण कार्य ग्राम पंचायत पिपलियाबाजखॉं | Approved | 259479.75 | 0 | 2024-06-08
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002091/IF/IAY/5821625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130640065 | Completed | 23490 | 23490 | 2025-11-07 | 2026-03-16
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002091/IF/IAY/5823818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127983105 | Completed | 23490 | 22446 | 2025-10-17 | 2026-04-15
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002091/IF/IAY/5827865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123515871 | Completed | 23490 | 21924 | 2025-10-17 | 2026-04-15
BHOPAL / PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002091/IF/IAY/5845414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141726790 | Completed | 23490 | 23490 | 2026-01-09 | 2026-04-15
BHOPAL / PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002091/RC/22012034667793 — सी सी रोड निर्माण कार्य मनरेगा+15 वां वित्‍त, खुमान सिंह से धीरज के घर, पिपलियाबाजखॉं | Completed | 36202 | 34540 | 2023-10-08 | 2024-07-08
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002091/RC/22012034680960 — सी सी रोड निर्माण कार्य ग्राम पंचायत पिपलियाबाजखाॅं | New | 0 | 0 | 2024-04-14
BHOPAL / PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002091/RS/22012035118709 — नाली निर्माण कार्य मनरेगा +15 वां वित्‍त शासकीय पुलिया से लालाराम के घर की ओर, पिपलियाबाजखॉं | Completed | 67147 | 64101 | 2023-10-08 | 2024-07-08
BHOPAL / PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002091/RS/22012035131146 — RCC नाली निर्माण कार्य मनरेगा +15 वां वित्त, चंदन मीणा से सुदेश शर्मा के घर तक, पिपलियाबाजखॉं | Completed | 48000 | 47628 | 2024-09-20 | 2024-12-02
BHOPAL / PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002091/RS/22012035138016 — ग्रेवाटर ट्रीटमेंट नाली निर्माण कार्य मनरेगा+ 15 वां वित्त रामगढ मोहल्‍ला, पिपलियाबाजखॉं | Ongoing | 71000 | 46388.85 | 2025-06-20
BHOPAL / PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002091/WC/22012035080558 — सोख्ता गढढा निर्माण कार्य मोहन सिंह के घर के पास, पिपलियाबाजखॉं | Completed | 48510.5 | 16575 | 2023-07-07 | 2026-04-16
BHOPAL / PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002091/WC/22012035197169 — पोखर निर्माण कार्य ग्राम पंचायत पिपलियाबाजखॉं | Closed | 0 | 0 | 2024-01-24
BHOPAL / PHANDA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1728002091/WC/VB/22012035332531 — रेन वाटर हार्वेस्टिंग कार्य शाला भवन ग्राम पंचायत पिपलियाबाजखाॅं | Approved | 0 | 0 | 2026-04-24
BHOPAL / PHANDA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1728002091/WC/VB/22012035332833 — रेन वाटर हार्वेस्टिंग कार्य सामुदायिक शेड ग्राम पंचायत पिपलियाबाजखॉं | Approved | 0 | 0 | 2026-04-24