## Work List
Exported on: 2026-09-27 05:20:38
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: KAPURI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEHORE / SEHORE | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1729001069/AV/22012034391583 — आंगनबाड़ी भवन निर्माण ग्राम कपूरी | Completed | 312000 | 192896.2 | 2019-01-11 | 2024-05-20
SEHORE / SEHORE | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1729001069/AV/22012034400036 — shantidam | Closed | 0 | 0 | 2019-04-01
SEHORE / SEHORE | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1729001069/AV/22012034447862 — आगनबाड़ी भवन निर्माण ग्राम लोदिया | Closed | 0 | 0 | 2019-01-26
SEHORE / SEHORE | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1729001069/AV/22012034470685 — Aagnwadi nirman gram londiya | Completed | 180000 | 161181 | 2019-10-25 | 2024-05-20
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1729001069/AV/22012034543248 — पेवर ब्लाक (मा. शा.कपूरी में) | Closed | 0 | 0 | 2020-10-02
SEHORE / SEHORE | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1729001069/AV/22012034578110 — CHABUTRA NIRMANWITH PLANTCTONIAN GRAM LONDIYA GRAM PANCHAYT KAPURI | Closed | 0 | 0 | 2021-04-14
SEHORE / SEHORE | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1729001069/AV/22012034578115 — CHABUTRA NIRMAN GRAM LONDIYA GRAM PANCHAYT KAPURI | Closed | 134000 | 0 | 2021-04-14
SEHORE / SEHORE | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair and maintenance of GP building / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1729001069/AV/22012034618116 — Marmmt karya Gram Panchayat Bhavan Londiya ka Fars | Completed | 7300 | 6324 | 2022-05-18 | 2023-06-09
SEHORE / SEHORE | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair and maintenance of GP building / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1729001069/AV/22012034618117 — Marmmt karya Gram Sawaraj Bhawan Kapuri Ka Fars | Completed | 7400 | 6936 | 2022-05-18 | 2023-06-09
SEHORE / SEHORE | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1729001069/DP/22012034443650 — निर्मल नीर ग्राम लोदिया ग्राम पंचायत कपूरी | Closed | 0 | 0 | 2019-01-26
SEHORE / SEHORE | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1729001069/DP/22012034444608 — निर्मल नीर ग्राम लोदिया शांति धाम ग्राम पंचायत कपूरी | Closed | 362370.93 | 5432 | 2020-03-10
SEHORE / SEHORE | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1729001069/DP/22012034493866 — पौधा रोपण सार्वजनिक स्थल पर हनुमान मंदिर के पास गाँव कपूरी | Closed | 677985.75 | 0 | 2020-04-30
SEHORE / SEHORE | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1729001069/DP/22012034596315 — Vashundha Bandan Birksha Ropan Gp Bhawan ke pass Londiya | Closed | 55847.4 | 884 | 2023-08-18
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006116 — कपिल धारा हरि प्रसाद अमर सिंह् | Deleted | 0 | 0 | 2012-12-17
SEHORE / SEHORE | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006123 — कपिल धारा कूप निर्माण | Deleted | 250000 | 0 | 2011-01-26
SEHORE / SEHORE | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006140 — कपिल धारा कुप महेश/भंवर जी | Completed | 250000 | 5495 | 2014-04-30 | 2016-08-23
SEHORE / SEHORE | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006146 — कपिल धारा कुप राम सिहं/मिश्री लाल | Deleted | 0 | 0 | 2011-01-26
SEHORE / SEHORE | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006162 — कपिल धारा कुप एवं मेड हरिनारायण | Completed | 297000 | 167468.2 | 2014-01-16 | 2016-08-23
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006168 — कपिल धारा कुप एवं मेड महेश कुमार | Deleted | 0 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006176 — कपिल धारा कुप एंव मेड प्रेम सिहं | Deleted | 0 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006183 — कपिल धारा कूप दुर्गा प्रसाद/बाफु लाल | Deleted | 297000 | 0 | 2012-12-17
SEHORE / SEHORE | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006189 — कपिल धारा कुप मोतीलाल | Completed | 272000 | 123307.59 | 2014-02-26 | 2016-12-10
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006193 — कपिल धारा कुप एंव मेड राजमल | Deleted | 0 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729001069/IF/1000006208 — निर्मल भारत अभियान जगदीश ओर अन्य | Deleted | 30000 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729001069/IF/1000006213 — निर्मल भारत अभियान संतोश दास ओर अन्य | Deleted | 0 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729001069/IF/1000006227 — निर्मल भारत अभियान संतोश दास ओर अन्य | Deleted | 44000 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006239 — कपिल धारा कुप एंव मेड गजराज / देवकरण | Deleted | 299000 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006240 — कपिल धारा कूप् अनोखी लाल | Deleted | 0 | 0 | 2012-12-17
SEHORE / SEHORE | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1000006250 — कपिल धारा कुप दुर्गाप्रसाद | Completed | 297000 | 166081.5 | 2014-01-05 | 2016-12-10
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1729001069/IF/1000006252 — पशु. शेड. निर्माण. द्रोपदी. बाई/मोतीलाल | Deleted | 38000 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1729001069/IF/1000006254 — पशु.शेड. निर्माण. गंगाराम/रामनारायण | Deleted | 38000 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1729001069/IF/1000006867 — पशु शेड जीतेन्द्र / ठाकुर प्रसाद लोन्दिया | Deleted | 0 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1729001069/IF/1000006869 — पशु शेड लोन्दिया thakur prasad / kaluram | Deleted | 0 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1729001069/IF/1000006872 — pashu shed londiya thakur prasad / kaluram | Deleted | 38000 | 0 | 2012-12-17
SEHORE / SEHORE | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1121 — कपि‍लधारा कुपनि‍र्माण हरि‍प्रसाद अमरसि‍हं कपुरी | Completed | 0 | 102363 | 2011-04-13 | 2013-11-13
SEHORE / SEHORE | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1122 — कपि‍लधारा कूपनि‍र्माण कहैन्‍यालाल देवकरण कपुरी | Completed | 0 | 172367.1 | 2011-04-20 | 2011-06-20
SEHORE / SEHORE | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1123 — कपि‍लधारा कुपनि‍र्माण सुरेश हरि‍प्रसाद कपुरी | Completed | 0 | 234134.75 | 2011-04-13 | 2013-01-28
SEHORE / SEHORE | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1124 — कपि‍लधारा कुपनि‍र्माण महेश भंवरजी कपुरी | Completed | 0 | 103341 | 2011-04-20 | 2013-11-13
SEHORE / SEHORE | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1125 — कपि‍लधारा कूपनि‍र्माण मि‍श्रीलाल मूलचंद कपुरी | Completed | 0 | 182797.9 | 2011-04-20 | 2013-01-28
SEHORE / SEHORE | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1188 — कपि‍लधारा कूपनि‍र्माण मानसि‍हं लक्ष्‍मीनारायण कपूरी | Completed | 0 | 239929.55 | 2011-04-25 | 2013-01-28
SEHORE / SEHORE | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1189 — कपि‍लधारा कूपनि‍र्माण भोजराज कालुराम कपुरी | Completed | 0 | 151176 | 2011-04-27 | 2012-07-05
SEHORE / SEHORE | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/1439 — कपिल धारा कूप निर्माण रामसिंह /मिश्रीलाल | Completed | 250000 | 229862 | 2011-11-16 | 2014-03-06
SEHORE / SEHORE | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/169 — कपिल धारा कूप निर्माण मातादिन/भगवानसिहं | Completed | 0 | 167942.55 | 2009-02-28 | 2009-11-09
SEHORE / SEHORE | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/170 — कपिल धारा कूप निर्माण रामगोपाल/भगरजी | Completed | 0 | 181265.09 | 2009-03-01 | 2009-11-09
SEHORE / SEHORE | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/171 — कपिल धारा कूपनिर्माण रामसिहं/ बाफूलाल | Completed | 0 | 109738.68 | 2009-04-15 | 2010-05-19
SEHORE / SEHORE | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/172 — कपिलधारा कूपनिर्माण जियालाल/अमरसिहं | Completed | 0 | 129629.85 | 2009-02-28 | 2009-06-22
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729001069/IF/22012035230842 — Khet Talab Nirman Work Shivcharan/Mulchand | Physically Completed | 276475.58 | 195889.5 | 2024-06-29 | 2026-03-31
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1729001069/IF/22012035241162 — Nandan Flodhan Bhagwan singh/Jagnnath | Ongoing | 140641 | 22356 | 2024-07-09
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1729001069/IF/22012035246317 — Nandanfloudhan work Jiwan singh/ Haricharan | Deleted | 172200 | 0 | 2024-06-11
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1729001069/IF/22012035283352 — Nandan Floudhan work Jiwan/Harichan | Approved | 0 | 0 | 2024-12-02
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/22012035396887 — Kapildgara Kup Nirman Work Lakhanlal Dubey/ Sukhdev Dubey | Deleted | 0 | 0 | 2025-04-14
SEHORE / SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729001069/IF/22012035419682 — JGSA2025 Recharge structure Kup Jivan /Haricharan 1729001069/IF/ 22012035419543 | Physically Completed | 25899.46 | 25098.9 | 2025-05-02 | 2026-03-30
SEHORE / SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729001069/IF/22012035420522 — JGSA2025 Recharge structure Kup Harinayan / Bhagirath1729001069/IF/ 22012035420424 | Physically Completed | 25899.46 | 21444.9 | 2025-05-02 | 2026-03-30
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729001069/IF/22012035421046 — Nandanfalouddan Work Jivan Singh /Haricharan | Approved | 0 | 0 | 2025-04-15
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729001069/IF/22012035421305 — Nandanfalouddan Work Harinarayan /Bhagirath | Approved | 0 | 0 | 2025-04-15
SEHORE / SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729001069/IF/22012035442922 — JGSA Recharge Structure Kapil Dhara Kup Jiyalal / Amr Singh | Physically Completed | 25899.46 | 25098.9 | 2025-05-03 | 2026-03-30
SEHORE / SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729001069/IF/22012035443016 — JGSA Recharge Structure Kapildhara Kup Durga Prasad / Kaniram | Physically Completed | 25899.46 | 24054.9 | 2025-05-03 | 2026-03-30
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729001069/IF/22012035443998 — JGSA Khet Talab Nirman Work Mukesh / Bapulal | Physically Completed | 181462.92 | 83005.64 | 2025-05-05 | 2026-05-13
SEHORE / SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729001069/IF/22012035452824 — JGSA2025 Recharge structure Akhlesh / Premnarayan | Physically Completed | 25899.46 | 20400.9 | 2025-05-05 | 2026-05-01
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729001069/IF/22012035472777 — JGSA Khet Talab Nirman work Mohanlal / Jagnnath | Physically Completed | 181462.92 | 91804.7 | 2025-05-16 | 2026-06-29
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/22012035474698 — Kapil Dhara Kup Nirman Work Lakhanlal Dubey / Sukhdev Dubey | Ongoing | 311322.11 | 78940.34 | 2025-05-21
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/22012035475020 — Kapi Dhara Kup Nirman Work Manoj Kumar / Ghisilal | Deleted | 0 | 0 | 2025-04-14
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/22012035475141 — Kapil Dhara Kup Nirman Work Manoj Kumar / Ghishilal | Ongoing | 310974.07 | 128050.12 | 2025-05-19
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/22012035491704 — Kapil Dhara Kup Nirman Work Sudhansu Verma / Ompirkash Verma | Ongoing | 311322.11 | 0 | 2025-05-19
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729001069/IF/22012035538427 — JGSA Khet Talab Nirman Work Amni Bai / Bhaver Ji | Physically Completed | 179611.93 | 138056.4 | 2025-05-29 | 2026-04-29
SEHORE / SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729001069/IF/22012035538489 — JGSA Dugwell Recharge Structure Thakur Prasad / Kaluram | Physically Completed | 25899.46 | 25098.9 | 2025-06-02 | 2026-03-30
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729001069/IF/22012035612630 — Ek Bagiya Maa Ke Nam Sitaram Lilakishan | Ongoing | 266577.25 | 51527 | 2025-09-12
SEHORE / SEHORE | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/6 — कपि‍ल धारा कुप नि‍र्माण कार्य घीसीलाल / गुरूबकस | Completed | 52000000 | 132557.86 | 2009-02-04 | 2009-06-15
SEHORE / SEHORE | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/683 — कपिलधारा कूपनिर्माण दुर्गा प्रसाद कनीराम कपुरी | Completed | 0 | 98755.87 | 2009-12-05 | 2011-06-27
SEHORE / SEHORE | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/7 — कपि‍ल धारा कुप नि‍र्माण कार्य मांगीलाल / पन्‍नालाल | Completed | 52000000 | 141355.6 | 2009-01-28 | 2009-06-23
SEHORE / SEHORE | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/716 — कपिलधारा कूपनिर्माण जीतमल अमर सिहं कपूरी | Completed | 0 | 79902.75 | 2009-12-05 | 2011-06-27
SEHORE / SEHORE | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/719 — कपिलधारा कूपनिर्माण रामेश्‍वर कुंवरजी कपूरी | Completed | 0 | 177540.83 | 2010-04-07 | 2011-06-06
SEHORE / SEHORE | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/763 — कपिलधारा कूपनिर्माण रामचंद्र नारायण सि‍हं कपूरी | Completed | 0 | 185300.07 | 2010-04-28 | 2011-06-13
SEHORE / SEHORE | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/9926709865 — babu kha/mohamad kha | Deleted | 272000 | 0 | 2014-01-26
SEHORE / SEHORE | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729001069/IF/9926710511 — कपिलधारा कूप निर्माण बाबू खॉ | Completed | 272000 | 224957 | 2014-03-05 | 2016-08-23
SEHORE / SEHORE | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1729001069/IF/9993703406 — indra awas Rameshchandra/chitu singh | Deleted | 0 | 0 | 2015-08-15
SEHORE / SEHORE | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1729001069/IF/9993703414 — indra awas Ramesh chandra/chitu singh. londiya | Deleted | 1431000000 | 0 | 2016-01-10
SEHORE / SEHORE | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1729001069/IF/9993703450 — indra awas Gordan/nannu lal londiya | Deleted | 1431000000 | 0 | 2015-08-15
SEHORE / SEHORE | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1729001069/IF/9993703455 — Indra awas Mangi lal/Panna lal kapuri | Deleted | 1431000000 | 0 | 2015-08-15
SEHORE / SEHORE | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/1691501 — Construction of IAY House -IAY REG. NO. MP3943203 | Completed | 15660 | 14616 | 2018-05-08 | 2018-09-22
SEHORE / SEHORE | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/1872918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5490450 | Completed | 15660 | 15660 | 2018-07-08 | 2019-01-30
SEHORE / SEHORE | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/2159921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5513415 | Completed | 15840 | 14784 | 2019-07-02 | 2019-10-01
SEHORE / SEHORE | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/3035237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2761861 | Completed | 17370 | 15440 | 2021-04-13 | 2022-02-23
SEHORE / SEHORE | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/3035240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3257657 | Completed | 17370 | 14734 | 2021-04-13 | 2022-12-21
SEHORE / SEHORE | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/3654703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126723988 | Completed | 18360 | 18156 | 2022-06-16 | 2023-02-03
SEHORE / SEHORE | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/3654737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126824569 | Completed | 18360 | 17952 | 2022-06-16 | 2023-02-03
SEHORE / SEHORE | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/3654747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126840396 | Completed | 18360 | 17747 | 2022-06-16 | 2023-02-03
SEHORE / SEHORE | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/3654753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126851641 | Completed | 18360 | 17544 | 2022-06-16 | 2023-02-03
SEHORE / SEHORE | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/3875457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131617551 | Ongoing | 27000 | 13464 | 2026-06-02
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/3941440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127166682 | Ongoing | 27000 | 12942 | 2025-06-03
SEHORE / SEHORE | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/4233431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127205931 | Completed | 18360 | 17340 | 2022-11-23 | 2023-04-21
SEHORE / SEHORE | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/4281381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126801646 | Completed | 18360 | 17544 | 2022-08-22 | 2023-02-03
SEHORE / SEHORE | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/4281394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126817279 | Physically Completed | 18360 | 18258 | 2022-08-29 | 2024-11-21
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/4618424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126111154 | Completed | 21870 | 21627 | 2024-09-25 | 2025-03-26
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/4623736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126815667 | Completed | 21870 | 21627 | 2024-09-25 | 2025-03-26
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/4623795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126821409 | Completed | 23490 | 22167 | 2024-12-15 | 2025-07-30
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/4634028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130102480 | Completed | 23490 | 21933 | 2024-09-25 | 2025-07-30
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/4640186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131618324 | Completed | 21870 | 21627 | 2024-09-25 | 2025-03-26
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5246863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP135879503 | Ongoing | 27000 | 18792 | 2025-07-22
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5262065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126291621 | Ongoing | 27000 | 21924 | 2025-07-22
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5265534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127263446 | Approved | 27000 | 0 | 2025-02-28
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5266263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126787032 | Physically Completed | 23490 | 21402 | 2025-06-03 | 2026-08-02
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5274536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149957124 | Physically Completed | 23490 | 21924 | 2025-07-22 | 2026-02-01
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5276248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127645434 | Completed | 23490 | 22446 | 2025-07-22 | 2026-09-24
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5279876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126813590 | Ongoing | 27000 | 9396 | 2025-07-22
SEHORE / SEHORE | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5297273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126850837 | Completed | 23490 | 22392 | 2026-06-02 | 2026-09-24
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5297665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126811453 | Physically Completed | 23490 | 6264 | 2025-10-17 | 2025-12-30
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5305374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126416903 | Physically Completed | 23490 | 15660 | 2025-09-15 | 2026-08-11
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5305449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127644951 | Ongoing | 27000 | 21924 | 2025-07-22
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5305466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126727011 | Completed | 23490 | 22968 | 2025-07-22 | 2026-08-18
SEHORE / SEHORE | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5311891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131617801 | Physically Completed | 23490 | 0 | 2025-02-12 | 2026-07-26
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5314399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126807256 | Approved | 27000 | 0 | 2025-02-12
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5325104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126720984 | Physically Completed | 23490 | 23490 | 2025-06-03 | 2026-03-15
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5331474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126791709 | Physically Completed | 23490 | 18792 | 2025-07-22 | 2026-08-11
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5333300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126820386 | Physically Completed | 23490 | 3132 | 2025-09-15 | 2026-02-03
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5341067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127162102 | Ongoing | 27000 | 6264 | 2025-07-22
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5412731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127735303 | Approved | 27000 | 0 | 2025-02-12
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5413609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126730003 | Ongoing | 27000 | 7200 | 2025-07-22
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5414258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126812467 | Approved | 27000 | 0 | 2025-02-12
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5414274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126849249 | Approved | 27000 | 0 | 2025-03-10
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5414663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149958153 | Ongoing | 27000 | 9396 | 2025-07-22
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5415418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126426088 | Physically Completed | 23490 | 12528 | 2025-07-22 | 2025-12-30
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5415472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126818843 | Approved | 27000 | 0 | 2025-02-12
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5415687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131742641 | Approved | 27000 | 0 | 2025-03-28
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5415714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126807977 | Ongoing | 27000 | 21924 | 2025-07-22
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5416175 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127860385 | Physically Completed | 23490 | 10962 | 2025-07-22 | 2026-01-06
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5416355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127216695 | Physically Completed | 23490 | 0 | 2025-02-12 | 2026-08-02
SEHORE / SEHORE | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5468935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126819337 | Ongoing | 27000 | 12528 | 2026-06-02
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5514582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126728729 | Ongoing | 27000 | 20358 | 2025-07-22
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5514766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126784841 | Approved | 27000 | 0 | 2025-02-28
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5577751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127193990 | Physically Completed | 23490 | 12528 | 2025-09-15 | 2026-08-02
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5692321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127213521 | Approved | 27000 | 0 | 2025-02-12
SEHORE / SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5877468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126835963 | Approved | 27000 | 0 | 2025-03-02
SEHORE / SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/5944109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126419715 | Approved | 27000 | 0 | 2025-09-09
SEHORE / SEHORE | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/600225 — Construction of IAY House -IAY REG. NO. MP1277589 | Completed | 15030 | 12705 | 2017-02-17 | 2019-06-25
SEHORE / SEHORE | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/75889 — Construction of IAY House -IAY REG. NO. MP-29-001-069-002/08 | Completed | 14310 | 13407 | 2016-03-21 | 2018-06-16
SEHORE / SEHORE | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/75890 — Construction of IAY House -IAY REG. NO. MP-29-001-069-002/16 | Completed | 14310 | 14409 | 2016-03-22 | 2018-06-16
SEHORE / SEHORE | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/75891 — Construction of IAY House -IAY REG. NO. MP-29-001-069-001/36 | Completed | 14310 | 12238 | 2016-03-21 | 2018-06-16
SEHORE / SEHORE | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729001069/IF/IAY/864116 — Construction of IAY House -IAY REG. NO. MP1660577 | Completed | 15480 | 10320 | 2017-06-17 | 2019-06-25
SEHORE / SEHORE | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1729001069/LD/22012034274529 — Medbandhan jivansinh/haricharan | Deleted | 22000 | 0 | 2016-04-14
SEHORE / SEHORE | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Stone graded Bund for Community / Repair and Maintenance of Stone graded Bund for Community | Repair & Maint of Bund | 1729001069/LD/22012034372406 — खेल मैदान ग्राम लोदिया ग्राम पंचायत कपूरी | Deleted | 0 | 0 | 2019-01-26
SEHORE / SEHORE | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1729001069/LD/22012034462290 — खेल मैदान ग्राम लोदिया ग्राम पंचायत कपूरी | Deleted | 0 | 0 | 2019-01-26
SEHORE / SEHORE | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1729001069/LD/22012034462291 — खेल मैदान ग्राम लोदिया ग्राम पंचायत कपूरी | Deleted | 0 | 0 | 2019-01-26
SEHORE / SEHORE | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1729001069/LD/22012034463106 — खेल मैदान ग्राम लोदिया ग्राम पंचायत कपूरी | Completed | 362370.93 | 194127.54 | 2019-03-09 | 2024-10-16
SEHORE / SEHORE | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1729001069/LD/22012034565638 — सार्वजनिक वृक्षारोपण ग्राम पंचायत कपूरी ग्राम लोंदिया खेल मैदान | Deleted | 0 | 0 | 2021-04-14
SEHORE / SEHORE | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1729001069/LD/297 — मेड बंधान सीताराम लीलाकिशन कपूरी | Completed | 0 | 16303 | 2011-06-15 | 2011-06-28
SEHORE / SEHORE | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1729001069/LD/3799386237 — मेड बन्धान मिश्रीलाल | Deleted | 0 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1729001069/LD/3799386259 — मेड बन्धान कन्हैया लाल | Deleted | 30000 | 0 | 2012-12-17
SEHORE / SEHORE | 2012-2013 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1729001069/LD/3799386262 — मेड बन्धान गजराज | Deleted | 30000 | 0 | 2012-12-17
SEHORE / SEHORE | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034160092 — c.c.road mandir se shala bhvan ki or | Completed | 126000 | 18888 | 2013-06-12 | 2014-03-06
SEHORE / SEHORE | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034160141 — सी.सी.रोड लोन्दिया | Deleted | 0 | 0 | 2012-12-17
SEHORE / SEHORE | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034160143 — सी.सी. रोड्लोन्दिया विश्नु प्रसाद के मकान से लक्ष् | Completed | 155000 | 154514 | 2013-09-25 | 2014-03-06
SEHORE / SEHORE | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034160145 — c.croad kapuri shiv prasad ke mkan se manoj/anokhi | Completed | 203000 | 201012 | 2013-09-25 | 2014-03-06
SEHORE / SEHORE | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729001069/RC/22012034203219 — londiya se kapuri kankar ki or | Completed | 1303351 | 303 | 2014-02-17 | 2016-05-18
SEHORE / SEHORE | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034223704 — vishnu prasad ke makan se suresh kumar ke makan ki | Completed | 196048 | 188658 | 2014-07-08 | 2016-10-27
SEHORE / SEHORE | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034223709 — Ramchander ke makan se om prakesh ke makan ki or ( | Deleted | 50029 | 0 | 2014-06-30
SEHORE / SEHORE | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034288741 — c.c.road Ajay tyagi ke makan se samsan ki or | Completed | 131000 | 128385 | 2015-12-08 | 2016-11-22
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034288745 — suresh kumar ke makan se dargha ki or | Completed | 98862 | 93467 | 2016-11-18 | 2018-06-16
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034326096 — c.c.road Patel bakhal londiya | Completed | 136500 | 17663 | 2017-02-08 | 2019-06-25
SEHORE / SEHORE | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034448847 — बाउंड्री वाल मा.शा.कपूरी | Completed | 49850 | 45582 | 2019-03-10 | 2025-02-04
SEHORE / SEHORE | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034449046 — नरेश के मकान से बटन के मकान तक | Completed | 44496 | 46110 | 2019-03-10 | 2019-07-16
SEHORE / SEHORE | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034449047 — जीतू के मकान से शमशान की और | Physically Completed | 76500 | 86062 | 2019-03-10 | 2021-03-30
SEHORE / SEHORE | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034449053 — जीवन दुबे के मकान से घीसी लाल के मकान तक | Completed | 24180 | 2504 | 2019-03-10 | 2025-02-04
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729001069/RC/22012034525752 — Dargha se Devli ki taraf | Closed | 0 | 0 | 2020-04-14
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729001069/RC/22012034525754 — Bada kuwa se Ramsingh ke khet tak | Closed | 0 | 0 | 2020-04-14
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034556741 — interlocking block tiles madhymik Shala panchyat bhavan | Completed | 37800 | 36184 | 2021-01-21 | 2022-07-07
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034562791 — सुरेश के मकान से पुलिया की और | Completed | 29000 | 573 | 2021-03-16 | 2023-06-12
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034562796 — सी.सी.रोड शमशान तक एवं शेड आस-पास कंक्रीट कपूरी | Completed | 40000 | 36999 | 2021-03-16 | 2024-02-08
SEHORE / SEHORE | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034589859 — NALI SURESH KE GHAR SE PULIYA TAK | Deleted | 0 | 0 | 2021-04-14
SEHORE / SEHORE | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034589861 — NALI SURESH KE GHAR SE PULIYA TAK | Deleted | 0 | 0 | 2021-04-14
SEHORE / SEHORE | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034599793 — CEMENT CANKIRIT | Deleted | 0 | 0 | 2021-10-03
SEHORE / SEHORE | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034599795 — CC ROAD NIRMAN SHAMSHAN PARISHAR ME | Completed | 76500 | 68515 | 2021-12-04 | 2023-06-09
SEHORE / SEHORE | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034615067 — C C Road Nirman sadak se samsanghat tak | Completed | 28000 | 20332 | 2023-05-08 | 2024-06-12
SEHORE / SEHORE | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034615313 — CC Road nirman sashamanghat se mukhaymarg ki our Londiya | Completed | 105000 | 103923 | 2023-07-27 | 2024-09-12
SEHORE / SEHORE | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034617203 — CC ROAD NALI NIRMAN KUNGILAL KE GHAR SE UMRAV KE GHAR TAK | Completed | 25575 | 17136 | 2022-10-05 | 2023-06-09
SEHORE / SEHORE | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034617680 — CC ROAD v NALI NIRMAN PM SADAK SE SAMRPIT DARY | Completed | 38985 | 25092 | 2022-10-12 | 2023-06-09
SEHORE / SEHORE | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034649823 — C C Road Nirman Work Pm sadak se Gobind ke Ghar Tak | Completed | 34452 | 30277 | 2023-09-02 | 2024-06-12
SEHORE / SEHORE | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034654666 — C C Road Nirman Work Punamchand ke Ghar se Rup singh ke Ghar Tak Kapuri | Completed | 46200 | 42432 | 2023-09-22 | 2024-09-12
SEHORE / SEHORE | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034828652 — CC Road Nirman Jivan ke Ghar se Anil Ke Ghar Tak Londiya | Completed | 15795 | 2430 | 2025-01-27 | 2025-07-30
SEHORE / SEHORE | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034828667 — CC Road Nirman Jagdish ke Ghar se Visnu Prasad Ke Ghar Tak Kapuri | Completed | 14337 | 11177.92 | 2024-12-14 | 2025-07-30
SEHORE / SEHORE | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034828669 — CC Road Nirman Work Mandir se Banshilal Ke Ghar Tak kapuri | Completed | 18000 | 13365 | 2025-01-11 | 2025-07-30
SEHORE / SEHORE | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034828670 — C C Road Nirman Work Ramesh Ke Ghar se Lakhan Ke Ghar Tak Kapuri | Completed | 21141 | 1944 | 2024-12-14 | 2025-07-30
SEHORE / SEHORE | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034828786 — cc road nirman mandir se banseelal ke khet tak | Approved | 18468 | 0 | 2024-06-06
SEHORE / SEHORE | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/22012034831745 — C C ROad Nirman WORK Birajmohan ke Ghar se Rakesh ke Ghar Tak Kapuri | Completed | 16000 | 5589.12 | 2025-01-19 | 2025-07-30
SEHORE / SEHORE | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729001069/RC/690 — निर्माण मार्ग कपुरी से लोदिया तक कपुरी | Deleted | 0 | 13789.95 | 2010-10-18
SEHORE / SEHORE | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729001069/RC/699 — मार्ग निर्माण कपूरी से लोदिया तक | Completed | 0 | 140330.04 | 2011-02-13 | 2013-02-19
SEHORE / SEHORE | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729001069/RC/839 — सी सी रोड पंच परमेश्‍वर योजना | Completed | 0 | 61742 | 2012-04-04 | 2016-01-25
SEHORE / SEHORE | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729001069/RC/कपूरी 1/50 — मार्ग निमार्ण कपूरी से लोदिया तक | Completed | 1161900 | 179537 | 2008-09-04 | 2008-02-26
SEHORE / SEHORE | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729001069/RC/कपूरी 3/55 — ग्रेवल लोंदि‍या से नि‍पानि‍या कला | Completed | 738000 | 439554.72 | 2008-04-02 | 2008-02-22
SEHORE / SEHORE | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034258208 — mahan lal / nannoolal va anya shouchale nirmaan | Completed | 108000 | 15120 | 2014-08-13 | 2017-01-05
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308347 — Bhojraj/kashiram sochaliye nirman londia. | Completed | 10800 | 10798 | 2016-12-01 | 2017-07-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308372 — Harinarayan/baldev sochaliye nirman londiya. | Completed | 12000 | 11996 | 2016-12-01 | 2017-07-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308373 — Jeetmal/amarsingh sochliye nirman kapuri | Completed | 10806 | 10798 | 2016-12-01 | 2017-07-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308374 — mohan lal/jagannathsochaliya nirman kapuri. | Completed | 12000 | 11996 | 2016-12-02 | 2017-09-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308375 — madhavsingh/sitaram sochaliye nirman kapuri. | Completed | 10800 | 10798 | 2016-12-01 | 2017-07-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308380 — Omprakash/Lilakishan sochaliye nirman londiya | Completed | 10800 | 10798 | 2016-12-02 | 2017-10-30
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308385 — Geeta bai/kamal singh sochaliye nirman kapuri | Completed | 10800 | 10798 | 2016-12-01 | 2017-07-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308387 — Narbada prasad/parvat singh sochaliye nirman londiya | Completed | 12000 | 3006 | 2016-12-01 | 2019-06-25
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308391 — Kamla bai/gorishankar sochaliye nirman londiya. | Completed | 12000 | 3006 | 2016-12-02 | 2019-06-25
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308396 — Kalu ram/baphu lal sochaliye nirman kapuri. | Completed | 10800 | 10798 | 2016-12-01 | 2017-07-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308401 — Harinarayan/devkaran sochaliye nirman kapuri | Completed | 12000 | 11996 | 2016-12-01 | 2017-07-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308404 — Hari prasad /ramnarayan sochaliya nirman londiya. | Completed | 12000 | 11996 | 2016-12-02 | 2017-10-30
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308406 — Mukesh/Baphu lal sochaliye nirman kapuri | Completed | 12000 | 11996 | 2016-12-01 | 2017-07-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308409 — Omprakash/ramgopal sochaliye nirman kapuri | Completed | 12000 | 11996 | 2016-12-01 | 2017-07-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308411 — Umrav singh /ramgopal sochaliye nirman kapuri | Completed | 12000 | 11996 | 2016-12-01 | 2017-10-30
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308414 — Radheshyam/banshi lal sochaliye nirman kapuri. | Completed | 12000 | 11996 | 2016-12-01 | 2017-10-30
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308416 — Ramesh/jayram sochaliye nirman kapuri | Completed | 10800 | 10798 | 2016-12-01 | 2017-08-15
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308819 — madoosingh/prahlad sochaliye nirman kapuri | Completed | 10800 | 10798 | 2016-12-09 | 2017-08-15
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308823 — Ramesh/brmha g sochaliye nirman kapuri | Completed | 10806 | 10798 | 2016-12-09 | 2019-06-25
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308825 — Kashiram/ babal singh sochaliye nirman londiya | Completed | 10800 | 10798 | 2016-12-09 | 2017-10-30
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308828 — Ghanshyam/bansi lal sochaliye nirman kapuri | Completed | 10800 | 10798 | 2016-12-21 | 2017-07-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308831 — Shyam lal/kishori lal sochaliye nirman kapuri | Completed | 12000 | 10994 | 2016-12-09 | 2017-07-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308838 — Jagdish/balmukand sochaliye nirman kapuri | Completed | 12000 | 11996 | 2016-12-09 | 2017-07-14
SEHORE / SEHORE | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034308840 — Mansingh/kishori lal sochaliye nirman kapuri | Completed | 10806 | 10798 | 2016-12-09 | 2017-07-14
SEHORE / SEHORE | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729001069/RS/22012034396874 — शोचालय निर्माण जगदीश /रंजीत सिंह ग्राम कपूरी | Deleted | 12000 | 0 | 2018-02-05
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729001069/RS/22012034483852 — सोखता गड्ढा मध्यमिक शाला कपूरी स्कूल के हैंड पंप के पास | Completed | 14283.77 | 2660 | 2020-07-03 | 2023-07-31
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729001069/RS/22012034483853 — सोखता गड्ढा प्राथमिक शाला लोदिया स्कूल के हैंड पंप के पास | Completed | 14283.77 | 2660 | 2020-07-03 | 2025-02-04
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729001069/RS/22012034490947 — सोखता गडडा बडा कुआ हैंड पंप के पास लोंदिया | Closed | 14283.77 | 0 | 2020-04-30
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729001069/RS/22012034490950 — सोखता गडडा इंदिरा आवास कॉलोनी हैंड पंप के पास लोंदिया | Closed | 14283.77 | 0 | 2020-04-30
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729001069/RS/22012034490951 — सोखता गडडा नदी हैंड पंप के पास लोंदिया | Closed | 14283.77 | 0 | 2020-04-30
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729001069/RS/22012034490952 — सोखता गडडा भैरो सिंह के घर के हैंड पंप के पास कपूरी | Completed | 14283.77 | 950 | 2021-02-23 | 2023-07-31
SEHORE / SEHORE | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729001069/RS/22012034490953 — सोखता गडडा कपूरी गाँव के चौराहा पुलिया हैंड पंप के पास कपूरी | Completed | 14283.77 | 2509 | 2022-02-20 | 2024-09-08
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1729001069/RS/22012034496374 — नाडेप निर्माण लोंदिया पुलिया के पास | Closed | 12480.05 | 0 | 2020-08-15
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1729001069/RS/22012034496375 — नाडेप निर्माण हैंड पंप के पास कपूरी | Closed | 12480.05 | 0 | 2020-08-15
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1729001069/RS/22012034496376 — नाडेप निर्माण बडा कुआ हैंड पंप के पास लोंदिया | Closed | 12480.05 | 0 | 2020-08-15
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Groups / Construction of Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1729001069/RS/22012034496377 — नाडेप निर्माण विजय त्यागी के घर के पास कपूरी | Closed | 12480.05 | 0 | 2020-08-15
SEHORE / SEHORE | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1729001069/RS/22012034496378 — नाडेप निर्माण नदी के पास लोंदिया | Closed | 12480.05 | 0 | 2020-08-15
SEHORE / SEHORE | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1729001069/RS/22012034609102 — NADEP NIRMAN SAMUHIK BHAVAN KE AAS PAS KAPURI. | Closed | 0 | 0 | 2021-10-02
SEHORE / SEHORE | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1729001069/RS/22012034609231 — NADAP NIRMAN PANCHYAT BHAVAN KE PAS LONDIYA | Closed | 1800 | 0 | 2021-12-05
SEHORE / SEHORE | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1729001069/RS/22012034609324 — NADEP NIRMAN SAMUDAYAK bHAVAN KE PAS KAPURI | Deleted | 0 | 0 | 2021-10-02
SEHORE / SEHORE | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1729001069/WC/22012034378290 — wcm check dam sanduriya | Completed | 832705 | 676499.88 | 2018-01-19 | 2019-06-14
SEHORE / SEHORE | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1729001069/WC/22012034382028 — mws louse boulder | Deleted | 6850 | 0 | 2017-10-02
SEHORE / SEHORE | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1729001069/WC/22012034390193 — तालाब जीर्णोद्धार ग्राम कपूरी | Deleted | 37648800000 | 0 | 2018-04-14
SEHORE / SEHORE | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1729001069/WC/22012034611957 — Talab vishtrikaran gram londiya gram panchayat kapuri. | Closed | 0 | 0 | 2020-10-02
SEHORE / SEHORE | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1729001069/WC/22012034619464 — तालाब पाल सुदृढ़ीकरण ग्राम लोदिया ग्राम पंचायत कपूरी | Ongoing | 675311.14 | 110723.4 | 2021-03-10
SEHORE / SEHORE | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1729001069/WC/22012034624031 — nali nirman suresh ke makan se nale tak | Deleted | 0 | 0 | 2021-01-26
SEHORE / SEHORE | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1729001069/WC/22012034691086 — Roof water harvisting panchayat bhavan kapuri | Completed | 34223.42 | 11836 | 2021-05-20 | 2025-01-03
SEHORE / SEHORE | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1729001069/WC/22012034691117 — Roof water harvistingh panchayat bhavan gram londiya gram panchayat kapuri. | Completed | 34223.42 | 7141 | 2021-05-30 | 2023-06-28
SEHORE / SEHORE | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1729001069/WC/22012034720774 — CTR POKHAR NIRMAN PILI KHADAN KAPURI | Closed | 334715.44 | 0 | 2021-04-14
SEHORE / SEHORE | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729001069/WC/22012034720800 — CTR KHET TALAB NIRMAN CHINTA BAI/CHAGAN LAL GRAM LONDIYA GRAM PANCHAYAT KAPURI. GRAM LONDIYA | Closed | 421804.72 | 0 | 2021-04-14
SEHORE / SEHORE | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1729001069/WC/22012034720827 — CTR SHOCK PIT MANOJ TYAGI KE MAKAN KE PAS KAPURI. | Closed | 14467.3 | 0 | 2021-04-14
SEHORE / SEHORE | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1729001069/WC/22012035064799 — Nirmal Neer kup Shamsan ke Pass Londiya | Ongoing | 670526.99 | 220794.8 | 2023-05-30
SEHORE / SEHORE | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729001069/WC/22012035109514 — Pani ki Tanki Nirman karya Ramesh ke ghar ke pass | Completed | 18600 | 1768 | 2023-09-22 | 2024-10-16
SEHORE / SEHORE | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1729001069/WC/22012035140125 — Tanki Nirman karya Agnwadi Bhawan ke pass Londiya | Completed | 19842 | 16575 | 2023-10-08 | 2024-09-12
SEHORE / SEHORE | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1729001069/WC/9184 — निर्मल नीर कपूरी | Completed | 0 | 84490.98 | 2008-04-02 | 2009-06-24
SEHORE / SEHORE | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1729001069/WC/9993653824 — shock pit nirman | Completed | 10000 | 608 | 2014-07-08 | 2016-05-19
SEHORE / SEHORE | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729001069/WC/कपूरी 4/55 — 1729001069/WC/कपूरी 4/55 | Deleted | 100000 | 153902 | 2008-04-02