## Work List
Exported on: 2026-10-01 21:34:35
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SAMRIBODA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1729002033/DP/22012034610830 — Nirmal Nir kup samri. Emlikheda, mavkheda | Ongoing | 537251.35 | 0 | 2023-10-07
SEHORE / ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1729002033/DP/22012034619422 — NANDAN FULOUDYAN GP SAMRI BONDA KALU SINGH/NAGGA JI | Approved | 0 | 0 | 2024-06-21
SEHORE / ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1729002033/DP/22012034620564 — Nandan faloudhyan sobharam /mangilal | Approved | 173308.58 | 0 | 2024-06-21
SEHORE / ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plntation Horti-TreesIndividual / Wasteland Block Plantation of Horticulture Trees for Individuals | Plantation | 1729002033/IF/22012034471045 — kapil dhara kup amar singh bhavana samri bonda | Ongoing | 230400.79 | 0 | 2019-03-09
SEHORE / ASHTA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002033/IF/22012034642831 — Kapil dhara kup Kishan lal/ Hamir | Ongoing | 246126.86 | 0 | 2021-01-07
SEHORE / ASHTA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002033/IF/22012034659595 — कपिलधारा कुप निर्माण अवतार सिह / हीरालाल ग्राम सामरीबोंदा | Ongoing | 246126.86 | 0 | 2021-03-13
SEHORE / ASHTA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002033/IF/22012034664889 — kapil dhara kup dhan singh /sobharam | Ongoing | 246126.86 | 0 | 2022-03-16
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002033/IF/22012035227686 — Kapil dhara kup dilip/bharta samri bonda | Ongoing | 282417.57 | 0 | 2024-06-29
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002033/IF/22012035227707 — Kapil dhara kup ramesh/pardhvi samri jhnda | Ongoing | 282417.57 | 0 | 2024-06-29
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Bio-gas plant for individual / Construction of Bio-gas plant for individual | Bio-gas plant | 1729002033/IF/22012035232908 — Nandan fulouddan ramesh /pardhvi | New | 0 | 0 | 2024-06-10
SEHORE / ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1729002033/IF/22012035233080 — Nandan fulouddan gp samri bondaramesh /pardhvi | Ongoing | 173308.58 | 8100 | 2024-06-29
SEHORE / ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1729002033/IF/22012035239777 — NANDAN FULOUDYAN GP SAMRI BONDA KALU SINGH/NAGGA JI | Ongoing | 173308.58 | 0 | 2024-07-06
SEHORE / ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1729002033/IF/22012035253693 — Nandan Falodhyan Shobharam so Mangilal Samribonda | Ongoing | 173308.58 | 6000 | 2024-08-13
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002033/IF/22012035281465 — Kapil dhara kup nirman laxman singh/gabba gp samri bonda | Ongoing | 312155.12 | 0 | 2025-06-22
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002033/IF/22012035281467 — Kapil dhara kup nirman narayansingh/siddulal gp samri bonad | Ongoing | 312155.12 | 0 | 2025-06-04
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002033/IF/22012035281886 — Kapil dhara kup nirman Ratansingh/nggaji | Ongoing | 312155.12 | 0 | 2025-06-04
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002033/IF/22012035287114 — Kapil dhara kup girdharlal/Bhavana gp samri bonda | Approved | 0 | 0 | 2025-01-03
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002033/IF/22012035387565 — Degwell nirman dilip/bharta samri bonda | New | 0 | 0 | 2025-04-14
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002033/IF/22012035410586 — JGSA dugwell nirman kapil dhara kup ukar/ bapu | Approved | 25899.46 | 0 | 2025-04-14
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002033/IF/22012035473016 — Dugwell nirman karya ramesh chandra/ pardhvi | New | 0 | 0 | 2025-04-14
SEHORE / ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/4303427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116595955 | Physically Completed | 27000 | 0 | 2022-08-31 | 2026-09-13
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/4569318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116549065 | Ongoing | 27000 | 0 | 2024-09-30
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/4746218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115700727 | Ongoing | 27000 | 0 | 2024-12-08
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/4746604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115339130 | Ongoing | 27000 | 0 | 2024-12-02
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/4747639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115185239 | Ongoing | 27000 | 0 | 2025-01-03
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/4749436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116156753 | Ongoing | 27000 | 0 | 2024-12-25
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/4750238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117191584 | Ongoing | 27000 | 0 | 2024-12-08
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/4750524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116556890 | Ongoing | 27000 | 0 | 2024-12-25
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/4751424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116628111 | Physically Completed | 23490 | 0 | 2024-12-25 | 2026-08-16
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/4757225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118749189 | Ongoing | 27000 | 0 | 2024-12-02
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/5175411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116431825 | Physically Completed | 23490 | 0 | 2025-06-27 | 2026-07-19
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/5640770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116343740 | Ongoing | 27000 | 0 | 2025-06-27
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/5692020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117608105 | Physically Completed | 23490 | 0 | 2025-07-18 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/5745759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115700915 | Ongoing | 27000 | 0 | 2025-08-21
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/5746793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115185012 | Approved | 27000 | 0 | 2025-05-13
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/6147796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118829730 | Ongoing | 27000 | 0 | 2026-07-07
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/6183312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147899463 | Ongoing | 27000 | 6900 | 2026-05-19
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/6190360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116785637 | Ongoing | 27000 | 0 | 2026-09-08
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/6194206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113697456 | Ongoing | 27000 | 11700 | 2026-05-19
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002033/IF/IAY/6370112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115700634 | Approved | 27000 | 0 | 2026-07-30
SEHORE / ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1729002033/LD/22012034529020 — Charagya nirman go shala ke pash | Ongoing | 477891.72 | 0 | 2021-03-29
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002033/RC/22012034535988 — 14fc+mnrega cc road - Main Road se Primary School Bhawan tak tigariya | Ongoing | 76500 | 0 | 2020-09-11
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002033/RC/22012034664938 — 15fc+mnrega CC Road - Anganwadi se Ramesh ke makan ki or Samri bonda | Ongoing | 50000 | 0 | 2023-10-07
SEHORE / ASHTA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002033/RS/22012034676159 — 15fc+mnrega Nali Nirman - kripal ke ghar se DP Tak Samri Jhanda GP Samribonda | Physically Completed | 46000 | 0 | 2023-01-08 | 2026-09-25
SEHORE / ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wastelands Block Plantation-Farm Forestry -Comm / Wasteland Block Plantation of Farm Forestry Trees for Community | Plantation | 1729002033/WC/22012034544806 — pukhar nirman karya samri mavkheda | Ongoing | 332572.21 | 0 | 2021-06-16
SEHORE / ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-fields-Comm / Block Plantation of Biodrainage Trees in fields for Community | Plantation | 1729002033/WC/22012034619563 — Nirmal nir kup umardad sobha puliya ke pash | Ongoing | 470874.11 | 0 | 2021-11-23
SEHORE / ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1729002033/WC/22012034619872 — nirmal nir kup umardad karma talab ke pash | Ongoing | 470874.11 | 0 | 2021-12-30
SEHORE / ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Gabion Check Dam for Community / Repair and Maintenance of Gabion Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1729002033/WC/22012034636993 — pukhar nirman karya shanti dham bhagtpura | Ongoing | 337715.44 | 0 | 2021-06-10
SEHORE / ASHTA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1729002033/WC/22012034654594 — Talai Nirman Bad ke pas Bhagatpura GP Samribonda | Ongoing | 880941.23 | 0 | 2021-05-25
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729002033/WC/22012035069067 — Pukhar nirman karya samri emlikheda | Ongoing | 485027.96 | 0 | 2023-06-17
SEHORE / ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1729002033/WC/22012035203967 — Nala vishtarikaran gram samri bonda kashm nadi | Approved | 0 | 0 | 2024-06-11
SEHORE / ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1729002033/WC/22012035209680 — Salkan pond gp samri bonda kashm nadi me | Approved | 0 | 0 | 2024-06-19