## Work List
Exported on: 2026-10-19 22:55:39
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: BAMULIYAKHECHI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1729002073/AV/22012034393807 — Shantidham Nirman Gram bamuliya Khichi | Completed | 180000 | 179565.91 | 2019-02-26 | 2021-02-10
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Stabilization Pond for Community / Construction of Stabilization Pond for Community | Construction of Tank | 1729002073/AV/22012034543886 — 15fc+mnrega Pani ki tanki nirman shala bhawan ke pas Bamuliya khichi | Ongoing | 19200 | 380 | 2021-02-15
SEHORE / ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1729002073/AV/22012034563153 — 15fc+mnrega boundrywall nirman shamshan prangan bamuliya khichi | Completed | 60000 | 59619 | 2021-04-15 | 2022-12-12
SEHORE / ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1729002073/AV/22012034582593 — Shantidham Nirman Mohammadpur Pakhni GP Bamuliya Khichi | Closed | 0 | 0 | 2021-04-14
SEHORE / ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1729002073/AV/22012034583334 — construction of kithen sed primari school gram bamuliya khichi | Closed | 0 | 0 | 2021-04-21
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1729002073/AV/22012034649397 — manrega +shanti dham pakni | Completed | 226381.46 | 207057.48 | 2024-10-07 | 2025-02-06
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1729002073/AV/22012034655443 — Khel Medan Nirman Govt Primary School Parisar evam Manglik Bhawan Moh. Pakhni GP Bamuliya Khichi | Ongoing | 447226.84 | 105948 | 2024-04-01
SEHORE / ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1729002073/DP/22012034548967 — माँ की बगिया मा शा बमुलिया खीची | Closed | 0 | 0 | 2021-10-02
SEHORE / ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1729002073/DP/22012034617346 — Community Plantation work Shala Parisar evam Community Hall ke pas Mo Pakhni GP Bamuliya Khichi | Approved | 0 | 0 | 2024-06-08
SEHORE / ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1729002073/IC/22012034884517 — Nandan fall udiyan Chandra singh/ Moti Singh mohamadpur pakhni GP bamuliya khichi | New | 0 | 0 | 2024-06-08
SEHORE / ASHTA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/1000001815 — कपिलधारा मांगीलाल पिता हरिसिंह | Deleted | 0 | 0 | 2012-11-19
SEHORE / ASHTA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/1000003893 — कपिलधारा कूप निर्माण रामलाल/देवाजी | Deleted | 275000 | 0 | 2012-11-19
SEHORE / ASHTA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/1000003897 — कपिलधारा कूप निर्माण गंगाराम/शंकरलाल | Deleted | 275000 | 0 | 2012-11-19
SEHORE / ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/1000017925 — कपिलधारा कूप देवीसिहं/भेरूसिहं | Completed | 291000 | 135267 | 2013-06-07 | 2013-08-15
SEHORE / ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/1000039288 — Kapildhara Lalkuwarbai Saodansingh Bamuliyakhichi | Completed | 282000 | 876 | 2013-09-25 | 2013-09-26
SEHORE / ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/1000039291 — Kapildhara Virendrasingh Sardarsingh Bamuliyakhich | Completed | 275000 | 876 | 2013-09-25 | 2013-09-26
SEHORE / ASHTA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/1167 — कपिलधारा कूप निर्माण कार्य प्‍यारसिह पिता बन्‍शीलाल बमूलियाखीची | Completed | 223000 | 193287 | 2011-04-01 | 2012-03-30
SEHORE / ASHTA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729002073/IF/1358 — कपिल धारा कूप निर्माणकार्य देवकरण पिता भेरूसिंह ग्राम बमुलियाखींची | Completed | 242000 | 250088 | 2012-01-18 | 2012-08-23
SEHORE / ASHTA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729002073/IF/1359 — कपिल धारा कूप निर्माणकार्य बाबूलाल पिता भागीरथ ग्राम बमुलियाखींची | Completed | 242000 | 282972 | 2012-01-19 | 2012-08-24
SEHORE / ASHTA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729002073/IF/1360 — कपिल धारा कूप निर्माणकार्य पूरणसिंह पिता लाडसिंह ग्राम बमुलियाखींची | Completed | 242000 | 287498 | 2012-01-30 | 2013-07-01
SEHORE / ASHTA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729002073/IF/1361 — कपिल धारा कूप निर्माणकार्य गोकुलसिंह पिता देवसिंह ग्राम बमुलियाखींची | Completed | 242000 | 222339 | 2012-01-20 | 2012-08-23
SEHORE / ASHTA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729002073/IF/1362 — कपिल धारा कूप निर्माणकार्य मांगीलाल पिता सावंतसिंह ग्राम बमुलियाखींची | Completed | 242000 | 253306 | 2012-02-02 | 2012-08-29
SEHORE / ASHTA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/1830 — कपिलधारा कुप निर्माण कार्य चन्‍दरसिह पिता मोतीसिह | Completed | 275000 | 42184 | 2012-12-27 | 2017-07-25
SEHORE / ASHTA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/1832 — कपिलधारा कुप निर्माण कार्य भगवतसिह पिता हरलाल ग्र | Completed | 242000 | 239168.9 | 2013-02-15 | 2014-03-11
SEHORE / ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/1838 — कपिलधारा कुप निर्माण कार्य भरतलाल पिता शंकरलाल गाम | Completed | 275000 | 267641.8 | 2013-05-31 | 2014-06-18
SEHORE / ASHTA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729002073/IF/1841 — कपिलधारा कुप निर्माण कार्य देवकरण पिता भेरूसिह ग्राम बमुलिया खीची | Completed | 242000 | 76642 | 2012-05-24 | 2013-07-01
SEHORE / ASHTA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729002073/IF/2163 — कपिलधारा कूप निर्माण कार्य देवीसिह पिता भेरूसिह बमूलियाखीची | Completed | 291000 | 106920 | 2013-01-18 | 2013-07-01
SEHORE / ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/22012034385742 — kapildhara kup nirman gendkunvar /svarupsingh | Completed | 230400.79 | 211851.5 | 2019-03-08 | 2021-06-29
SEHORE / ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/22012034465054 — Kapildhara kup Govardhan singh / keshar singh | Deleted | 0 | 0 | 2019-01-26
SEHORE / ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/22012034471440 — Kapildhara kup Govardhan singh / keshar singh | Completed | 230400.79 | 205354.5 | 2019-03-08 | 2021-06-29
SEHORE / ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1729002073/IF/22012034656793 — नंदन फलउधान प्रेमसिह / बलदेव ग्राम बमुलियाखीची | Ongoing | 114000 | 13868 | 2021-02-15
SEHORE / ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1729002073/IF/22012034664897 — नंदन फलोधान लालजी राम के खेत पर बमुलिया खिची | Ongoing | 114000 | 4388 | 2021-03-10
SEHORE / ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1729002073/IF/22012034705550 — नंदन फलोध्यान धापु बाई / मांगीलाल बमुलियाखीची | Deleted | 114000 | 0 | 2021-01-26
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1729002073/IF/22012035136939 — नंदन फलोउद्यान धापू बाई / मांगीलाल ग्राम बमुलिया खीची | Deleted | 0 | 0 | 2023-04-14
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1729002073/IF/22012035136942 — नंदन फलोउद्यान दिनेश कुमार / लाड़ सिह धनगर ग्राम मो पखनी ग्राप बमुलिया खीची | Deleted | 160586.73 | 0 | 2023-04-14
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1729002073/IF/22012035177694 — nandan fal udya Dinesh /ladsingh pakhni | Ongoing | 163086.73 | 76461.96 | 2023-12-13
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1729002073/IF/22012035177709 — nandan fal udyan Dhapu bai/mangilal bamuliya khichi | Ongoing | 163086.73 | 95699.96 | 2023-10-26
SEHORE / ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1729002073/IF/22012035232722 — Nandan Falodhyan Chandar so Moti Mo Pakhni GP Bamuliya Khichi | New | 0 | 0 | 2024-06-08
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002073/IF/22012035445420 — Dugwell Recharge Gendkuwar bai wo Swaroop Singh Bamuliya Khichi | Physically Completed | 25899.46 | 15378.84 | 2025-05-15 | 2026-05-02
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002073/IF/22012035445443 — Dugwell Recharge structure Nirmal neer Panchayat ke pas Bamuliya Khichi | Deleted | 0 | 0 | 2025-04-14
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002073/IF/22012035447492 — Dugwel Recharge Harku Bai wo Bharat MO Pakhni GP Bamuliya Khichi | Physically Completed | 25899.46 | 20417.96 | 2025-05-15 | 2026-04-09
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002073/IF/22012035447539 — Dugwell Recharge Bharatlal so shankarlal Mo Pakhni GP bamuliya khichi | Physically Completed | 25899.46 | 21203.32 | 2025-05-15 | 2026-04-11
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002073/IF/22012035447556 — Dugwell Recharge Bhagwat singh so harlal bamuliya Khichi | Physically Completed | 25899.46 | 21461.28 | 2025-05-15 | 2026-04-05
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002073/IF/22012035447577 — Khet Talab Nirman Narayan singh so Gangaram Bamuliya Khichi | Physically Completed | 55865.38 | 32278.28 | 2025-05-15 | 2026-04-22
SEHORE / ASHTA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/236 — कपिलधारा कूप निर्माण कार्य सतीष पिता रन्‍जीत बमुलियाखीची | Completed | 214000 | 219710 | 2009-02-07 | 2010-02-18
SEHORE / ASHTA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/237 — कपिलधारा कूप निर्माण कार्य कन्‍यालाल पिता दौलाजी बमुलियाखीची | Completed | 214000 | 212051 | 2009-02-07 | 2010-05-07
SEHORE / ASHTA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/238 — कपिलधारा कूप निर्माण कार्य लक्ष्‍मण पिता मुन्‍शीलाल बमुलियाखीची | Completed | 214000 | 186454 | 2009-05-02 | 2010-05-07
SEHORE / ASHTA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/689 — कपिलधारा कूप निर्माण कार्य शंकरलाल पिता पन्‍नालाल बमूलियाखीची | Completed | 223000 | 95344 | 2011-01-28 | 2012-03-30
SEHORE / ASHTA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/690 — कपिलधारा कूप निर्माण कार्य भेरूलाल पिता पूनाजी पखनी | Completed | 223000 | 307194 | 2011-01-28 | 2011-09-07
SEHORE / ASHTA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/691 — कपिलधारा कूप निर्माण कार्य हरकूबाई पति भारतसिह बमूलियाखीची | Completed | 223000 | 290264 | 2011-01-28 | 2011-09-07
SEHORE / ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1729002073/IF/9926699842 — bakri shed swaroop singh/sobak singh ts 3651 | Completed | 47000 | 46850.47 | 2014-02-28 | 2014-05-20
SEHORE / ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/9926709835 — Kapildhar Kup/madan/mehetab singh | Completed | 295000 | 260507.6 | 2014-03-01 | 2016-08-20
SEHORE / ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/9926710563 — kapildhara HEMRAJ DEVSINGH | Deleted | 295000 | 0 | 2014-01-26
SEHORE / ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/9926710574 — kapildhara Hemraj Devsingh | Completed | 295000 | 255797.6 | 2014-03-03 | 2016-08-15
SEHORE / ASHTA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/9993682345 — indra avash yojna - bharat singh S/o setan singh | Completed | 14310 | 8668 | 2015-10-20 | 2017-06-10
SEHORE / ASHTA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/9993682347 — indra avash yojna- devkaran S/o mandrup | Completed | 14310 | 9169 | 2015-10-20 | 2017-06-05
SEHORE / ASHTA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/1167956 — Construction of IAY House -IAY REG. NO. MP2679937 | Completed | 15480 | 14472 | 2017-12-04 | 2018-05-10
SEHORE / ASHTA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/1168645 — Construction of IAY House -IAY REG. NO. MP3604006 | Completed | 15480 | 15042 | 2017-12-22 | 2018-07-04
SEHORE / ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/1863134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4170669 | Completed | 15660 | 15660 | 2018-06-30 | 2018-10-16
SEHORE / ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/1863186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4247040 | Completed | 15660 | 14616 | 2018-07-21 | 2018-10-16
SEHORE / ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/1863362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4473894 | Completed | 15660 | 14616 | 2018-07-21 | 2018-09-25
SEHORE / ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/1871853 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4959165 | Completed | 15660 | 15660 | 2018-07-21 | 2018-10-05
SEHORE / ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/1879175 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4167561 | Completed | 15660 | 15660 | 2018-07-29 | 2018-10-16
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2101950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4179080 | Completed | 15840 | 15664 | 2019-07-03 | 2019-11-25
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2103053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4199976 | Completed | 15840 | 15312 | 2019-07-03 | 2019-10-31
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2103425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4199937 | Completed | 15840 | 15312 | 2019-07-03 | 2019-10-31
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2116692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4476321 | Completed | 15840 | 15312 | 2019-07-03 | 2019-10-31
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2116693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4476324 | Completed | 15840 | 15840 | 2019-07-03 | 2019-09-10
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2131401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4798544 | Completed | 15840 | 15136 | 2019-07-03 | 2019-10-29
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2132452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4821605 | Completed | 15840 | 15136 | 2019-07-03 | 2019-10-29
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2133112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4836183 | Completed | 15840 | 15840 | 2019-07-03 | 2019-09-10
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2133774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4854445 | Completed | 15840 | 14080 | 2019-07-03 | 2020-01-15
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2133804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4855153 | Completed | 15840 | 14784 | 2019-07-03 | 2019-09-16
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2134537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4874502 | Completed | 15840 | 15312 | 2019-07-18 | 2019-11-10
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2137758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4957809 | Completed | 15840 | 15840 | 2019-07-03 | 2019-09-10
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2137763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4957944 | Completed | 15840 | 15840 | 2019-07-03 | 2019-11-10
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2145381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5149290 | Completed | 15840 | 15488 | 2019-07-19 | 2019-09-27
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2149341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5249895 | Completed | 15840 | 15312 | 2019-07-03 | 2019-10-31
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2161296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5549196 | Completed | 15840 | 15488 | 2019-07-20 | 2019-10-18
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2163039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5595199 | Completed | 15840 | 15136 | 2019-07-03 | 2019-10-29
SEHORE / ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/2163227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5599943 | Completed | 15840 | 15312 | 2019-07-03 | 2019-10-31
SEHORE / ASHTA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/3006374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4176471 | Completed | 17100 | 16212 | 2021-04-22 | 2022-02-13
SEHORE / ASHTA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/3006375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4874709 | Completed | 17100 | 15054 | 2021-04-22 | 2022-02-13
SEHORE / ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/4279274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115786815 | Completed | 18360 | 18360 | 2022-09-01 | 2023-06-28
SEHORE / ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/4279275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115786945 | Completed | 18360 | 18360 | 2022-07-24 | 2023-06-28
SEHORE / ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/4279277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115787911 | Completed | 18360 | 18360 | 2022-07-18 | 2023-06-28
SEHORE / ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/4281760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131899766 | Completed | 18360 | 17136 | 2022-08-26 | 2024-06-05
SEHORE / ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/4281761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131900047 | Completed | 18360 | 18360 | 2022-09-01 | 2023-06-28
SEHORE / ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/4283118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150911943 | Completed | 18360 | 18360 | 2022-08-12 | 2023-06-28
SEHORE / ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/4283119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150913372 | Completed | 18360 | 18360 | 2022-08-26 | 2023-08-24
SEHORE / ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/4300015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113936920 | Completed | 18360 | 18360 | 2022-09-01 | 2023-06-28
SEHORE / ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/4302836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115786899 | Completed | 18360 | 18360 | 2022-08-12 | 2023-06-28
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/4562355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115786683 | Completed | 23490 | 21942 | 2024-11-12 | 2026-01-22
SEHORE / ASHTA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/462254 — Construction of IAY House -IAY REG. NO. MP1726488 | Completed | 15030 | 15054 | 2017-03-01 | 2018-11-09
SEHORE / ASHTA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/462258 — Construction of IAY House -IAY REG. NO. MP1726496 | Completed | 15030 | 14562 | 2017-02-08 | 2018-07-04
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/4668318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150912696 | Ongoing | 23490 | 21510 | 2024-11-05
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/4765832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115787661 | Ongoing | 23490 | 20412 | 2024-11-27
SEHORE / ASHTA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/495951 — Construction of IAY House -IAY REG. NO. MP2206217 | Completed | 15030 | 14388 | 2017-02-08 | 2018-01-20
SEHORE / ASHTA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/498203 — Construction of IAY House -IAY REG. NO. MP2232275 | Completed | 15030 | 14511 | 2017-02-08 | 2018-08-28
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5250298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131900314 | Ongoing | 23490 | 21402 | 2025-06-17
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5251494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115787011 | Approved | 23490 | 0 | 2025-02-04
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5262159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150911092 | Physically Completed | 23490 | 17226 | 2025-05-27 | 2026-05-31
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5263433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150913095 | Ongoing | 23490 | 18270 | 2025-06-12
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5264449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131900636 | Ongoing | 23490 | 22968 | 2025-06-03
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5268163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151373310 | Ongoing | 23490 | 18270 | 2025-06-17
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5268335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113937208 | Ongoing | 23490 | 20880 | 2025-06-03
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5268947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150912929 | Ongoing | 23490 | 16443 | 2025-06-17
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5270507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150912089 | Ongoing | 23490 | 0 | 2025-06-17
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5270797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150911766 | Ongoing | 23490 | 21924 | 2025-05-28
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5271888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115786477 | Approved | 23490 | 0 | 2025-02-06
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5274430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150912439 | Completed | 23490 | 23229 | 2025-06-03 | 2026-01-22
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5278473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150913546 | Ongoing | 23490 | 18270 | 2025-07-29
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5278636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131900805 | Ongoing | 23490 | 19836 | 2025-06-03
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5279685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131900556 | Ongoing | 23490 | 16443 | 2025-06-17
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5282651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113936686 | Approved | 23490 | 0 | 2025-02-06
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5283678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115787275 | Ongoing | 23490 | 0 | 2025-06-02
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5284233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150913255 | Physically Completed | 23490 | 21924 | 2025-08-01 | 2025-12-18
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5285420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150911644 | Ongoing | 23490 | 21402 | 2025-06-18
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5291071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150912809 | Ongoing | 23490 | 17748 | 2025-05-27
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5296125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151369495 | Approved | 23490 | 0 | 2025-02-06
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5296436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115787103 | Ongoing | 23490 | 0 | 2025-06-17
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5297562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113937144 | Ongoing | 23490 | 14616 | 2025-08-10
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5309643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113798770 | Ongoing | 23490 | 20358 | 2025-05-27
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5313138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150912568 | Ongoing | 23490 | 8091 | 2025-06-02
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5313410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115787495 | Approved | 23490 | 0 | 2025-03-13
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5314501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131900877 | Physically Completed | 23490 | 0 | 2025-06-03 | 2026-07-05
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5317564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142053759 | Ongoing | 23490 | 13050 | 2025-07-29
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5318769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115787194 | Ongoing | 23490 | 12528 | 2025-06-03
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5318966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151367417 | Ongoing | 23490 | 14877 | 2025-08-01
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5320840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150911438 | Physically Completed | 23490 | 18531 | 2025-08-01 | 2026-06-14
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5330369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115786572 | Ongoing | 23490 | 0 | 2025-06-02
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5333337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151359275 | Ongoing | 23490 | 7569 | 2025-10-14
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5335284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115786853 | Ongoing | 23490 | 15660 | 2025-06-24
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5338116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115786642 | Ongoing | 23490 | 6786 | 2025-06-12
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5341638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113936865 | Ongoing | 23490 | 21924 | 2025-05-24
SEHORE / ASHTA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/549276 — Construction of IAY House -IAY REG. NO. MP3341470 | Completed | 15030 | 15480 | 2017-05-05 | 2018-03-05
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5573431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113936638 | Ongoing | 23490 | 21924 | 2025-05-27
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5692104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150913682 | Ongoing | 23490 | 16182 | 2025-07-22
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5716583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131900234 | Approved | 23490 | 0 | 2025-07-18
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/5878789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115787869 | Approved | 23490 | 0 | 2025-04-06
SEHORE / ASHTA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/829496 — Construction of IAY House -IAY REG. NO. MP3939997 | Completed | 15480 | 14298 | 2017-12-08 | 2018-06-27
SEHORE / ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/831175 — Construction of IAY House -IAY REG. NO. MP3486191 | Completed | 15480 | 14616 | 2018-06-25 | 2018-09-25
SEHORE / ASHTA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/846644 — Construction of IAY House -IAY REG. NO. MP1446347 | Completed | 15480 | 14472 | 2017-12-04 | 2018-05-10
SEHORE / ASHTA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/899041 — Construction of IAY House -IAY REG. NO. MP2123945 | Completed | 15480 | 14172 | 2018-02-03 | 2018-06-08
SEHORE / ASHTA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/971006 — Construction of IAY House -IAY REG. NO. MP3578195 | Completed | 15480 | 15762 | 2018-02-16 | 2018-10-23
SEHORE / ASHTA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002073/IF/IAY/973911 — Construction of IAY House -IAY REG. NO. MP3643352 | Completed | 15480 | 14742 | 2018-02-16 | 2018-07-04
SEHORE / ASHTA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002073/IF/कुप निर्माण मनोहर पिता ह‍र‍ीचरण ग्रा — कुप निर्माण मनोहर पिता ह‍र‍ीचरण ग्राम बमुलिया खीची | Completed | 156400 | 121121 | 2008-05-19 | 2009-01-15
SEHORE / ASHTA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729002073/RC/138 — सी.सी रोड निर्माण कार्य बमुलिया खीची | Completed | 200000 | 46956 | 2009-11-12 | 2009-12-10
SEHORE / ASHTA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729002073/RC/147 — नवीन ग्रेवलरोड निर्माण कार्य जूनाग्राम से कांकड तक बमूलियाखीची | Completed | 498000 | 684046 | 2010-02-01 | 2011-08-03
SEHORE / ASHTA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729002073/RC/189 — नवीन ग्रेवलरोड निर्माण कार्य पुलिया से शमशान की ओर बमूलियाखीची | Completed | 499000 | 600566 | 2010-04-04 | 2011-08-03
SEHORE / ASHTA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729002073/RC/22012034155437 — ग्रेवलरोड निर्माण बमूलिया से मोलूखेडी की और | Deleted | 0 | 0 | 2012-11-19
SEHORE / ASHTA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729002073/RC/22012034155438 — ग्रेवलरोड निर्माण पखनी से शमशान तक | Deleted | 0 | 0 | 2012-11-19
SEHORE / ASHTA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729002073/RC/22012034155439 — ग्रेवलरोड निर्माण दुलीचन्‍द्र के घर से मोलूखेडी की और | Deleted | 0 | 0 | 2012-11-19
SEHORE / ASHTA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729002073/RC/22012034157887 — ग्रेवलरोड निर्माण पखनी से सिया कांकड तक | Deleted | 499000 | 0 | 2012-11-19
SEHORE / ASHTA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729002073/RC/22012034157892 — ग्रेवलरोड निर्माण बमूलिया से मोलूखेडी तक | Deleted | 499000 | 0 | 2012-11-19
SEHORE / ASHTA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034175439 — Panch Parmeswar C.C.Road T.S.No.2118 Bamuliyakhich | Completed | 205000 | 202556.4 | 2013-07-19 | 2014-02-22
SEHORE / ASHTA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034185003 — C.C.Road JANPATH + NREGA Jasmat singh ke Ghar se | Completed | 82000 | 79870 | 2013-09-24 | 2017-06-03
SEHORE / ASHTA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034185009 — पंचपरमेश्‍वर सी.सी.रोड िनर्माण कार्य मुख्‍यमार्ग ब | Completed | 204180 | 191918 | 2013-09-24 | 2014-02-28
SEHORE / ASHTA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034185717 — C.C.Road Vidhayak+NREGA T.S.No.216 Bamuliyakhichi | Completed | 82000 | 81713 | 2013-09-25 | 2016-10-07
SEHORE / ASHTA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729002073/RC/22012034202618 — khet sadak yojna bamuliyakhichi se molukhedi nale | Completed | 1186000 | 146 | 2014-02-07 | 2014-03-19
SEHORE / ASHTA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034283187 — Panch Parmeshwar CCR Main Road Puliya se Anop Singh ke Ghar tak Bamuliya Khinchi | Completed | 107000 | 105894 | 2015-08-21 | 2015-12-10
SEHORE / ASHTA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034291359 — 14 vitaye ayoge +nrega | Completed | 64000 | 64788 | 2015-12-05 | 2017-04-15
SEHORE / ASHTA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034318211 — 14 w vitta cc road babulal ke makan se panchyat bhawan babuliyakhichi | Completed | 113000 | 112694 | 2017-01-20 | 2017-07-10
SEHORE / ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034332321 — 14वॉ वित्‍त सीसी रोड डीपीआर नं- 01 से 04 तक ग्राम बमूलियाखींची | Completed | 82565 | 37152 | 2017-04-04 | 2019-05-15
SEHORE / ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034344211 — सीसी रोड मो-पुर पखनी क्र ०६ मेनरोड से शा-हेण्‍डपम्‍प | Completed | 82300 | 81528 | 2017-08-24 | 2017-10-30
SEHORE / ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034351601 — सीसी रोड मेनरोड से मनोहरसिंह के घर तक ठाकुर मोहला बमुलियाखीची | Completed | 17900 | 12384 | 2017-11-03 | 2018-10-10
SEHORE / ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034371171 — CC ROAD MAHENDRA SINGH KE GHAR SE PANDIT KE GHAR BAMULIYAKHICH | Closed | 28000 | 0 | 2017-10-02
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034385879 — सीसी रोड सुरजसिंह के मकान से देवीसिंह | Completed | 6312 | 7308 | 2018-06-04 | 2018-12-25
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034385881 — सीसी रोड राम मन्‍िदर से कमल सिंह | Completed | 2160 | 2088 | 2018-06-19 | 2018-12-25
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034385883 — सीसी रोड कन्‍नू के घर से बापू के घर तक | Completed | 9594 | 9396 | 2018-06-04 | 2018-12-20
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034385884 — सीसी रोड गजेन्‍द्र सिंह के घर से कमल सिह | Completed | 5400 | 6264 | 2018-06-23 | 2018-12-25
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034385885 — सीसी रोड माधो के घर से दरियाव के घर तक | Completed | 2100 | 1566 | 2018-06-25 | 2019-05-15
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034385887 — सीसी रोड कैलाश के घर से रामचरण के घर तक | Completed | 2100 | 2088 | 2018-06-19 | 2018-12-25
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034385889 — सीसी रोड प्रहलाद के घर से सुरजमल के घर तक | Completed | 1620 | 2088 | 2018-06-04 | 2018-08-21
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034385892 — सीसी रोड सोदान सिंह के मकान से तवरलाल के मकान तक | Completed | 6976 | 6264 | 2018-08-14 | 2018-12-30
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034385893 — सीसी रोड माता मंदिर से मुन्‍नालाल के घर तक | Completed | 42000 | 44718 | 2018-04-06 | 2018-05-30
SEHORE / ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034385895 — सीसी रोड सीताराम के घर से देवसिह के घर तक | Closed | 6000 | 0 | 2017-10-02
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034396634 — C.C.ROD NIRMAND KARYA BAMULIYA KHICHI | Completed | 56264 | 54114 | 2018-10-06 | 2020-02-15
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034396764 — Slab Puliya Nirman Karya Gram Bamuliya Kheechi | Completed | 91929 | 64984 | 2019-02-01 | 2020-04-16
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034438954 — ccroad | Deleted | 0 | 0 | 2019-01-26
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034445632 — 14wa vittay c c road nirman men road se saroop singh ke makan tak | Deleted | 0 | 0 | 2019-01-26
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034446998 — 14fc+mnrega cc road - Jagdish ke gahr se panchcyat bhawan ki or Bamuliya Khichi | Completed | 120000 | 63042 | 2019-02-28 | 2020-08-25
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034447000 — 14fc+mnrega cc road - Main road se swaroop singh ke ghar tak | Completed | 52500 | 58068 | 2019-02-28 | 2020-05-10
SEHORE / ASHTA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034472068 — 14fc+mnrega ccroad mangilal ke makan se kamal singh ke makan tak | Completed | 34425 | 34848 | 2019-08-22 | 2019-10-01
SEHORE / ASHTA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034472070 — 14fc+mnrega cc road - Lal singh ke makan se puliya ki or | Physically Completed | 83997 | 24102 | 2019-11-01 | 2021-02-01
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034532603 — 14fc+mnrega cc road - Kishan ke makan se Munnalal ke makan tak Bamulya Khichi | Completed | 40000 | 40090 | 2020-08-15 | 2020-11-01
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034532604 — 14fc+mnrega cc road - Dulichand ke makan se Ambedkar Chabutra tak Bamuliya Khichi | Completed | 67000 | 66500 | 2020-08-08 | 2020-11-20
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034550007 — 15fc+mnrega cc road - Bhagwat ke ghar se ram singh ke ghar ki or Bamuliya Khichi | Completed | 36000 | 29422 | 2021-01-11 | 2021-11-12
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034550008 — 15fc+mnrega cc road- Panchcyat Bhawan se Naveen Puliya ki or Bamuliya Khichi | Completed | 26000 | 25270 | 2020-12-21 | 2021-11-12
SEHORE / ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034563704 — cc road -Kanhaiyalal ke makan se laxman ke makan ki or Bamuliya khichi | Completed | 15300 | 12931 | 2021-04-01 | 2021-11-27
SEHORE / ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034581504 — 15fc+mnrega cc road nirman ashok ke makan se naale tak gram mohammadpur pakhni gp bamuliya khichi | Completed | 36000 | 32043 | 2021-10-10 | 2023-12-01
SEHORE / ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034598191 — 14 वा वित्त + nregs सी सी रोड निर्मान कार्य जमनाप्रसद के मकान से सजन के मकान की ओर मो.पकनी | Closed | 11000 | 0 | 2021-08-17
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034618420 — 15fc+mnrega cc road PM Road se Hemraj ke ghar ki or Mo Pakhni GP Bamuliya Khichi | Completed | 63000 | 58786 | 2023-07-04 | 2024-06-19
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034635482 — CC Road Nirman 15th Fc+Mnrega PM Road Se Satish Ke Ghar Ki Or Gram Mo.Pakhni GP Bamuliya Khichi | Completed | 76000 | 71731 | 2023-10-09 | 2024-09-21
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034645020 — CC Road Kumer singh ke ghar se Hanuman mandir ki or Bamuliya Khichi | Completed | 26000 | 25194 | 2023-12-13 | 2024-09-21
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034684012 — 15fc+narega c c rod jagdish ke ghar seRamratan and Jenpal or Rajendra ke ghar tak | Completed | 35000 | 33534 | 2024-06-21 | 2025-02-06
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/22012034841150 — 15fc Mnrega CC Road Subag Mewada ke makan se Manglik bhawan ki or Mo Pakhni GP Bamuliya Khichi | Deleted | 44000 | 0 | 2025-01-25
SEHORE / ASHTA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729002073/RC/391 — नवीन ग्रेवलरोड निर्माण कार्य तलाब वाला रास्‍ता (TS 762 ) बमूलीयाखीची | Completed | 498000 | 316556 | 2011-01-28 | 2012-03-30
SEHORE / ASHTA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729002073/RC/683 — नवीन ग्रेवलरोड निर्माण कार्य नाले से बमूलियाखीची कालोनी तक (TS NO 203) बमूलियाखची | Deleted | 493000 | 0 | 2011-04-28
SEHORE / ASHTA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729002073/RC/685 — नवीन ग्रेवलरोड निर्माण कार्य खार वाला रोड बमुलियाख | Completed | 493000 | 465598 | 2011-05-01 | 2013-07-01
SEHORE / ASHTA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729002073/RC/686 — नवीन ग्रेवलरोड निर्माण कार्य पखनी मोतीसिह के खेत स | Completed | 499000 | 1752 | 2013-06-14 | 2014-01-14
SEHORE / ASHTA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729002073/RC/687 — नवीन ग्रेवलरोड निर्माण कार्य कालोनी से मोलूखेडी तक बमुलियाखीची | Completed | 493000 | 76000 | 2011-08-11 | 2013-07-01
SEHORE / ASHTA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729002073/RC/688 — नवीन ग्रेवलरोड निर्माण कार्य बावडी वाला रोड बमुलियाखीची | Completed | 498000 | 551583 | 2011-04-15 | 2012-08-23
SEHORE / ASHTA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/746 — परमेश्‍वर योजना सी0सी0 रोड निर्माण कार्य (TSNO 674) ग्राम बमूलियाखीची | Completed | 229000 | 211686 | 2012-11-29 | 2012-12-11
SEHORE / ASHTA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002073/RC/915 — पंचपरमेश्‍वर सी0सी0 रोड निर्माण कार्य (TSNO 706)ग् | Deleted | 163000 | 0 | 2012-01-31
SEHORE / ASHTA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002073/RS/22012034312665 — sochaliya nirman dinesh/pratap | Completed | 12000 | 11847 | 2017-01-02 | 2017-10-15
SEHORE / ASHTA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002073/RS/22012034312672 — sochaliya nirman manohar/baldev | Completed | 12000 | 11847 | 2017-01-06 | 2017-08-15
SEHORE / ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002073/RS/22012034312676 — sochalaya nirman bagwan singh/bagwat | Deleted | 12000 | 0 | 2018-03-31
SEHORE / ASHTA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002073/RS/22012034319224 — sochalay nirman munala/gopal | Completed | 12000 | 11680 | 2017-03-25 | 2017-08-15
SEHORE / ASHTA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002073/RS/22012034319232 — sochalay nirmand bammuliya narendra /shivnarayan | Completed | 12000 | 11680 | 2017-03-25 | 2017-08-10
SEHORE / ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002073/RS/22012034319234 — sochalay nirman bamuliya khichi bhanvar bai /ramprasad | Completed | 12000 | 1720 | 2017-05-05 | 2017-06-25
SEHORE / ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002073/RS/22012034419679 — SOCHALAY NIRMAND RAJARAM/ANOKHILAL | Deleted | 0 | 0 | 2018-05-31
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729002073/RS/22012034485041 — sokhta gadda panchayat bhawan ke pass bamuliya khinchi | Completed | 14283.77 | 1454 | 2020-06-27 | 2023-12-29
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729002073/RS/22012034485043 — sokhta gadda nirman school ke pass bamuliya khinchi | Deleted | 0 | 0 | 2020-04-14
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729002073/RS/22012034485044 — sokhata gaddanirman hanuman mandir ke pass bamuliya khichi | Completed | 14283.77 | 1644 | 2020-06-27 | 2023-12-29
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729002073/RS/22012034485046 — sokhta gadda nirman setaram ke makan ke paas bamuliya khichi | Completed | 14283.77 | 2138 | 2020-06-27 | 2023-12-29
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729002073/RS/22012034485047 — sokhta gadda nirman hanuman mandir ke pass pakhani | Completed | 14283.77 | 2138 | 2020-06-27 | 2023-12-29
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729002073/RS/22012034485048 — sokhta gadda nirman hahijan mohalla mamuliya khichi | Completed | 14283.77 | 2024 | 2020-06-27 | 2023-12-29
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729002073/RS/22012034485070 — sokhta gadda nirman perathmik sala bhavan pakhani | Completed | 14283.77 | 1074 | 2020-06-27 | 2023-12-29
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soakage Channel for Community / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1729002073/RS/22012034496935 — सामुदायिक टायलेट निर्माण कार्य बमुलिया खीची | Completed | 44000 | 43700 | 2020-10-24 | 2021-11-27
SEHORE / ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002073/RS/22012034506953 — 15fc+mnrega Nali nirman - Ashok ke makan se nale ki or Mo. Pakhni | Closed | 30000 | 0 | 2021-02-01
SEHORE / ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002073/RS/22012034543597 — 15fc+mnrega cc nali nirman govind ke makan ki or se shyam singh ke makan ki or gp bamuliyakhichi | Completed | 30000 | 27882 | 2022-03-21 | 2023-12-14
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002073/RS/22012034694517 — Nali Nirman 15th Fc+Mnrega Main Rod Se Ram Mandir Tak Ram Mandir Se Mahen Ke Makan Tak Mo.Pakhni | Completed | 61000 | 58561 | 2023-12-05 | 2024-09-21
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002073/RS/22012035119068 — Nali nirman panchayat bhuvan se nale tak Bamuliya khichi | Closed | 0 | 0 | 2023-10-02
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002073/RS/22012035123451 — 15th Fc+ Mnrega Rcc Nali Nirman Panchayat Bhawan Se Nale Tak Bamuliya Khichi | Completed | 92000 | 90705 | 2024-02-20 | 2024-06-20
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002073/RS/22012035127081 — 15fc+narega nalli nirman bhayi ji se Atmaram ke ghar tak | Closed | 0 | 0 | 2024-03-14
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002073/RS/22012035127082 — 15fc+narega nalli nirman bhayi ji se Atmaram ke ghar tak | Closed | 14000 | 0 | 2024-03-14
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002073/RS/22012035127085 — 15fc+marega manglik bhavan and jagdisha oR Ramratan ke ghar tak Pakhni | Completed | 21000 | 6804 | 2024-07-06 | 2025-02-13
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002073/RS/22012035127086 — 15fv+nali nirman Arjun ke ghar se nale tak Pakhni | Ongoing | 21000 | 15552 | 2024-06-21
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002073/RS/22012035127381 — 15fc+mnrega Nali Nirman Bhai ji se Atmaram ke ghar tak Mo Pakhni GP Bamuliya Khichi | Closed | 14000 | 0 | 2024-03-15
SEHORE / ASHTA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1729002073/SK/1871 — Bharat Nirman Rajeev Gandhi Sewa Kendra,BAMULIYAKHECHI | Completed | 1285000 | 699163.2 | 2014-02-07 | 2018-07-12
SEHORE / ASHTA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1729002073/WC/202 — निर्मल नीर कूप निर्माण कार्य बमूलिया खीची | Completed | 195000 | 158370 | 2010-02-19 | 2011-08-03
SEHORE / ASHTA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1729002073/WC/22012034425192 — geviyan nirmand karya bamiliya khichi | Ongoing | 58000 | 5424 | 2018-10-06
SEHORE / ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1729002073/WC/22012034425199 — Pokhar Nirman Pakhni | Ongoing | 288000 | 49400 | 2020-05-22
SEHORE / ASHTA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1729002073/WC/22012034445691 — Check dam nirman - shaman ke pas Gram Bamuliya Kheechi | Deleted | 0 | 0 | 2019-01-26
SEHORE / ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1729002073/WC/22012034760858 — roof rain water harvesing bamuliya khichi | Completed | 10000 | 6699 | 2021-08-07 | 2023-12-14
SEHORE / ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1729002073/WC/22012034804615 — Roof Water Harvesting Prathmik sala bhawan ke pas gram bamuliya khichi gp bamuliya khichi | Closed | 10000 | 0 | 2021-04-21
SEHORE / ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1729002073/WC/22012034804630 — Roof Water Harvesting Prathmik Sala Bhawan Ke Pas gram mohammadpur Pakhni Gp Bamuliya Khichi | Closed | 10000 | 0 | 2021-04-21
SEHORE / ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729002073/WC/22012034804639 — 15fc+mnrega pani ki thel nirman samshan ke samne gram bamuliya khichi gram panchayat bamuliya khichi | Completed | 19000 | 15638 | 2021-10-10 | 2023-12-14
SEHORE / ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1729002073/WC/22012034812427 — CTR Roof Rain water Harvesting Anganwadi Bhawan Bamuliya Khichi | Closed | 22229.14 | 0 | 2021-06-05
SEHORE / ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1729002073/WC/22012034812429 — CTR Roof Rain water Harvesting Anganwadi Bahwan Pakhni GP Bamuliya Khichi | Closed | 22229.14 | 0 | 2021-06-05
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1729002073/WC/22012035291662 — Dugwell Recharge structure Nirmal neer Panchayat ke pas Bamuliya Khichi | Closed | 25899.46 | 6335.1 | 2025-05-26
SEHORE / ASHTA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1729002073/WC/376 — निर्मल नीर कूप निर्माण कार्य 2 {ts772} बमूलिया खीची | Completed | 236000 | 231784 | 2011-01-28 | 2012-08-23
SEHORE / ASHTA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1729002073/WC/434 — निर्मलनीर कूप निर्माण कार्य समशान पर बमूलियाखीची | Completed | 236000 | 194740 | 2011-05-01 | 2012-08-23
SEHORE / ASHTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1729002073/WC/कूप निर्माण कार्य फूलसिह पिता लालजीर — कूप निर्माण कार्य फूलसिह पिता लालजीराम बमूलिया खीची | Completed | 156000 | 193937 | 2008-05-29 | 2010-02-18
SEHORE / ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1729002073/WH/22012034443590 — TALAB PAL SUDHRIKARAN BAMULIYA KHICHI | Deleted | 0 | 0 | 2020-04-14
SEHORE / ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1729002073/WH/22012034443591 — TALAB PAL SUDHRIKARAN BAMULIYA KHICHI | Deleted | 0 | 0 | 2020-04-14
SEHORE / ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1729002073/WH/22012034446582 — तालाब गहरी करण बामूलिया खीची | Closed | 0 | 0 | 2021-01-26
SEHORE / ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1729002073/WH/22012034446583 — तालाब गहरी करण बामूलिया खीची | Closed | 0 | 0 | 2021-01-26
SEHORE / ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1729002073/WH/22012034447647 — तालाब गहरिकरण निर्माण कार्य बमुलिया खिचि | Ongoing | 444759.14 | 29200 | 2021-04-29