## Work List
Exported on: 2026-10-02 00:36:01
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: HUSAINPURKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1729002089/DP/22012034580918 — Community Plantation work Pahadi Par Husenpurkhedi | Ongoing | 427106.07 | 0 | 2023-08-07
SEHORE / ASHTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002089/IF/22012035209112 — Kapildhara Kup Nirman Rajmal so Kaniram Kamalpurkhedi | Ongoing | 277848.13 | 0 | 2024-03-12
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002089/IF/22012035227444 — Kapildhara Kup Ram singh so Than singh Kamalurkhedi GP Husenpurkhedi | Ongoing | 282417.57 | 0 | 2025-01-31
SEHORE / ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1729002089/IF/22012035240480 — Nandan Falodhyan Mukesh so Tej singh Kamalpurkhedi GP Husenpurkhedi | Ongoing | 173308.58 | 0 | 2024-07-06
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002089/IF/22012035371873 — dug well recharrge structure bharat singh/mansingh gram panchayat husenpurkhedi | Approved | 0 | 0 | 2025-04-14
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002089/IF/22012035371917 — dug well recharrge structure jeevan/man singh singh gram panchayat husenpurkhedi | Approved | 0 | 0 | 2025-04-14
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002089/IF/22012035419973 — dug well recharrge structure kumer/ranjit gram panchayat husenpurkhedi | Approved | 0 | 0 | 2025-04-14
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002089/IF/22012035447679 — Khet Talab Nirman Reena Bai wo Raghuveer Kamalpur | Ongoing | 450885.64 | 0 | 2025-05-03
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002089/IF/22012035447697 — Khet Talab nirman hiralal so patiram Husenpurkhedi | Approved | 0 | 0 | 2025-04-14
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002089/IF/22012035447705 — Khet Talab Nirman Hukam singh so Bapur singh Husenpurkhedi | Ongoing | 450885.64 | 0 | 2025-05-03
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002089/IF/22012035447732 — Khet Talab Nirman Kumer singh so ranjeet singh Kamalpur GP husenpurkhedi | Ongoing | 450885.64 | 0 | 2025-05-02
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729002089/IF/22012035598546 — Ek bagiya maa ke naam Khushu so Balram Yadav Husenpurkhedi | Ongoing | 277836.1 | 0 | 2025-09-10
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729002089/IF/22012035622010 — Ek Bagiya Maa Ke Naam Aruna wo Laxminarayan Husenpurkhedi | Ongoing | 263510.03 | 0 | 2025-09-23
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729002089/IF/22012035622015 — Ek Bagiya Maa Ke Naam Gokal Bai wo Parmeshwar Husenpurkhedi | Ongoing | 263510.03 | 0 | 2025-09-25
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/4673499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117513105 | Ongoing | 27000 | 0 | 2025-01-17
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5169360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117497916 | Ongoing | 27000 | 0 | 2025-04-18
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5232831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117877832 | Physically Completed | 23490 | 0 | 2025-05-19 | 2026-07-12
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5239371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117314336 | Completed | 23490 | 0 | 2025-04-18 | 2026-09-11
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5262649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115379961 | Ongoing | 27000 | 0 | 2025-04-18
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5283655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118522771 | Ongoing | 27000 | 0 | 2025-05-19
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5578883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117313420 | Approved | 27000 | 0 | 2025-02-04
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5722455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118305381 | Ongoing | 27000 | 4200 | 2025-09-10
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5735066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117513094 | Ongoing | 27000 | 0 | 2025-08-19
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5735090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117591273 | Ongoing | 27000 | 0 | 2025-08-19
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5743151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120584747 | Ongoing | 27000 | 0 | 2025-08-19
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5743171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117832514 | Completed | 23490 | 0 | 2025-09-10 | 2026-09-11
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5744138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117865395 | Completed | 23490 | 0 | 2025-08-19 | 2026-09-11
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5744141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117866264 | Ongoing | 27000 | 0 | 2025-09-10
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5744142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117876076 | Completed | 23490 | 0 | 2025-09-15 | 2026-09-11
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5744912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117887482 | Physically Completed | 27000 | 2100 | 2025-09-10 | 2026-09-20
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5744913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117887851 | Ongoing | 27000 | 0 | 2026-07-10
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5747875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118319119 | Ongoing | 27000 | 0 | 2025-08-19
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5748107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118150904 | Ongoing | 27000 | 0 | 2026-09-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5748577 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117852859 | Ongoing | 27000 | 2100 | 2025-09-15
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5749111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117650561 | Completed | 23490 | 0 | 2025-08-25 | 2026-09-11
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5749311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118302646 | Ongoing | 27000 | 8400 | 2025-08-19
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5957838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119310904 | Physically Completed | 23490 | 16200 | 2026-05-26 | 2026-08-16
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5957913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151170102 | Physically Completed | 23490 | 19200 | 2026-05-26 | 2026-08-23
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/5966036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115243327 | Ongoing | 27000 | 13500 | 2026-05-26
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/6178574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118290522 | Physically Completed | 23490 | 20100 | 2026-07-08 | 2026-08-23
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/6185920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118375168 | Ongoing | 27000 | 24000 | 2026-07-08
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/6187995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118354661 | Ongoing | 27000 | 7800 | 2026-07-08
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/6192203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117881149 | Ongoing | 27000 | 12000 | 2026-07-08
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/6195385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118346344 | Ongoing | 27000 | 15900 | 2026-07-08
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/6199406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118126424 | Ongoing | 27000 | 19800 | 2026-07-08
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/6202065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118072808 | Physically Completed | 27000 | 24000 | 2026-07-08 | 2026-09-27
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/6203933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117798701 | Ongoing | 27000 | 24000 | 2026-07-08
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/6204006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117803318 | Ongoing | 27000 | 0 | 2026-07-08
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002089/IF/IAY/6206426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116994879 | Ongoing | 27000 | 19800 | 2026-07-08
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002089/RC/22012034826419 — CC Road Lalu Malviya ke makan se PMGSY ki or Husenpurkhedi | Ongoing | 99000 | 0 | 2024-12-23
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002089/RC/22012034826421 — 15fc Mnrega CC Road Bhagwat Mewada ke ghar se kumer singh ke ghar ki or Kamalpurkhedi GP Husenpurkhe | Ongoing | 24000 | 0 | 2024-12-23
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002089/RS/22012035113706 — 15fc+mnrega Nali Nirman - Ramchandar ke makan se chagan malviya ke makan ki or husenpurkhedi | Ongoing | 66000 | 0 | 2023-10-04
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002089/RS/22012035131073 — PVC Pipe Nali Devi singh ke ghar se Mangilal evam Nale ki or Kamalpurkhedi GP Husenpurkhedi | Ongoing | 22000 | 0 | 2024-12-02
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002089/RS/22012035131074 — PVC Pipe Nali Devi singh ke ghar se jagdish ke ghar ki or Kamalpurkhedi GP Husenpurkhedi | Ongoing | 9000 | 0 | 2024-12-01
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002089/RS/22012035131075 — PVC Pipe Nali Anil shrivastav ke ghar se jeevan jaiswal ke ghar ki or Husenpurkhedi | Ongoing | 23000 | 0 | 2024-12-01
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1729002089/WC/22012035092164 — Contour Trenches Nirman Pahadi Par Husenpurkhedi | Ongoing | 233695 | 0 | 2023-10-16