## Work List
Exported on: 2026-10-02 04:24:25
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BHUPHOD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1729002122/FP/22012034640435 — Diversion channel Purarudhdan Patel ke khet ke pas Bhupod | Ongoing | 283525.68 | 0 | 2024-06-14
SEHORE / ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1729002122/IF/22012034904812 — Kapildhara Nirman Anar Singh Gurubagas GP Bhupod | Ongoing | 250732.62 | 0 | 2022-04-29
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1729002122/IF/22012035432583 — khet talab nirman kary ramchandar /karan singh gp bhuphod | New | 0 | 0 | 2025-04-14
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1729002122/IF/22012035515021 — kapil dhara kup nirman rahul ukar singh gp bhuphod | Approved | 0 | 0 | 2025-04-14
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1729002122/IF/22012035544475 — khet talab nirman karary radheshyam bai | New | 0 | 0 | 2025-04-14
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1729002122/IF/22012035544512 — khet talab nirman karary radheshyam bai | Approved | 450885.64 | 0 | 2025-04-14
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002122/IF/IAY/4766526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115613705 | Ongoing | 27000 | 0 | 2024-11-21
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002122/IF/IAY/4991735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113999735 | Ongoing | 27000 | 0 | 2025-05-23
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002122/IF/IAY/4996248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115613352 | Ongoing | 27000 | 0 | 2025-05-23
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002122/IF/IAY/5115616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115613410 | Ongoing | 27000 | 0 | 2025-04-16
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002122/IF/IAY/5192463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126522224 | Ongoing | 27000 | 0 | 2025-05-23
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002122/IF/IAY/5419421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115613535 | Ongoing | 27000 | 2600 | 2025-07-31
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002122/IF/IAY/5421562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118551699 | Ongoing | 27000 | 0 | 2025-07-31
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002122/IF/IAY/5422179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115634298 | Ongoing | 27000 | 0 | 2025-07-31
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002122/IF/IAY/5737551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120924291 | Physically Completed | 23490 | 0 | 2025-09-08 | 2026-07-30
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1729002122/LD/22012034595448 — बंजर एवम पड़त भूमि का समतलीकरण कब्रिस्तान के पास भूफोड | Ongoing | 405927.5 | 0 | 2023-10-03
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair & Maintenance of Storm Water Drain for Community | Solid and Liquid Waste Management | 1729002122/RS/22012035118286 — pvc paip nali nirman kary shamshan ki or | Ongoing | 22000 | 0 | 2023-10-08
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair & Maintenance of Storm Water Drain for Community | Solid and Liquid Waste Management | 1729002122/RS/22012035118318 — pvc paip nali nirman suresh patel ke ghar se rakesh parmar ke ghar tk | Ongoing | 22000 | 0 | 2023-10-08
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1729002122/WC/22012035188429 — डायवर्सन चैनल का पुनरुद्धार ग्राम भूफोड | Ongoing | 327940.45 | 0 | 2024-03-13