## Work List
Exported on: 2026-10-11 19:36:44
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: PARDI KHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coast Line Plantation of Forestry Trees for Comm / Along the coast Block Plantation of Sericulture Trees for Community | Plantation | 1729002144/DP/22012034600857 — वृक्षारोपण शांति धाम ग्राम पंचायत पारदीखेड़ी | Ongoing | 427106.07 | 38233 | 2023-08-26
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1729002144/DP/22012034616090 — Nirmal Neer Kup Nirman Shantidham Parisar Pardikhedi | Ongoing | 537251.35 | 10206 | 2024-08-22
SEHORE / ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002144/IF/22012035051516 — कपिल धारा कूप निर्मान सोभाल सिंह /हेमराज सिंह (रुपाहेडा) | Closed | 0 | 0 | 2022-10-02
SEHORE / ASHTA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002144/IF/22012035051525 — कपिल धारा कूप निर्मान गब्बुलाल /कुवर जी (पारदीखेडी) | Closed | 0 | 0 | 2022-10-02
SEHORE / ASHTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1729002144/IF/22012035093242 — कपिल धारा कुप निर्माण कार्य भुपेंद्र सिह / अजय सिंह( पारदीखेडी) | Ongoing | 278262.09 | 110218 | 2023-06-30
SEHORE / ASHTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002144/IF/22012035093263 — कपिल धारा कुप निर्माण कार्य बद्रिलाल / बोंदा जी ( पारदीखेडी) | Closed | 0 | 0 | 2023-04-14
SEHORE / ASHTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1729002144/IF/22012035093294 — कपिल धारा कुप निर्माण कार्य नारायन सिंह / भेरु लाल ( पारदीखेडी) | Ongoing | 278238.64 | 107624 | 2023-06-30
SEHORE / ASHTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1729002144/IF/22012035106734 — कपिल धारा कुप निर्माण कार्य गब्बुलाल/कुवर जी ( पारदीखेडी) | Ongoing | 278238.64 | 40439 | 2023-06-23
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002144/IF/22012035445276 — Khet Talab Nirman Asha Bai wo Vijendra Singh Pardikhedi | Physically Completed | 147621.16 | 71179.07 | 2025-05-01 | 2026-04-26
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002144/IF/22012035447854 — Khet Talab Nirman Laljriam so Ramratan Pardikhedi | Physically Completed | 55865.38 | 36488.21 | 2025-05-01 | 2026-03-28
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002144/IF/22012035447871 — Khet Talab Nirman Man singh so Mangilal Pardikhedi | Physically Completed | 55865.38 | 25004.45 | 2025-05-01 | 2026-04-15
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002144/IF/22012035448339 — Khet talab nirman ray singh so devi singh Paridikhedi | Physically Completed | 55865.38 | 19312.47 | 2025-05-01 | 2026-04-15
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002144/IF/22012035448358 — Khet Talab Nirman Ajab singh so umrav singh Pardikhedi | Physically Completed | 55865.38 | 29722.73 | 2025-05-01 | 2026-04-15
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002144/IF/22012035529542 — Dugwell Recharge Rajal bai wo Ghasiram Pardikhedi | Completed | 25899.46 | 10699.86 | 2025-05-20 | 2026-04-03
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002144/IF/22012035529563 — Dugwell Recharge Man singh so Mangilal Pardikhedi | Completed | 25899.46 | 14877 | 2025-05-20 | 2026-02-13
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002144/IF/22012035529571 — Dugwell Gangaram so Kasihram Pardikhedi | Completed | 25899.46 | 12261.46 | 2025-05-20 | 2026-04-03
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002144/IF/22012035529581 — Dugwell Recharge Tej singh so Prahlad singh Pardikhedi | Completed | 25899.46 | 12265.96 | 2025-05-20 | 2026-02-13
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002144/IF/22012035529677 — Dugwell Recharge Mangilal so Roop SIngh Pardikhedi | Completed | 25899.46 | 6523.36 | 2025-05-20 | 2026-04-03
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729002144/IF/22012035610981 — Ek bagiya maa ke naam sugan wo gangaram Pardikhedi | Ongoing | 263510.03 | 70650 | 2025-09-07
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729002144/IF/22012035635623 — Ek bagiya Maa ke naam Kunta Bai/Gansingh Gram panchayat Pardikhedi | Ongoing | 263511.37 | 66767 | 2025-10-29
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729002144/IF/22012035635626 — Ek bagiya Maa ke naam Kunta Bai Devkaran Gram panchayat Pardikhedi | Ongoing | 263511.37 | 84848 | 2025-11-03
SEHORE / ASHTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4401148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119433543 | Completed | 19890 | 19669 | 2023-12-09 | 2024-05-03
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4585282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119546042 | Completed | 23490 | 21321 | 2024-12-23 | 2026-04-01
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4673890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119358838 | Completed | 21870 | 21870 | 2024-11-22 | 2025-03-07
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4673924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119433348 | Completed | 23490 | 21717 | 2025-01-03 | 2026-04-01
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4674147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116162089 | Completed | 23490 | 22248 | 2024-12-01 | 2026-04-01
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/4674354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119771960 | Ongoing | 27000 | 18225 | 2024-09-29
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4674358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119779873 | Completed | 23490 | 21753 | 2024-10-07 | 2026-04-01
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4674360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119783778 | Completed | 21870 | 21870 | 2024-11-22 | 2025-01-22
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4675913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124186706 | Completed | 23490 | 23103 | 2024-10-28 | 2026-04-01
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4676294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123455129 | Completed | 23490 | 21708 | 2024-11-25 | 2026-04-01
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4757099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119433471 | Completed | 21870 | 21870 | 2024-11-17 | 2025-03-21
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4757105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119435691 | Completed | 23490 | 22194 | 2025-01-27 | 2026-04-01
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4758758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119089805 | Completed | 21870 | 21870 | 2024-11-11 | 2025-02-12
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4759613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119772237 | Completed | 21870 | 21627 | 2024-12-04 | 2025-02-12
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4759623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119778982 | Completed | 23490 | 21717 | 2025-01-03 | 2026-04-01
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/4759627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119783470 | Ongoing | 27000 | 18711 | 2024-12-23
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4759628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119784038 | Completed | 21870 | 21870 | 2024-12-01 | 2025-02-05
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4761239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120383825 | Completed | 23490 | 22851 | 2025-01-27 | 2026-04-01
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4879566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119433359 | Completed | 23490 | 22095 | 2025-01-27 | 2026-04-01
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/4885052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119433563 | Completed | 23490 | 21708 | 2025-02-24 | 2026-04-01
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5821723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119546077 | Physically Completed | 23490 | 23490 | 2026-02-16 | 2026-06-21
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5822043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119091592 | Physically Completed | 23490 | 23490 | 2025-11-03 | 2026-07-19
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5822044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119091705 | Physically Completed | 23490 | 22707 | 2025-10-14 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5822684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119358617 | Physically Completed | 23490 | 23490 | 2025-10-06 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5822861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119084734 | Physically Completed | 23490 | 23490 | 2025-10-13 | 2026-04-05
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5822862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119085485 | Ongoing | 27000 | 1566 | 2026-05-26
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5822952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119610816 | Physically Completed | 23490 | 23490 | 2025-11-26 | 2026-07-26
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5823109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119083094 | Physically Completed | 23490 | 23490 | 2025-10-14 | 2026-05-17
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5823326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147725717 | Physically Completed | 23490 | 23229 | 2025-10-06 | 2026-07-19
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5823800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119093407 | Physically Completed | 23490 | 23490 | 2025-10-06 | 2026-04-05
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5824043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119084051 | Physically Completed | 23490 | 23229 | 2025-12-05 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5824412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123554457 | Physically Completed | 23490 | 23490 | 2025-10-10 | 2026-07-30
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5824700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119082444 | Ongoing | 27000 | 8127 | 2026-04-08
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5824809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119433593 | Ongoing | 27000 | 19314 | 2026-03-02
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5824810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119435864 | Physically Completed | 23490 | 23490 | 2026-01-01 | 2026-06-14
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5825006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119595591 | Ongoing | 27000 | 16182 | 2026-02-27
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5825367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119093991 | Physically Completed | 23490 | 23490 | 2025-10-31 | 2026-07-26
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119779141 | Physically Completed | 23490 | 23490 | 2025-11-26 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119779237 | Physically Completed | 23490 | 23490 | 2025-10-13 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119779328 | Physically Completed | 23490 | 23490 | 2025-11-26 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119779462 | Physically Completed | 23490 | 23490 | 2025-11-26 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119779638 | Ongoing | 27000 | 23490 | 2026-01-13
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119595341 | Physically Completed | 23490 | 23490 | 2025-11-03 | 2026-07-26
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118118751 | Physically Completed | 23490 | 19836 | 2025-09-30 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119091128 | Physically Completed | 23490 | 23490 | 2025-12-03 | 2026-07-26
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119780130 | Ongoing | 27000 | 19770 | 2025-12-19
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119780598 | Physically Completed | 23490 | 23490 | 2025-11-26 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118518119 | Physically Completed | 23490 | 23490 | 2025-10-31 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119092322 | Ongoing | 27000 | 21402 | 2026-01-19
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119433460 | Physically Completed | 23490 | 23490 | 2025-10-27 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5826986 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119433507 | Physically Completed | 23490 | 23490 | 2025-10-31 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5827286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119090102 | Physically Completed | 23490 | 23490 | 2025-10-10 | 2026-04-05
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5827303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124191447 | Physically Completed | 23490 | 23490 | 2025-09-30 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5827769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126582894 | Physically Completed | 23490 | 21402 | 2026-01-08 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5828022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119092949 | Physically Completed | 23490 | 21924 | 2025-09-30 | 2026-04-12
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5828146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119092687 | Ongoing | 27000 | 21663 | 2025-10-06
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5828147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119093207 | Physically Completed | 23490 | 23490 | 2025-10-06 | 2026-03-15
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5828148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119093692 | Physically Completed | 23490 | 21924 | 2025-10-31 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5828299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148141601 | Ongoing | 27000 | 21924 | 2025-11-03
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5828573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124233208 | Physically Completed | 23490 | 20880 | 2025-09-30 | 2026-08-16
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5844420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116162019 | Physically Completed | 23490 | 23490 | 2026-04-01 | 2026-05-17
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5844700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119771704 | Physically Completed | 23490 | 23490 | 2025-12-18 | 2026-04-12
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5844701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119771819 | Ongoing | 27000 | 16443 | 2026-01-29
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5844702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119771874 | Physically Completed | 23490 | 21141 | 2026-01-07 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5844704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119772553 | Ongoing | 27000 | 23490 | 2026-02-06
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5844705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119772901 | Physically Completed | 23490 | 23490 | 2025-12-19 | 2026-07-26
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5844748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119771068 | Physically Completed | 23490 | 23490 | 2025-12-05 | 2026-07-30
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5844832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119774490 | Physically Completed | 23490 | 23229 | 2026-01-07 | 2026-06-28
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5845189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119435565 | Completed | 23490 | 23490 | 2025-12-05 | 2026-08-05
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5845454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148141479 | Physically Completed | 23490 | 23490 | 2025-12-05 | 2026-05-10
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5845641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119773832 | Physically Completed | 23490 | 23490 | 2025-12-19 | 2026-04-12
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5845642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119773967 | Ongoing | 27000 | 21663 | 2026-01-13
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5845643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119774013 | Physically Completed | 23490 | 23490 | 2026-01-20 | 2026-07-30
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5846038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148158723 | Ongoing | 27000 | 1827 | 2026-04-08
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5846055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119435594 | Completed | 23490 | 23490 | 2025-12-05 | 2026-08-05
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5846056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119435611 | Physically Completed | 23490 | 23490 | 2025-12-05 | 2026-04-05
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5878398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119784271 | Ongoing | 27000 | 20097 | 2026-04-07
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5878399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119785171 | Ongoing | 27000 | 14616 | 2026-05-14
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5878400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119785293 | Ongoing | 27000 | 14355 | 2026-02-16
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5878401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119785367 | Physically Completed | 23490 | 21663 | 2026-02-10 | 2026-07-30
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5878402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118123548 | Ongoing | 27000 | 19314 | 2026-04-01
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5878434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119433400 | Physically Completed | 23490 | 23490 | 2026-02-02 | 2026-04-05
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5878562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119774199 | Physically Completed | 23490 | 23490 | 2026-02-10 | 2026-05-17
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002144/IF/IAY/5878563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119774577 | Physically Completed | 23490 | 23490 | 2026-02-10 | 2026-06-28
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5878564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119779556 | Ongoing | 27000 | 18009 | 2026-04-09
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/5878565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119780692 | Ongoing | 27000 | 21924 | 2026-02-16
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/6186042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119783936 | Ongoing | 27000 | 8400 | 2026-03-24
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/6189039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119094082 | Ongoing | 27000 | 10500 | 2026-03-26
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/6197648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119772129 | Ongoing | 27000 | 8400 | 2026-03-24
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/6202021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114161634 | Ongoing | 27000 | 12798 | 2026-06-12
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/6202663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123556598 | Ongoing | 27000 | 0 | 2026-03-24
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/6210728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119783710 | Ongoing | 27000 | 14154 | 2026-06-01
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/6212196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119784342 | Approved | 27000 | 0 | 2025-05-10
SEHORE / ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/6257963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119773327 | Approved | 27000 | 0 | 2025-03-13
SEHORE / ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/6285679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119546031 | Approved | 27000 | 0 | 2025-11-17
SEHORE / ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002144/IF/IAY/6370746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148844727 | Ongoing | 27000 | 0 | 2026-09-03
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1729002144/LD/22012034592976 — शांतिधाम निर्माण कार्य पारदीखेड़ी | Completed | 329561.83 | 290710.32 | 2023-10-05 | 2026-05-21
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002144/RC/22012034630014 — 15fc+mnrega CC Road Nirman - Ajay singh ke makan se Handpump ki or Pardikhedi | Completed | 42000 | 41769 | 2023-04-25 | 2024-10-09
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002144/RC/22012034646514 — 15fc+mnrega CC Road - Gajraj singh ke ghar se harisingh ke ghar ki or Pardikhedi | Completed | 43000 | 42704 | 2023-08-03 | 2024-11-22
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1729002144/RC/22012034657412 — 15fc+mnrega CC Road Radheshyam ke ghar se Chowk ki or Pardikhedi | Ongoing | 40000 | 37422 | 2024-07-17
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002144/RC/22012034822772 — 15fc Mnrega CC Road Pump House se vikram ke ghar ki or Pardikhedi | Completed | 36000 | 34506 | 2024-09-09 | 2024-11-22
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1729002144/RC/22012034822785 — CC Road Gajraj singh ke makan se Narbat singh ke ghar ki or Pardikhedi | Ongoing | 84000 | 75600 | 2024-09-25
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002144/RS/22012034690620 — 15fc+mnrega Nali Nirman - Ambedkar Chabutare se Nale ki or Pardikhedi | Completed | 18000 | 17918 | 2023-05-10 | 2024-10-09
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002144/RS/22012034690621 — 15fc+mnrega Nali Nirman - Jagannath ke makan se Prahlad singh ke makan ki or Pardikhedi | Completed | 39000 | 38334 | 2023-05-27 | 2024-10-09
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1729002144/RS/22012034696455 — नाली निर्माण कार्य पीएम सड़क हेंडपंप से देव बाबा के ओडले की और | Completed | 64000 | 63427 | 2023-07-12 | 2024-10-09
SEHORE / ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002144/RS/22012035112852 — 15fc+mnrega Nali Nirman - Hari singh ke ghar se Ram mandir ki or Pardikhedi | Closed | 63000 | 0 | 2023-09-25
SEHORE / ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002144/RS/22012035126338 — 15fc+mnrega Nali Nirman - Balram ke ghar se Nale ki or Rupaheda GP Pardikheda | Completed | 57000 | 56688 | 2024-04-24 | 2024-11-22
SEHORE / ASHTA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1729002144/RS/22012035131204 — 15fc Mnrega Nali Nirman School se Ram Mandir ki or Rupaheda GP Pardikhedi | Ongoing | 58000 | 52200 | 2025-07-26
SEHORE / ASHTA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1729002144/RS/22012035138991 — 15FC mnrega RCC nali nirman kripal singh ke ghar se lakhan singh ke ghar ki or gram rupakheda | Approved | 47000 | 0 | 2025-11-15
SEHORE / ASHTA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1729002144/RS/22012035139003 — Rcc nali nirman gram rupakheda | Approved | 0 | 0 | 2025-04-14
SEHORE / ASHTA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1729002144/RS/22012035139004 — Rcc nali nirman gram rupakheda | Approved | 47000 | 0 | 2025-04-14
SEHORE / ASHTA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1729002144/RS/VB/YD/22012035140051 — Construction of Soak Pit Nirman Samudayik Bhawan Ke Pass | Ongoing | 29241.15 | 0 | 2026-09-29
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1729002144/WC/22012035121972 — Pokhar Nirman Dharamraj Maharaj ke khet ke pas Pardikhedi | Physically Completed | 385261.22 | 344158.28 | 2023-10-05 | 2026-04-03
SEHORE / ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1729002144/WC/22012035121978 — Pokhar Nirman Karya Laljiram ke khet ke pas Pardikhedi | Physically Completed | 385261.22 | 323548.68 | 2023-11-27 | 2026-04-03
SEHORE / ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1729002144/WC/22012035291641 — Dugwell Recharge Nirmal Neer ke pas Pardikhedi | Approved | 25899.46 | 0 | 2025-04-14