## Work List
Exported on: 2026-10-02 16:47:25
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: GUNDRAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RAISEN / SANCHI | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1730001082/AV/22012034628481 — BOUNDARY WALL NIRAMAN (PRATHMIK SHALA NEEMDHANA) Gundrai | Completed | 108000 | 106592.71 | 2023-02-02 | 2023-03-30
RAISEN / SANCHI | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1730001082/AV/22012034629576 — BOUNDARY WALL (PRATHMIK SHALA NEEMDHANA) NEEMDHANA | Closed | 0 | 0 | 2022-04-14
RAISEN / SANCHI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Cyclone shelter for Community / Construction of Cyclone shelter for Community | Construction of Other Community Building/Assets | 1730001082/AV/22012034643128 — Shantidham Nirman Kary (Tola Donga) Gundrai | Completed | 226381.46 | 196264.81 | 2025-01-03 | 2025-04-15
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1730001082/AV/22012034643129 — Shantidham Nirman Kary (Neemdhana Tola) Gundrai | Completed | 226381.46 | 176506.65 | 2023-12-30 | 2024-08-25
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1730001082/AV/22012034644785 — Kachchi Boundary Wall Nirman (Shantidham Neemdhana) Gundrai | Deleted | 0 | 0 | 2023-08-15
RAISEN / SANCHI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1730001082/AV/22012034651096 — SHANTIDHAM BOULDER BOUNDRY WALL CHANDANGODA | Completed | 359272.47 | 312488.98 | 2025-01-03 | 2026-03-01
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1730001082/AV/22012034651097 — SHANTIDHAM BOULDER BOUNDRY WALL GUNDRAI TOLA | Completed | 295014.67 | 236994.99 | 2024-03-06 | 2026-03-01
RAISEN / SANCHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1730001082/DP/22012034597920 — AMRIT VATIKA NIRMAN ( HAIGH SCHOOL KE PAS)GUNDRAI | Ongoing | 55847.4 | 8840 | 2023-09-09
RAISEN / SANCHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1730001082/DP/22012034609171 — Samudayik Plantation (Shantidham Ke Pas) Chandangoda | Physically Completed | 427106.07 | 174091 | 2024-07-16 | 2026-06-19
RAISEN / SANCHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1730001082/DP/22012034612287 — SAMUDAYIK VRAKSHAROPAN KARYA SHANTIDHAM GUNDRAI TOLA | Closed | 0 | 0 | 2023-10-02
RAISEN / SANCHI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1730001082/IF/22012035035447 — SOAK PIT NIRMAN (SITA RAM / GOKAL PRASAD) CHANDANGODA | Completed | 9814.23 | 7321.31 | 2022-12-22 | 2023-03-25
RAISEN / SANCHI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1730001082/IF/22012035035450 — SOAK PIT NIRMAN (SANTOSH / BIHARI LAL) CHANDANGODA | Closed | 9814.23 | 0 | 2022-10-02
RAISEN / SANCHI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1730001082/IF/22012035035456 — SOAK PIT NIRMAN (POORAN SINGH / KALURAM) CHANDANGODA | Completed | 9814.23 | 7377.28 | 2022-12-23 | 2023-03-30
RAISEN / SANCHI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1730001082/IF/22012035035459 — SOAK PIT NIRMAN (MULCHAND / MUSHADDI LAL) CHANDANGODA | Closed | 9814.23 | 0 | 2022-10-02
RAISEN / SANCHI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1730001082/IF/22012035035464 — SOAK PIT NIRMAN (LAL JI PRASAD / BABULAL) CHANDANGODA | Completed | 9814.23 | 7376.12 | 2023-01-13 | 2023-03-30
RAISEN / SANCHI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1730001082/IF/22012035035466 — SOAK PIT NIRMAN (RATAN LAL / MANGALIYA) CHANDANGODA | Completed | 9814.23 | 7376.12 | 2022-12-23 | 2023-03-30
RAISEN / SANCHI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1730001082/IF/22012035035470 — SOAK PIT NIRMAN (GUDDU / GOKAL PRASAD) CHANDANGODA | Completed | 9814.23 | 7376.12 | 2023-01-13 | 2023-03-30
RAISEN / SANCHI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1730001082/IF/22012035035472 — SOAK PIT NIRMAN (MANISHA BAI / HARINAYARAYN) CHANDANGODA | Completed | 9814.23 | 7376.12 | 2022-12-23 | 2023-03-30
RAISEN / SANCHI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1730001082/IF/22012035035474 — SOAK PIT NIRMAN (PHOOL SINGH / BHANVAR LAL) CHANDANGODA | Completed | 9814.23 | 7376.12 | 2022-12-23 | 2023-03-30
RAISEN / SANCHI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1730001082/IF/22012035035476 — SOAK PIT NIRMAN (NARAYAN SINGH / MOHAR SINGH) CHANDANGODA | Completed | 9814.23 | 7377.28 | 2023-01-13 | 2023-03-30
RAISEN / SANCHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1730001082/IF/22012035141635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106020397 | Completed | 19890 | 18564 | 2023-08-29 | 2023-12-14
RAISEN / SANCHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1730001082/IF/22012035141636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106020437 | Completed | 19890 | 18564 | 2023-08-29 | 2023-11-01
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730001082/IF/22012035155340 — Nadep (Prakash/ Ram Charan) Chandangoda | Deleted | 0 | 0 | 2023-08-15
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730001082/IF/22012035155341 — Nadep (Ram Swaroop/ Ram Charan) Chandangoda | Deleted | 0 | 0 | 2023-08-15
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730001082/IF/22012035155343 — Nadep (Govind Singh/ Shankar Lal) Chandangoda | Deleted | 0 | 0 | 2023-08-15
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730001082/IF/22012035155347 — Nadep (Shekhar/ Pratap) Chandangoda | Deleted | 0 | 0 | 2023-08-15
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730001082/IF/22012035155349 — Nadep (Sumit/ kanhaiyalal) Chandangoda | Deleted | 0 | 0 | 2023-08-15
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1730001082/IF/22012035170548 — Nadep Hit (Prakash/ Ram, Ram Swaroop/ Ram, Govind/ Shan, Shekhar/ Pra, Sumit/ Khanai.) Chandangoda | Closed | 0 | 0 | 2023-08-15
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730001082/IF/22012035449486 — KHET TALAB HEMANT JAT/ LAKHAN SINGH JAT CHANDANGODA | Completed | 323079.24 | 246738 | 2025-05-03 | 2026-02-26
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730001082/IF/22012035571190 — JGSA Khet TALAB KAILASH / KHET SINGH GRAM GUNDRAI | Completed | 55865.38 | 42804 | 2025-06-20 | 2026-02-19
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730001082/IF/22012035571195 — JGSA KHET TALAB DIWAN SINGH / JAGRAJ SINGH GRAM GUNDRAI | Completed | 55865.38 | 42804 | 2025-06-20 | 2026-02-19
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035583890 — EK BAGIYA MA KE NAAM PARWATI BAI GRAM GUNDRAI | New | 0 | 0 | 2025-06-05
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035583896 — EK BAGIYA MA KE NAAM PHULWATI GRAM CHANDANGODA | New | 0 | 0 | 2025-06-05
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035597838 — EK BAGIYA MA KE NAAM SULOCHANA / OMPRAKASH GRAM GUNDRAI | New | 0 | 0 | 2025-06-05
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035600026 — EK BAGIYA MA KE NAAM SULOCHAMA / OMPRAKASH GRAM GUNDRAI | Approved | 0 | 0 | 2025-06-05
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035600027 — EK BAGIYA MA KE NAAM PARWATI BAI / MADANLAL GRAM GUNDRAI | Approved | 0 | 0 | 2025-06-05
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035600030 — EK BAGIYA MA KE NAAM BAIJANTI BAI / BHOLERAM GRAM GUNDRAI | Approved | 0 | 0 | 2025-06-05
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730001082/IF/22012035600033 — EK BAGIYA MA KE NAAM PHULWATI BAI GRAM CHANDANGODA | Closed | 172217.65 | 0 | 2025-06-05
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730001082/IF/22012035600036 — EK BAGIYA MA KE NAAM KISHORI GRAM CHANDANGODA | Closed | 172217.65 | 0 | 2025-06-05
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035600635 — EK BAGIYA MA KE NAAM BABLI BAI GRAM CHANDANGODA | Approved | 0 | 0 | 2025-06-05
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035604782 — EK BAGIYA MA KE NAAM PHULWATI BAI GRAM CHANDANGODA | Ongoing | 129651.41 | 69899.35 | 2025-09-05
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035604787 — EK BAGIYA MA KE NAAM KISHORI GRAM CHANDANGODA | Ongoing | 129651.41 | 77729.35 | 2025-09-05
RAISEN / SANCHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4384457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106020397 | Closed | 0 | 0 | 2022-11-11
RAISEN / SANCHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4384458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106020437 | Closed | 0 | 0 | 2022-11-11
RAISEN / SANCHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4387280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116112301 | Completed | 18360 | 18054 | 2023-03-09 | 2023-08-18
RAISEN / SANCHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4393625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148130292 | Completed | 18360 | 18343 | 2023-06-19 | 2023-10-11
RAISEN / SANCHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4411308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148129933 | Completed | 19890 | 18564 | 2023-12-17 | 2024-04-21
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4538465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106020383 | Completed | 21870 | 21870 | 2024-09-24 | 2025-01-13
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4538467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106020542 | Completed | 23490 | 21717 | 2024-09-24 | 2025-04-16
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4541415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105613620 | Completed | 21870 | 21870 | 2024-09-24 | 2025-01-13
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4541417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105613712 | Completed | 21870 | 21870 | 2024-09-24 | 2025-01-13
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4541419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105613971 | Completed | 23490 | 22149 | 2024-09-24 | 2025-11-10
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4564920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115976852 | Completed | 21870 | 21870 | 2024-09-24 | 2025-01-13
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4658099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148129923 | Completed | 23490 | 22149 | 2024-09-24 | 2025-08-29
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4658100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148129943 | Completed | 23490 | 22365 | 2024-09-24 | 2025-10-06
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4658101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148129955 | Completed | 21870 | 21870 | 2024-11-09 | 2025-03-06
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4658102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148129971 | Completed | 21870 | 21870 | 2024-09-24 | 2025-02-06
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4658103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148130257 | Completed | 21870 | 21870 | 2024-09-24 | 2025-03-06
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4658111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148131257 | Completed | 21870 | 21870 | 2024-11-15 | 2025-02-26
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4737416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105613633 | Completed | 21870 | 21627 | 2024-11-09 | 2025-02-26
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4760025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120676488 | Completed | 21870 | 21870 | 2024-11-09 | 2025-03-15
RAISEN / SANCHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/4775795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115976971 | Completed | 23490 | 21870 | 2024-11-09 | 2025-04-16
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/5825435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106019580 | Completed | 23490 | 23490 | 2025-10-10 | 2026-01-20
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/5826632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106020403 | Completed | 23490 | 23490 | 2025-10-10 | 2025-12-20
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/5827384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115103305 | Completed | 23490 | 23490 | 2025-10-10 | 2026-02-01
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/5844129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105613669 | Completed | 23490 | 23490 | 2025-11-20 | 2026-03-26
RAISEN / SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730001082/IF/IAY/5846168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148129884 | Completed | 23490 | 23490 | 2025-11-23 | 2026-03-09
RAISEN / SANCHI | 2024-2025 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1730001082/LD/22012034945045 — NALI NIRMAN JASWANT NAYAK KE GHAR SE PARSHOTTAM NAYAK KE GHAR KI AUR | Completed | 117000 | 60102 | 2025-03-14 | 2026-05-02
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730001082/RC/22012034640040 — CC ROAD (GOVARDHAN KE MAKAN SE MAIN ROAD & SUKMA KE MAKAN SE MAIN ROAD KI AUR) CHANDANGODA | Completed | 41000 | 40443 | 2023-07-01 | 2023-08-03
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730001082/RC/22012034652175 — CC ROAD (RADHESHYAM KE GHAR SE MANDIR KI AUR HOTE HUYE GOPILAL KE GHAR SE VEDPRAKASH TAK CHANDANGODA | Completed | 42300 | 41706 | 2023-10-09 | 2024-09-10
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730001082/RC/22012034652177 — CC ROAD (BABU KE GHAR SE CHARAN KE GHAR KI AUR HOTE HUYE MATA MANDIR KE PAS) GUNDRAI LAL ) | Completed | 42300 | 41990 | 2023-10-09 | 2024-05-27
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730001082/RC/22012034652179 — CC ROAD (KAILASH KE GHAR SE HAR PRASAD KE GHAR KI AUR) GUNDRAI | Completed | 36000 | 34918 | 2023-09-17 | 2024-01-12
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730001082/RC/22012034680785 — CC ROAD (RAKESH KE GHAR SE BALLU KE GHAR KI AUR) CHANDANGODA | Closed | 0 | 0 | 2023-04-14
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730001082/RC/22012034680786 — CC ROAD (RAKESH KE GHAR SE BALLU KE GHAR KI AUR) CHANDANGODA | Completed | 44000 | 43506 | 2024-03-17 | 2024-09-10
RAISEN / SANCHI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730001082/RC/22012034829696 — CC ROAD SARDAR SINGH KE GHAR SE MANGI LAL KE GHAR KI AUR | Completed | 50000 | 46872 | 2025-02-24 | 2025-07-14
RAISEN / SANCHI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1730001082/RC/22012034846895 — CC ROAD JASWANT NAYAK KE GHAR SE PUROSHOTTAM NAYAK KE GHAR KI AUR | Approved | 50000 | 0 | 2025-04-14
RAISEN / SANCHI | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1730001082/RC/VB/YD/22012034854612 — Constr of Cement Concrete Roads for Comm GUNDRAI | Approved | 0 | 0 | 2026-09-02
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730001082/RS/22012034696883 — NALI RCC (DALPAT NAYAK KE GHAR SE BALIRAM NAYAK KE GHAR KI AUR) GUNDRAI TOLA | Completed | 55000 | 54587 | 2023-06-10 | 2023-07-28
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730001082/RS/22012034705943 — Kachchi Nali Nirman (Balaram Nayak Ke Ghar se Puliya Ki Aur) Gundrai Tola | Deleted | 0 | 0 | 2023-08-15
RAISEN / SANCHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1730001082/RS/22012034705955 — Nadep (Prakash/ Ram Charan) Chandangoda | Deleted | 0 | 0 | 2023-08-15
RAISEN / SANCHI | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1730001082/RS/VB/YD/22012035139953 — Construction of Soak Pit for 1 | Approved | 27804.31 | 0 | 2026-07-25
RAISEN / SANCHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1730001082/WC/22012035114540 — bolder chack dam (gulab ke ghar ke pas nadi par) chandangoda | Closed | 0 | 0 | 2023-04-14
RAISEN / SANCHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1730001082/WC/22012035220242 — Pashu Hoj Shantidham ke pas Gundrai Tola | Approved | 10000 | 0 | 2024-04-14
RAISEN / SANCHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1730001082/WC/22012035225553 — PASHU HOJ NIRMAN PANI KI TANKI KE PAS | Completed | 10000 | 8991 | 2025-02-17 | 2025-05-21
RAISEN / SANCHI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1730001082/WC/VB/YD/22012035334986 — Constr of Masonry/CC Anicut for 1 GUNDRAI | Approved | 0 | 0 | 2026-07-25